## Sheet1
Exhaust Fan Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
EF No.: | EF-1 | Serving: |  | Toilet 69 & Toilet 71
Section 1 - Submittal / Approvals
Submittal. The above HVAC Equipment and subsystems critical to them are complete and ready for functional performance testing. The installation/ start-up checklist items are complete and have been checked off only by the parties having direct knowledge of the event, as marked below, respective to each responsible contractor. The prefunctional checklist is submitted for approval, subject to a list of outstanding items remaining to be completed. This checklist will be updated upon the completion of any outstanding items. None of the outstanding items (if listed) preclude safe and relieable functional performance tests from being conducted.
Electrical Contractor |  |  | Date
The items on the Prefunctional Checklist are to be completed as part of the startup and initial checkout prior to the start of any functional performance testing. This checklist does not take the place of the equipment manufacturer's recommended checkout and startup procedures. Contractors asigned responsibility for specific sections of the checklist will be responsible to verify that checklist items by their subcontractors are complete and checked off. Contractor coulmns on the checklist sheets refer to the contractor responsible to verify that the item has been completed. A/E-Architect/Engineer, ATC-Automatic Temperature Controls Contractor, CA-Commissioning Agent, EC-Electrical Contractor, MC-Mechancial Contractor, TAB-Test and Balance Contractor.
Approvals. This filled out, completed checklist has been reviewed. Its completion is approved with any exceptions noted below.
Commissioning Agent |  |  | Date |  | Owners Representative |  |  | Date
Eastern Air Balance Corporation
Exhaust Fan Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
EF No.: | EF-1 | Serving: |  | Toilet 69 & Toilet 71
Section 6 - Operational Checks
The following Prefunctional Checklist items are to be completed and signed of on for each Exhaust Fan as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  |  | Date | Contractor |  | Initials | Comments
Electrical wiring complete to fan. |  |  |  | EC
Verify proper fan rotation. |  |  |  | EC
Voltage Check
Unit Rated Voltage = 115 Volts / 1Ø |  |  |  | EC
Actual Voltage = Volts |  |  |  | EC
Actual voltage is within +/- 5% of rated voltage |  |  |  | EC
Notes: