## Sheet1
Pump Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
Pump No.: | P-1A | Serving: |  | Hot Water
Section 1 - Submittal / Approvals
Submittal. The above HVAC Equipment and subsystems critical to them are complete and ready for functional performance testing. The installation/ start-up checklist items are complete and have been checked off only by the parties having direct knowledge of the event, as marked below, respective to each responsible contractor. The prefunctional checklist is submitted for approval, subject to a list of outstanding items remaining to be completed. This checklist will be updated upon the completion of any outstanding items. None of the outstanding items (if listed) preclude safe and relieable functional performance tests from being conducted.
Mechanical Contractor |  |  | Date
The items on the Prefunctional Checklist are to be completed as part of the startup and initial checkout prior to the start of any functional performance testing. This checklist does not take the place of the equipment manufacturer's recommended checkout and startup procedures. Contractors asigned responsibility for specific sections of the checklist will be responsible to verify that checklist items by their subcontractors are complete and checked off. Contractor coulmns on the checklist sheets refer to the contractor responsible to verify that the item has been completed. A/E-Architect/Engineer, ATC-Automatic Temperature Controls Contractor, CA-Commissioning Agent, EC-Electrical Contractor, MC-Mechancial Contractor, TAB-Test and Balance Contractor.
Approvals. This filled out, completed checklist has been reviewed. Its completion is approved with any exceptions noted below.
Commissioning Agent |  |  | Date |  | Owners Representative |  |  |  |  | Date
Eastern Air Balance Corporation
Pump Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
Pump No.: | P-1A | Serving: |  | Hot Water
Section 2 - Requested Documentation Submitted
One (1) Electronic Copy of the requested documentation listed below shall be provided to the Commissioning Authority by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Required Documentation |  |  | Date | Contractor |  | Initials |  | Comments
Manufacturers Product Data Sheets |  |  |  | MC
Manufacturers Performance Data (Pump Curves) |  |  |  | MC
Manufacturers Installation Manual |  |  |  | MC
Manufacturers Operation / Maintenance Manual |  |  |  | MC
Manufacturers Troubleshooting Guide |  |  |  | MC
Notes:
Section 3 - Model Verification
The following information is to be provided by the contractor indicated. Initial and date when completed. Enter any comments for deficient items. 1 = as specified, 2 = as submitted, 3 = as installed.
Required Documentation |  |  | P-1A |  | Contractor |  | Date | Initials | Comments
Pump Manufacturer |  | 1
|  | 2 | Armstrong |  | CA |  | 2020-06-10 | DTR
|  | 3 |  |  | MC
Pump Model Number |  | 1
|  | 2 | Series 4030 3x2x10 |  | CA |  | 2020-06-10 | DTR
|  | 3 |  |  | MC
Pump Serial Number |  | 3 |  |  | MC
Notes:
Pump Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
Pump No.: | P-1A | Serving: |  | Hot Water
Section 4 - Installation Documentation Record
The following Prefunctional Checklist items are to be completed and signed of on for each Hydronic Pump as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  |  | Date | Contractor |  | Initials |  | Comments
Pump has been permanently labeled. |  |  |  | MC
Vibration isolation devices installed and functional. |  |  |  | MC
Pump set in place and properly grouted. |  |  |  | MC
Temperature and pressure wells and gauges installed. |  |  |  | MC
Pump has been properly lubricated. |  |  |  | MC
All piping connections have been completed and all piping is properly supported. |  |  |  | MC
All piping thermal insulation has been completed. |  |  |  | MC
All piping has been properly labeled. |  |  |  | MC
Construction strainers have been removed. |  |  |  | MC
Final strainers are clean and in place. |  |  |  | MC
All hydronstatic testing or piping system is complete. |  |  |  | MC
All system valves have been installed and left in the fully open position. |  |  |  | MC
Notes:
Pump Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
Pump No.: | P-1A | Serving: |  | Hot Water
Section 4 - Installation Documentation Record
The following Prefunctional Checklist items are to be completed and signed of on for each Hydronic Pump as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  |  | Date | Contractor |  | Initials |  | Comments
Pump VFD wired to controlled equipment. |  |  |  | MC
Pump VFD size (HP) matches Pump motor size (HP) |  |  |  | MC
Pump VFD is located away from excessive temperature. |  |  |  | MC
Pump VFD is located away from excessive moisture. |  |  |  | MC
Pump VFD has been fully programmed and a written copy of all programmed operating parameters is provided. |  |  |  | MC
Notes:
Pump Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
Pump No.: | P-1A | Serving: |  | Hot Water
Section 6 - Operational Checks
The following Prefunctional Checklist items are to be completed and signed of on for each Hydronic Pump as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  |  | Date | Contractor |  | Initials |  | Comments
No excessive pump noise or vibration. |  |  |  | MC
No apparent leakage at pump seals. |  |  |  | MC
Amperage Check
Motor Rated Amperage = Amps |  |  |  | MC
Actual Amperage L1 / L2 = Amps |  |  |  | MC
Actual Amperage L1 / L3 = Amps |  |  |  | MC
Actual Amperage L2 / L3 = Amps |  |  |  | MC
Rated Motor Service Factor = |  |  |  | MC
Rated Motor S.F. Amperage = Amps |  |  |  | MC
Verify that the actual operating motor amperage is less than the rated motor amperage. |  |  |  | MC
Notes: