## Sheet1
Exhaust Fan Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
Fan No.: | EF-1 | Serving: |  | Toilet 69 & Toilet 71
Section 1 - Submittal / Approvals
Submittal. The above HVAC Equipment and subsystems critical to them are complete and ready for functional performance testing. The installation/ start-up checklist items are complete and have been checked off only by the parties having direct knowledge of the event, as marked below, respective to each responsible contractor. The prefunctional checklist is submitted for approval, subject to a list of outstanding items remaining to be completed. This checklist will be updated upon the completion of any outstanding items. None of the outstanding items (if listed) preclude safe and relieable functional performance tests from being conducted.
Mechanical Contractor |  |  | Date
The items on the Prefunctional Checklist are to be completed as part of the startup and initial checkout prior to the start of any functional performance testing. This checklist does not take the place of the equipment manufacturer's recommended checkout and startup procedures. Contractors asigned responsibility for specific sections of the checklist will be responsible to verify that checklist items by their subcontractors are complete and checked off. Contractor coulmns on the checklist sheets refer to the contractor responsible to verify that the item has been completed. A/E-Architect/Engineer, ATC-Automatic Temperature Controls Contractor, CA-Commissioning Agent, EC-Electrical Contractor, MC-Mechancial Contractor, TAB-Test and Balance Contractor.
Approvals. This filled out, completed checklist has been reviewed. Its completion is approved with any exceptions noted below.
Commissioning Agent |  |  | Date |  | Owners Representative |  |  |  |  | Date
Eastern Air Balance Corporation
Exhaust Fan Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
Fan No.: | EF-1 | Serving: |  | Toilet 69 & Toilet 71
Section 2 - Requested Documentation Submitted
One (1) Electronic Copy of the requested documentation listed below shall be provided to the Commissioning Authority by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Required Documentation |  |  | Date | Contractor |  | Initials |  | Comments
Manufacturers Product Data Sheets |  |  |  | MC
Manufacturers Installation Manual |  |  |  | MC
Manufacturers Operation / Maintenance Manual |  |  |  | MC
Manufacturers Troubleshooting Guide |  |  |  | MC
Notes:
Section 3 - Model Verification
The following information is to be provided by the contractor indicated. Initial and date when completed. Enter any comments for deficient items. 1 = as specified, 2 = as submitted, 3 = as installed.
Required Documentation |  |  | EF-1 |  | Contractor |  | Date | Initials | Comments
Exhaust Fan Manufacturer |  | 1
|  | 2 | Cook |  | CA |  | 2020-06-10 | DTR
|  | 3 |  |  | MC
Exhaust Fan Model Number |  | 1
|  | 2 | 90C15DH |  | CA |  | 2020-06-10 | DTR
|  | 3 |  |  | MC
Exhaust Fan Serial Number |  | 3 |  |  | MC
Notes:
Exhaust Fan Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
Fan No.: | EF-1 | Serving: |  | Toilet 69 & Toilet 71
Section 4 - Installation Documentation Record
The following Prefunctional Checklist items are to be completed and signed of on for each Exhaust Fan as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  |  | Date | Contractor |  | Initials |  | Comments
Exhaust Fan has been permanently labeled. |  |  |  | MC
Exhaust Fan casing is is good condition / no dents or damage. |  |  |  | MC
All shipping bolts have been removed and fan mountings checked. |  |  |  | MC
Fan wheel rotates freely. |  |  |  | MC
Backdraft damper installed and operates freely. |  |  |  | MC
Exhaust duct system is complete and all exhaust grilles have been installed. |  |  |  | MC
All volume dampers installed as indicated on the drawings and left in full open position. |  |  |  | MC
Notes:
Exhaust Fan Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
Fan No.: | EF-1 | Serving: |  | Toilet 69 & Toilet 71
Section 6 - Operational Checks
The following Prefunctional Checklist items are to be completed and signed of on for each Exhaust Fan as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  |  | Date | Contractor |  | Initials |  | Comments
No fan noise or excessive vibration. |  |  |  | MC
Amperage Check
Motor Rated Amperage = Amps |  |  |  | MC
Actual Motor Amperage = Amps |  |  |  | MC
Rated Motor Service Factor = |  |  |  | MC
Rated Motor S.F. Amperage = Amps |  |  |  | MC
Verify that the actual operating motor amperage is less than the rated motot amperage. |  |  |  | MC
Notes: