IN THE VILLAGE OF CENTERTOWN, MISSOURI

Bill No. 0020-021 Ordinance No. \_214

AN ORDINANCE AUTHORIZING THE CHAIRMAN TO MODIFY AN AGREEMENT WITH B & P PATTERSON, LLC FOR CONTRACTOR SERVICES FOR CENTERTOWN’S STORMWATER IMPROVEMENTS PROJECT

BE IT ORDAINED BY THE BOARD OF TRUSTEES OF THE VILLAGE OF CENTERTOWN, MISSOURI, AS FOLLOWS:

 Section 1. The Board of Trustees for the Village of Centertown, Missouri, hereby authorizes Adam Brown as the Chairman of the Board of Trustees for the Village of Centertown, Missouri to modify an agreement with B & P Patterson, LLC for contractor services for Centertown’s Stormwater Improvements Project, dated April 14, 2020 and ordained in Ordinance 199, dated the same.

 Section 2. Change Order No. 1 modifies the original contract completion date from ninety days to 150 days. Increase of 60 days.

 Section 3. Change Order No. 2 modifies the original contract price from $181,281.35 to $183,131.35. This is an increase of $1,850.00 for the removal and disposal of the abandoned underground fuel oil tank discovered near the corner of Main Street and Monroe Street. This work also includes the additional sidewalk removal and fill required to return the void back to grade.

 Section 4. This ordinance shall be in full force and effect from and after its

 passage by the Board of Trustees.

**FIRST READING HELD: AUGUST 25, 2020**

**SECOND READING HELD AND FINAL PASSAGE ON THIS 25TH DAY OF AUGUST, 2020 BY THE FOLLOWING VOTE:**

Aye Nay

Adam Brown \_X\_\_ \_\_\_\_\_

Paula Hinshaw \_X\_\_ \_\_\_\_\_

Heather Hunger \_X\_\_ \_\_\_\_\_

Sherry Kempf \_ABSENT\_\_ \_\_\_\_\_

Celine Whitaker \_ABSENT\_\_ \_\_\_\_\_

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

ORDINANCE 214, DATED AUGUST 25, 2020 Page 2