IN THE VILLAGE OF CENTERTOWN, MISSOURI

Bill No. 0020-022 Ordinance No. 215

AN ORDINANCE AUTHORIZING THE CHAIRMAN TO MODIFY AN AGREEMENT WITH B & P PATTERSON, LLC FOR CONTRACTOR SERVICES FOR CENTERTOWN’S STORMWATER IMPROVEMENTS PROJECT

BE IT ORDAINED BY THE BOARD OF TRUSTEES OF THE VILLAGE OF CENTERTOWN, MISSOURI, AS FOLLOWS:

Section 1. The Board of Trustees for the Village of Centertown, Missouri, hereby authorizes Adam Brown as the Chairman of the Board of Trustees for the Village of Centertown, Missouri to modify an agreement with B & P Patterson, LLC for contractor services for Centertown’s Stormwater Improvements Project, dated April 14, 2020 and ordained in Ordinance 199, dated the same.

Section 2. Change Order No. 3 modifies the original contract price from $183,135.35 to $192,855.35.

Section 3. Contract price change is to cover half of the base material mistakenly used by B&P Patterson at the intersection of Lookout Trail and Monroe Street. This compensation for base pavement is contingent that B&P Patterson will not pursue reimbursement for additional expenses caused by project delays.

Section 4. This ordinance shall be in full force and effect from and after its

passage by the Board of Trustees.

**FIRST READING HELD: November 5, 2020**

**SECOND READING HELD AND FINAL PASSAGE ON THIS 5th DAY OF November, 2020 BY THE FOLLOWING VOTE:**

Aye Nay

Adam Brown \_X\_\_ \_\_\_\_\_

Paula Hinshaw \_X\_\_ \_\_\_\_\_

Heather Hunger \_X\_\_ \_\_\_\_\_

Celine Whitaker \_X\_\_ \_\_\_\_\_

ORDINANCE 215, DATED NOVEMBER 5, 2020 PAGE 2