## Instructions
Instructions: | Enter exercise information in cells A2 through E2. Populating cell E2 with the projected exercise date will auto-populate suggested timeline dates in the "D" column.

## Discussion-based exercises
Exercise Name | Exercise Type | Exercise Lead |  | Exercise Date(s)
[Exercise Name] | [Exercise Type] | [Exercise lead] |  | [Exercise Date] |  | *Entering exercise date will auto-populate the suggested timeline
Exercise Planning Tasks | Responsible Party | Contact Information | Suggested Timeline | Target Date | Status (drop down menu) | Notes
I. Design and Development
Foundation |  |  | [Prior to design of exercise concepts and objective. 6-8 months before exercise]
Review exercise program guidance, including: Elected and appointed officials' intent and guidance Integrated Preparedness Plan (IPP) Existing plans and procedures Risk, threat, and hazard assessments Relevant After-Action Report/Improvement Plan (AARs/IPs) Grant or cooperative agreement requirements | [Exercise Program Manager] |  | #VALUE! |  |  | Purpose: IPP Priorities: References:
Develop draft exercise project timeline |  |  | #VALUE!
Exercise Planning Team and Events
Identify elected and appointed officials and representatives from the sponsor organization for potential Exercise Planning Team membership |  |  | #VALUE!
Identify participating organizations for potential Exercise Planning Team membership |  |  | #VALUE!
Officially stand up Exercise Planning Team with Exercise Planning Team Leader and section chiefs, as appropriate |  |  | #VALUE!
Develop exercise budget |  |  | #VALUE!
Schedule first planning meeting (C&O or IPM) |  |  | #VALUE!
Identify/review topics or issues to be covered during the first planning meeting (C&OM or IPM) |  |  | #VALUE!
Planning Meetings
Concepts and Objectives (C&O) Meeting (optional) |  |  | #VALUE!
Coordinate meeting logistics, prepare meeting presentation, prepare and send invitations and read-ahead packets |  |  | #VALUE!
Meeting Outcomes
Exercise concept and scope
Proposed objectives and core capabilities
Extent of participant play
Confirmed exercise planning team
Planning timeline, milestones, and meeting dates
Follow-up
Develop and distribute meeting minutes |  |  | #VALUE!
Initial Planning Meeting (IPM) |  |  | #VALUE!
Coordinate meeting logistics, prepare meeting presentation, prepare and send invitations and read-ahead packets |  |  | #VALUE!
Meeting Outcomes
Include outcomes from C&O Meeting if combined with IPM
Finalized scope, objectives, and core capabilities
Determine evaluation elements (capability targets and critical tasks)
Determine scenario elements threat, scope, vanue, conditions)
Identify needed and available subject matter experts for scenario vetting
List of participating organizations and extent of play
Refine exercise timeline as needed
Identify all source documents needed for exercise documentation
Identify exercise logistics needs and responsible party (date, location, including breakout locations or specific exercise play sites, if needed)
Assign responsibilities and due dates for tasks and determine date for next planning meeting
Follow-up
Develop and distribute meeting minutes |  |  | #VALUE!
Develop and distribute draft exercise documentation |  |  | [Prior to agreed upon time/meeting]
Midterm Planning Meeting (MPM) (as needed) |  |  | #VALUE!
Coordinate meeting logistics, prepare meeting presentation, prepare and send invitations and read-ahead packets |  |  | #VALUE!
Meeting Outcomes
Review and refine all exercise materials, documents, and tasks
Well developed scenario and MSEL injects if no MSEL meeting scheduled)
Finalize decisions on exercise site and logistics requirements
Assign responsibilities and due dates for tasks, and determine date for next planning meeting
Follow-up
Develop and distribute meeting minutes |  |  | #VALUE!
Develop and distribute draft exercise documentation |  |  | [Prior to agreed upon time/meeting]
Final Planning Meeting (FPM) |  |  | #VALUE!
Coordinate meeting logistics, prepare meeting presentation, prepare and send invitations and read-ahead packets |  |  | #VALUE!
Meeting Outcomes
Final approval of exercise documents and material for production
All identified issues resolved
Confirm all exercise logistical elements (including exercise site(s), equipment, and schedule)
Assign any remaining responsibilities and due dates for tasks
Follow-up
Develop and distribute meeting minutes |  |  | #VALUE!
Finalize all publications |  |  | #VALUE!
Prepare supporting materials |  |  | #VALUE!
Exercise Documentation
Develop Situation Manual (SitMan)
Develop Player Handout (as needed)
Develop Facilitator’s Guide
Develop multimedia exercise presentation
Develop exercise evaluation packets (including Exercise Evaluation Guides [EEGs])
Develop Participant Feedback Forms
Additional Documentation (as applicable)
Develop Photo Consent Form
Develop Weapons and Safety Policy
Exercise Site Areas
Designate media/observer area
Designate registration area
Designate parking area
Media/Public Information
Develop media policy
Develop Press Release and/or Public Announcements as needed
Logistics
Identify exercise venue
Arrange for use of exercise venue (reserve room/use of facility)
Arrange for participant parking at venue
Arrange for audio/visual equipment (e.g., microphones, screens, projectors)
Arrange for exercise supplies (e.g., pens, markers, flipcharts)
Arrange for food and refreshments
Develop mailing lists (players, facilitators, Exercise Planning Team)
Develop ID badges, name/table tents, breakout room identification and sign-in sheets
Arrange for restrooms
Develop signage
Exercise Staffing
Determine exercise staff requirements
Create exercise control structure
Select and train exercise staff
II. Conduct
Exercise Play Preparation
Distribute exercise documentation |  |  | #VALUE!
Set up exercise site(s) |  |  | #VALUE!
Present pre-exercise Elected and Appointed Official Briefing (as needed)
Conduct Evaluator Training |  |  | #VALUE!
Observer Briefing (as needed) |  |  | [Exercise Date]
Print exercise documentation
Exercise Conduct
Facilitate exercise play
Collect data
Wrap-Up Activities
Conduct post-exercise player Hotwash |  |  | Immediately following ENDEX
Conduct facilitator/evaluator debrief |  |  | Immediately following ENDEX
Collect Participant Feedback Forms |  |  | Immediately following ENDEX
III. Evaluation
Data Analysis
Complete and submit all EEGs |  |  | Immediately following exercise
Perform Root Cause Analysis
After-Action Report
Develop draft AAR
Distribute draft AAR to participating organizations’ policy and decision makers for review
After-Action Meeting (AAM) |  |  | #VALUE!
Schedule meeting
Coordinate meeting logistics, prepare and send invitations and read-ahead packets |  |  | #VALUE!
Receive feedback on Draft AAR, make any revisions, and develop draft list of corrective actions |  |  | #VALUE!
Meeting Outcomes
Reach consensus on AAR/IP
Reach consensus on draft corrective actions
Propose concrete deadlines for implementation of corrective actions
Reach consensus on assigned corrective actions to preparedness stakeholders
Follow-up
Finalize AAR/IP
Distribute final AAR/IP
IV. Improvement Planning
Continuous Improvement
Share lessons learned, best practices, and successes identified in AAR/IP
Identify how corrective actions will be integrated back into the Integrated Preparedness Cycle
Implement corrective actions
Track AAR/IP implementation
Identify corrective actions to be addressed at future IPPW |  |  | [Prior to IPPW]

## Operations-based exercises
Exercise Name | Exercise Type | Exercise Lead | Exercise Date(s)
[Insert Exercise Name] | [Exercise Type] | [Exercise Lead] | [Exercise Date] | *Entering exercise date will auto-populate the suggested timeline
Exercise Planning Tasks | Responsible Party | Contact Information | Suggested Timeline | Target Date | Status (drop down menu) | Notes
I. Design and Development
Foundation
Review exercise program guidance, including: Elected and appointed officials' intent and guidance Integrated Preparedness Plan (IPP) Existing plans and procedures Risk, threat, and hazard assessments Relevant After-Action Report/Improvement Plan (AARs/IPs) Grant or cooperative agreement requirements | [Exercise Program Manager] |  | #VALUE! |  |  | Purpose: IPP Priorities: References:
Develop draft exercise project timeline |  |  | #VALUE!
Exercise Planning Team and Events
Identify elected and appointed officials and representatives from the sponsor organization for potential Exercise Planning Team membership |  |  | #VALUE!
Identify participating organizations for potential Exercise Planning Team membership |  |  | #VALUE!
Officially stand up Exercise Planning Team with Exercise Planning Team Leader and section chiefs, as appropriate |  |  | #VALUE!
Develop exercise budget |  |  | #VALUE!
Schedule first planning meeting (C&O or IPM) |  |  | #VALUE!
Identify/review topics or issues to be covered during the first planning meeting (C&OM or IPM) |  |  | #VALUE!
Planning Meetings
Concepts and Objectives (C&O) Meeting (optional) |  |  | #VALUE!
Coordinate meeting logistics, prepare meeting presentation, prepare and send invitations and read-ahead packets |  |  | #VALUE!
Meeting Outcomes
Exercise concept and scope
Proposed objectives and core capabilities
Extent of participant play
Confirmed exercise planning team
Planning timeline, milestones, and meeting dates
Follow-up
Develop and distribute meeting minutes |  |  | #VALUE!
Initial Planning Meeting (IPM) |  |  | #VALUE!
Coordinate meeting logistics, prepare meeting presentation, prepare and send invitations and read-ahead packets |  |  | #VALUE!
Meeting Outcomes
Include outcomes from C&O Meeting if combined with IPM
Finalized scope, objectives, and core capabilities
Determine evaluation elements (capability targets and critical tasks)
Determine scenario elements threat, scope, vanue, conditions)
Identify needed and available subject matter experts for scenario vetting
List of participating organizations and extent of play
Refine exercise timeline as needed
Identify all source documents needed for exercise documentation
Identify exercise logistics needs and responsible party (date, location, including breakout locations or specific exercise play sites, if needed)
Assign responsibilities and due dates for tasks and determine date for next planning meeting
Follow-up
Develop and distribute meeting minutes |  |  | #VALUE!
Develop and distribute draft exercise documentation |  |  | [Prior to agreed upon time/meeting]
Midterm Planning Meeting (MPM) (as needed) |  |  | #VALUE!
Coordinate meeting logistics, prepare meeting presentation, prepare and send invitations and read-ahead packets |  |  | #VALUE!
Meeting Outcomes
Review and refine all exercise materials, documents, and tasks
Well developed scenario and MSEL injects if no MSEL meeting scheduled)
Finalize decisions on exercise site and logistics requirements
Assign responsibilities and due dates for tasks, and determine date for next planning meeting
Follow-up
Develop and distribute meeting minutes |  |  | #VALUE!
Develop and distribute draft exercise documentation |  |  | [Prior to agreed upon time/meeting]
Master Scenarios Event List (MSEL) Meeting (if necessary) |  |  | #VALUE!
Coordinate meeting logistics, prepare meeting presentation, prepare and send invitations and read-ahead packets |  |  | #VALUE!
Meeting Outcomes
Identify key event injects and delivery timeline
Revise draft scenario-based documentation
Review remaining timeline for completion
Assign responsibilities and due dates for tasks, and determine date for next planning meeting
Follow-up
Develop and distribute meeting minutes |  |  | #VALUE!
Develop and distribute draft exercise documentation |  |  | [Prior to agreed upon time/meeting]
Final Planning Meeting (FPM) |  |  | #VALUE!
Coordinate meeting logistics, prepare meeting presentation, prepare and send invitations and read-ahead packets |  |  | #VALUE!
Meeting Outcomes
Final approval of exercise documents and material for production
All identified issues resolved
Confirm all exercise logistical elements (including exercise site(s), equipment, and schedule)
Assign any remaining responsibilities and due dates for tasks
Follow-up
Develop and distribute meeting minutes |  |  | #VALUE!
Finalize all publications |  |  | #VALUE!
Prepare supporting materials |  |  | #VALUE!
Exercise Documentation
Develop Exercise Plan (ExPlan)
Develop Player Handout (as needed)
Develop Ground Truth
Develop Controller/Evaluator (C/E) Handbook
Develop Master Scenario Events List (MSEL)
Develop Control Staff Instructions (COSIN) (as needed)
Develop exercise evaluation packets (including Exercise Evaluation Guides [EEGs])
Develop Evaluation Plan (EvalPlan)
Develop Participant Feedback Forms
Additional Documentation (as applicable)
Develop Liability Waiver Form
Develop Photo Consent Form
Develop Weapons and Safety Policy
Develop Symptomology Cards
Exercise Site Areas
Designate exercise play area(s)
Designate response route(s)
Designate exercise assembly area
Designate control cell location(s)
Designate Simulation cell location
Designate Emergency Medical Services area
Designate media/observer area
Designate registration area
Designate parking area
Media/Public Information
Develop media policy
Develop Press Release and/or Public Announcements as needed
Logistics
Identify exercise venue
Arrange for use of exercise venue (reserve room/use of facility)
Arrange for participant parking at venue
Arrange for audio/visual equipment (e.g., microphones, screens, projectors)
Arrange for exercise supplies (e.g., pens, markers, flipcharts)
Arrange for food and refreshments
Develop mailing lists (players, facilitators, Exercise Planning Team)
Develop ID badges and sign-in sheets
Arrange for restrooms
Develop signage
Exercise Staffing
Determine exercise staff requirements
Create exercise control structure
Select and train exercise staff
II. Conduct
Exercise Play Preparation
Distribute exercise documentation |  |  | #VALUE!
Set up exercise site(s) (including Simulation and/or Control Cells, as needed) |  |  | #VALUE!
Check for potential safety issues |  |  | #VALUE!
Present pre-exercise Elected and Appointed Official Briefing (as needed)
Conduct Controller/Evaluator Training |  |  | #VALUE!
C/E Briefing (if separate from C/E Training) |  |  | [Exercise Date]
Actor Briefing (as needed) |  |  | [Exercise Date]
Player Briefing |  |  | [Exercise Date]
Observer Briefing (as needed) |  |  | [Exercise Date]
Exercise Conduct
Conduct Safety Briefing |  |  | [Each day of exercise]
Control exercise play
Collect data
Wrap-Up Activities
Conduct post-exercise player Hotwash |  |  | Immediately following ENDEX
Conduct C/E Debrief |  |  | Immediately following ENDEX
Collect Participant Feedback Forms |  |  | Immediately following ENDEX
III. Evaluation
Data Analysis
Complete and submit all EEGs |  |  | Immediately following exercise
Perform Root Cause Analysis
After-Action Report
Develop draft AAR
Distribute draft AAR to participating organizations’ policy and decision makers for review
After-Action Meeting (AAM) |  |  | #VALUE!
Schedule meeting |  |  | Immediately following exercise
Coordinate meeting logistics, prepare and send invitations and read-ahead packets |  |  | #VALUE!
Receive feedback on Draft AAR, make any revisions, and develop draft list of corrective actions |  |  | #VALUE!
Meeting Outcomes
Reach consensus on AAR/IP
Reach consensus on draft corrective actions
Propose concrete deadlines for implementation of corrective actions
Reach consensus on assigned corrective actions to preparedness stakeholders
Follow-up
Finalize AAR/IP
Distribute final AAR/IP
IV. Improvement Planning
Continuous Improvement
Share lessons learned, best practices, and successes identified in AAR/IP
Identify how corrective actions will be integrated back into the Integrated Preparedness Cycle
Implement corrective actions
Track AAR/IP implementation
Identify corrective actions to be addressed at future IPPW |  |  | [Prior to IPPW]