## RFI Tracker
RFI No. | RFI Title | Submitted By | Date Submitted | Assigned To | Priority | Status | Response Due Date | Response Date | Notes/Comments
RFI-001 | Below Slab Pipe Hangers | Mifflin Plumbing/Michael Scott PM | 2022-03-03 | Mechanical Consultant & Architect | High | Pending | 2024-03-05 |  | response pending, followed up on March 4.
RFI-002 | [RFI Title] | [Company/Person] | [MONTH DAY, YEAR] | [Architect/Eng] | Medium | Pending | [MONTH DAY, YEAR] | [MONTH DAY, YEAR]
RFI-003 | [RFI Title] | [Company/Person] | [MONTH DAY, YEAR] | [Engineer] | Low | Closed | [MONTH DAY, YEAR] | [MONTH DAY, YEAR]

## How to use
RFI No. | Using a consistent numbering format can be helpful down the line, a common industry practice is to use 001/002/003/etc.
RFI Title | Try to use a 2 to 4 word title that is easy to mention in email subject lines and easy to recall in conversations.
Dates | The dates have been formatted to apear as MONTH DAY, YEAR. This can become a quick use function, if you write 3/12 for Mar 12, the date will automatically populate in the standard format. This can be changed based preference.
Priority | These cells have been set to condittional formatting to change color based on the text that is inserted into the cell. High means the color will change to red, Medium means the color will change to yellow, Low means the color will change to green.
Status | These cells have been set to condittional formatting to change color based on the text that is inserted into the cell. Open means yellow, Closed means grey.
Additional Info | This is a most basic form of RFI tracking that can offer immense value if updated and reviewed regularly. Based on your requirments, you are recommended to add/remove columns, conditional formatting and filters as needed.