## Sheet1
TRC Field Maintenance Projects (2016-2018) |  |  |  |  | Mark Schneier Updated: 5/10/2018
Item | Task | Description | POCs | Status | Notes
1 | Update TRC Website | Need to aquire Windows based software vice current MAC software. TRC Website will be updated using new SW. | Mark Schneier | Open | Website is a work in progress as TRC shifts over to a new software system. New Windows based software worked however our web hosting company transferred us to another provider. We have since switched to Go Daddy and the new website is progressing.
2 | Limbs in Road | remove the large limbs from the side of the road. | Council | Open | Limbs that were too large to chip from the spring 2018 working party were left on the side of the road and need to be removed.
3 | Picnic Table | Seat of table broken | Council | Open | One picnic table has a broken seat. Need to repair.
4 | Pilot Boxes | Box railing needs painted and repaired. | Council | Open | The pilot box railings need painted and some of the latuce has fallen out.
5 | White steps slippery | add another coat of paint and sand mixed in for a non-Skid surface | Council | Open | May/June 2017 Completed?
6 | Gazebo | Add extention to gazebo | Hank | Open | Build an extention to the existing gazebo. Meetings to be held at the field from now on.
7 | Trim Trees | Trim trees along side of road. Preferably before IMAC event | Council | Closed | 2016: to hot and too much rain. Will plan to do before IMAC 2017 event. IMAC canx. Trimming was completed in March 2018. Only the last section of road closest to the field.
8 | Rock the road | Rock remaining dirt portion of the road | Larry Woolard | Closed | Used RAP to finish road and have left over for fill when needed.
9 | Repair Model stands | Repair 2 model assembly stands | Mark Ward | Closed | New wood, wheels and stain
10 | Repair Pilot Boxes | Need to reset the Pilot Box posts or add wedges to keep stright | Council | Closed | Fall Work Party in Oct completed this action. Thanks Mark and Russ for leading effort.
11 | New Pilot Box foot stands | Replace old foot pad area with new. | Mark Schneier | Closed | Fall Work Party in Oct completed this action. Thanks Mark and Russ for leading effort.
12 | Mowers/Trimmers | Ensure Mowers/Trimmers ready to Run | Council | Closed | good for IMAC in June and Scale event in Aug. Pete Lewis Repaired mower Deck wheel on black mower. Mowers all working great. Complete clean of grass and oil and grease. 9 /18/2016. Alex Guass sharpened all the mower blades and Pete Lewis did maintenance at Fall Field Work Party in Oct
13 | Gazebo Door | Replace Gazebo door | Council | Closed | Hank Jones, Mike Purcell completed door install and a new step. 9/24/2016.
14 | Gate Lock Combo | Change Gate Lock Combination for new TRC flying year | Larry Woolard | Closed | Larry Changed Combo. Emails sent to all paid members by Mark Schneier
15 | Windsock repair | New Windsock provided | Mark Schneier | Closed | New windsock in the shed. Field using Red flag for day-day use. Please pull it down when you leave. (TRC Paid Mark for purchase)
16 | USA Flag repair | New American Flag provided | Mark Schneier | Closed | New US Flag in the Shed in plastic container. (Donated)
17 | Mold on all Benches | Remove all mold from picnic and spectator benches prior to painting | Council | Closed | Fall Work Party completed this action. One bench back rest still needs new paint
18 | Stain all Benches | New coat of red stain on all picnic benches, spectator benches, Gazebo and model stands | Council | Closed | Fall Work Party completed this action. Many TRC members to thank for painting Gazebo!!
19 | Solar Power station | Finish Solar power statio at gazebo for electric chargers and power. | Larry Woolard | Closed | Aquired a solar panel (free), mounting pole/brackets. Mounted pole before IMAC. Need batteries and other electrical connectors and chord. Need some pole adaptors- 4" pipe threads. This project was completed Summer of 2017.
20 | Rain Gutter | Gazebo Rain Gutter needs repaired. |  | Closed | Removed gutter at Fall Work Party 2017.
21 | Shed Mouse problem | buy mouse traps or poison | Mark Schneier | Closed | Purchase product and placed in shed in Sep 2016. Continue to monitor. We continue to put out poison in the gazebo and shed. Poisen is about half eaten so far as of May 2018. Continue to monitor.
22 | Shed entrance Flashing | Shed entrance flashing torn up. Repair or replace. | Mike Purcell | Closed | Completed April '17. New flashing purchased with a rounddown wood strip underneith. (donated)
23 | Generator Carb repair | Would not run as carb was leaking gas at Aug Scale event | Pete Lewis | Closed | Pete repaired in Sep. Gen used various times since then with no issues. (Last run 4/15/17)
24 | TRC Trainer planes | repair TRC trainer planes for events | Frank Rega Jr | Closed | Frank Jr. is building a new TRC trainer. Also heard about making a wooden box to store all components away from mice. Test flew trainer with OS.40 engine. Flies great. Mark Schneier made wing bag to protect it and added TRC decals. This aircraft was destroyed Summer 2018.
25 | Gazebo Door and wood steps | New Vinal Door needed. Repair wood steps and deck area around the gazebo door. | Council | Closed | Hank Jones, Mike Purcell completed door install and a new step. 9/24/2016. I would still like to repair wood deck area around door.
26 | Overgrown Grass | Remove High grass all along the edge from main Road | Larry Woolard | Closed | Working to get a tractor, Hedgehog and time to meet others to do the work. Russ Shaffer and Bob Prout both mentioned they would coordinate with Larry. Russ and Larry did a remarkable job for the club. RUSS was on the tractor for several hours. The road and field look simply AWESOME. 9/18/2016
27 | Round Up Grass on road | After Hedge Hog cuts the grass low enough, Roundup all along the main road to kill the grass | Larry Woolard | Closed | Larry Purchased Roundup and truck/ tank sprayed the newly cut down grass.
28 | No Smoking Signs | we need a couple "No Smoking" signs for the shed area due to gas stored. | Mark Schneier | Closed | Email from President to all membership reminding about gas in the shed and no smoking. Mark, Can you make up a couple signs over next weekend. Email from President
29 | Field Fryer | Donated from Bob Proutt | Council | Closed | Bob Proutt donated a hand made fryer for use at various TRC events. Stored in shed.
30 | Shelve in Shed | Build a 2nd shelve in the storage shed | Fred Nacella | Closed | Fred was able to frame up and Mike P. added the painted plywood shelve. Completely cleaned out the shed for winter preps. 3 mouse traps still in shed.
31 | Paint Gazebo | Need to paint exposed wood used to add the gazebo door. | Mike Purcell | Closed | Fall Work Party completed this action. Many TRC members to thank for painting Gazebo!!
32 | John Deere Mower | Donated mower in exchange for TRC memebership- Tom Parsons | Mike Purcell | Closed | Pete Lewis did maintenance at Fall Field Work Party in Oct
33 | Power wash shed | Power wash shed, and other filed structures to remove mold. | Larry Woolard | Closed | Fall Work Party completed this action. Many TRC members to thank for painting Gazebo!!
34 | New steps by Gazebo | remove old step and replaced | Mike Purcell | Closed | Wood and white paint donated.
35 | Upgrade Pilot Boxes | Pavers need to be set in sand. Frame with Pressure treated wood. | Fred Nacella | Closed | all 4 pilot boxes completed.
36 | Field Roller | Discussed a field roller made out of an old water heater from another club | Mark Schneier | Closed | (2/23/17) After several months of searching, we were able to obtain an old water heater. In Feb Mark Schneier started to strip off covering and pipes, welded all holes except one shut. Put 300 lbs of sand, Installed an axel and Frame and hitch for mowers to pull. Nicely painted white. Initially tested and works great. Stored behind Shed. (TRC paid for Sand $80.) * Please do not use on your own!!!
37 | TRC Main Entrance Sign | Added new rock and brick pavers to make sharp looking. | Mark Schneier | Closed | Added new rock and brick pavers to make sharp looking.
38 | TRC Main Entrance Sign | We need to put some wood sealer on the sign at our main entrance. | Mark Schneier | Closed | Frank Rega Jr had clear paint. Mark completed
39 | Gravel Road signs | Other damaged signs will be replaced | Mark Schneier | Closed | Just 1 remains damaged. Ordered aluminum sign blanks and made new road signs and badges required signs for the field. Continue to monitor signs and maintain as required.
40 | Painting Tables | Field tables and one picnic table still need painting. Poss one bench too. | Council | Closed | Will complete in May/June. Tables were painted.
41 | Frequency board | Frequency board/frame is stored in the shed; should we need it for events. | Council | Closed | Frequency Board stored in the shed if we evenr need it again
42 | Main Gate | There should only be a TRC lock upon the gate. (Both gates actually) | Council | Closed | Mr Cartwright is no longer farming/ nor has access to the TRC road. His lock is removed
43 | Mow field | grass cut low and included the additional 20 feet at the road end. | TRC | Closed | TRC Spring Work Party: April'17
44 | Repair Runway | Rolled and seeded the runway | TRC | Closed | TRC Spring Work Party: April'17
45 | Kill weeds on the road | Sprayed roundup on ½ of the road | TRC | Closed | TRC Spring Work Party: April'17
46 | Kill weeds on the field | Sprayed roundup on the fence line | TRC | Closed | TRC Spring Work Party: April'17
47 | Shed entrance Flashing | Shed entrance flashing torn up. | TRC | Closed | TRC Spring Work Party: April'17
48 | Gazebo Step safety | Installed a nonslip pad on the steps to the field building | TRC | Closed | TRC Spring Work Party: April'17
49 | Lunch for work party | Cooked and ate a lot of hot dogs | TRC | Closed | TRC Spring Work Party: April'17
50 | Solar Power station | Installed the solar panels | TRC | Closed | TRC Spring Work Party: April'17. See #13 for final electrical hook up
51 | Gazebo night light | Installed the street light on North side | TRC | Closed | TRC Spring Work Party: April'17. See #13 for final electrical hook up
52 | Pilot Boxes | Rubber matt's | TRC | Closed | Donated. Able to move around if stones are slippery.
53 | Model Assembly Table | one table has loose top rail. Need long screws to reattach | Council | Closed | May/June 2017.