## tiny home eco village
Tiny Home Eco Village
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
To-Do
Name | Subtasks | Owner | Status | Due date | Timeline - Start | Timeline - End | Notes
Organize Study Group |  | Mode Ben Avraham | Working on it | 2026-03-29 | 2026-01-05 | 2026-03-29
Subitems | Name | Owner | Status | Due Date | Details
| Verdantronix | Mode Ben Avraham | Working on it | 2026-02-27 | Assemble Team
| Non Profit Organization 1 |  |  | 2026-03-27 | Biomass Waste in Multnomah County
| Non Profit Organization 2 |  |  | 2026-03-27 | Biogas Equipment
| Multnomah County Commissioner |  |  | 2026-03-27 | Locations for Eco Village
| City of Portland Commissioner |  |  | 2026-03-27 | PGE
| City of Gresham Commissioner |  |  | 2026-03-29 | Tiny Home Villages
| Congressional Office/House |  |  | 2026-03-27 | Able Body Houseless Population
| Congressional Office/Senate |  |  | 2026-03-27 | Biomass Energy
Write White Paper |  |  | Not Started | 2026-06-30 | 2026-04-01 | 2026-06-30
Subitems | Name | Owner | Status | Due Date | Details
| Zoom Meeting of Study Group | Mode Ben Avraham |  | 2026-04-01 | Study Group Meeting on Research
| White Papers on Research |  |  | 2026-05-15 | Research Papers Submitted
| Editing & Revisions of Papers | Mode Ben Avraham |  | 2026-06-13 | Editing & Revisions of Seven Papers
| Zoom Meeting on White Paper | Mode Ben Avraham |  | 2026-06-26 | Review of Draft White Paper
| Final Draft White Paper | Mode Ben Avraham |  | 2026-06-30 | Final Draft White Paper from Research
Solicit Legislature |  |  | Not Started | 2026-09-30 | 2026-07-04 | 2026-09-30
Subitems | Name | Owner | Status | Due Date | Details
| Distribution of White Paper | Mode Ben Avraham |  | 2026-07-31 | Email and Call Legislative Offices
| Meetings With Legislature |  |  | 2026-09-30 | Lobby for a Bill to be Voted on
|  |  |  | 2026-03-29 to 2026-09-30 | 2026-01-05 | 2026-09-30