## 2021
Rural Improvement Zone
Project Number | Description | RIZ Approved | Quoted Bid for Project/Date | Awarded to/Date | Approved to Pay | Status | Fully Paid
16-10 | Ditch clean out - Franklin Dr #1. Unit 2 - 1 to 7 (BUS STOP & TURN AROUND) | 2016-07-06 |  | Time and Material - Kriegel | 2016-07-06 | Completed August 2018 | Chk 1275 - $2485 | 1500
16-12 | Ditch clean out - Wilson Ave. Unit 1 - 368 to 372. Cut edges off above culverts on top half. | 2016-05-04 | $2500.00- 10/2/19 | Kriegel Excavating | 2016-06-01 | Completed |  | 1400
16-13 | Ditch clean out - Lakeshore Dr. Unit 1 - 182 & 183. Ditch below Becky Payne property is filled in. | 2016-05-04 |  | Kriegel Excavating | 2016-07-06 | Completed |  | 1000
16-15 | Ditch clean out - Caron Dr to Lakeshore. Unit 1 - 133 & 134. Establish ditch, cut edges and grass on North side. | 2016-05-04 |  | Kriegel Excavating | 2016-06-01 | Completed | $2,185.00 - #1285 | 2000
16-18 | Ditch clean out - Franklin Dr - Unit 2 from lot 213 down to S Lakeshore, around corner to lot 96. 447' & 65' (Down hill in front of Wayne Johannes Residence) | 2016-07-06 |  | Time and Material - Kriegel | 2016-07-06 | Completed | $4,482 - #1287 | 12000
16-20 | Ditch clean out - Park Ct Unit 1 lot 234. Establish ditch on south side, cut grass edges of ditch on north side. Need culverts added on south side for 2 campers. | [5 empty] | Need to re-evaluate
16-21 | Ditch clean out - Caron Dr Unit 1 from lot 421 to orange stand pipe on east side 440' | 2016-07-06 |  | Time and Material - Kriegel | 2016-07-06 | Completed | $2,289.00 - #1286 | 1000
16-25 | Install culverts and intakes in the area of Unit 1 lot 111 between Schwab's and Robinson's property. | 2017-05-03 |  | Kriegel Excavating | 2017-05-03 | Completed Paid Ck#1251 | 7835 | 7605
17-04 | Madonna Park Project - Proposal #2 - Silt basin below Moen's West Pond - Clearing, tile pipe through dam, shaping and seeding | 2017-07-05 |  | FAAS Construction & Excavating - $51,500 | 2017-10-04 | Proceed before 17-06 | Completed - $51,500 Ck# 1242 ck#1277 - $8208 CK#1282 $15,687.04 Ck# 1277 $8,208.00
17-05 | Madonna Park Project - Proposal # 3 - Existing basin #1 - clean out basin to dimensions on plan, clear any trees to pile dirt for later use, seeding. |  |  | FAAS Construction & Excavating - $13,500 |  | Completed | 14850
17-07 | Madonna Park Project - Proposal #5 - New pond East of Terry O - Off Wesley Dr Lots 4001-4005 |  |  | FAAS Construction & Excavating - $38,500 |  | Completed
17-08 | Madonna Park Project - Proposal #6 - Raise road west of Andy's Lake 8'. Includes improved drainage, culverts, clearing of trees, rock, seeding, etc. |  |  | FAAS Construction & Excavating - $116,800 |  | Completed | 128480
17-09 | Martin Dr - ditch clean out | 2017-04-05 |  | Time and Material - Kriegel |  | Completed |  | 6000
17-12 | Capital Dr ditch clean out - rock of slopes | 2017-09-06 |  | Kriegel | 2017-09-06 | Completed | Ck# 1273 $200/Ck#1270 $3305.64
2018
18-01 | Skyline/Buena Vista - Unit 5 lot 170 - Ditch clean out | 2018-04-04 |  | Time & material Kriegel Excavating | 2018-04-04 | Completed | Paid Ck 1265 - $1650
18-02 | Skyline Dr - Unit 5 lot 263 - Ditch clean out and erosion repair | 2018-04-04 |  | Time & material Kriegel Excavating | 2018-04-04 | Completed | Paid Ck 1266 - $950
18-03 | North boat ramp/public access ditch & in front of Unit 5 lot 219 - clean ditches for improved water flow to stop erosion. Seed when completed. | 2018-06-06 |  | Time & material Kriegel Excavating | 2018-06-06 | Completed | Paid Ck 1267 - $983
18-04 | Ditch or catch basin needed on Skyline Drive from Drake to Buena Vista on North side of roadway. Culverts may be needed at driveways and/or to cross road to divert water flow. | 2018-06-06 |  | Time & material Kriegel Excavating | 2018-06-06 | Completed | Paid Ck 1268 - $1660.50
18-05 | Corner of Lakeshore & Woody Dr - install intake & ditch clean out. In stall drop box. Owner pays for culvert. | 2018-07-11 |  | Rick Kriegel Excavating | 2018-07-11 | Completed |  | 4500
18-06 | Buena Vista & Lakeshore North Side - Culvert and ditch clean out. Owner pays for culvert. | 2018-07-11 |  | Rick Kriegel Excavating | 2018-07-11 | Completed |  | 3000
18-07 | Watering of seeding for 2018 season projects as needed. | 2018-07-11 |  | Time & material Kriegel Excavating | 2018-07-11 | Completed | Ck#1272 - $2500 Ck# 1279 - $400 CK#1278 $2,200
18-08 | Capital & Lakeshore Dr top side - clean out curbs. Same is needed at Barbara & Lakeshore. Ditch clean out also needed in both areas. | 2018-07-11 |  | Time & material Kriegel Excavating | 2018-07-11 | Completed | Ck#1271 - $2328
18-09 | Review all Holiday Lake road projects as they are completed and determine if ditch clean out is needed as well. | 2018-07-11 |  | Time & material Kriegel Excavating | 2018-07-11 | Closed
18-10 | Skyline Dr - Unit 5 lot 263 - Replace 8" culvert with larger culvert to handle water flow. Phase 2 | 2018-06-06 |  | Time & material Kriegel Excavating | 2018-07-11 | Completed - tracking additional cost to 18-02
18-11 | North Lakeshore evaluate intake - Unit 6 lots 145 - 147 | 2018-09-05 |  |  |  | Completed
18-12 | Remove silt from retention pond at Larry's Drive and cut off tile. Clean out culverts and silt near stand pipe. | 2018-09-05 |  | Faas to do while in area | 2018-09-05 | Completed
18-13 | 6129 N Lakeshore Dr - Water coming into home - Evaluate solution by cleaning ditches/adding culverts/intake - also evaluate intake near 3171/172 | 2018-09-05 |  | Rick Kriegel Excavating | 2019-06-05 | Completed
18-15 | 1190/1191 - East Ridge - evaluate ditches and water diversion | 2018-09-05 |  | Rick Kriegel Excavating |  | Project(s) to be determined
18-16 | Seeding of ditch between Hard's driveways | 2018-10-03 |  | Time & material Kriegel Excavating | 2018-10-03 | Completed | $325.00 - #1284
18-17 | Replace Culvert under road at N Lakeshore 6143 and place 18" culvert at Povlick Driveway to divert water to stand pipe. | 2018-10-03 |  | Time & material Kriegel Excavating | 2018-10-03 | Completed
2019
19-01 | North Boat Ramp Dredging | 2019-04-03 |  | FAAS Construction |  | Completed
19-02 | Fluer Drive Dredging | 2019-04-03 |  | FAAS Construction |  | Completed
19-03 | Beach Boat ramp- Dredging | 2019-04-03 |  | FAAS Construction |  | Completed
19-04 | 5215 North Lakeshore- Ditch Clean out | 2019-05-01 |  | Kriegel Excavating |  | Completed
19-05 | 2159-60 E Lakeshore- Ditch Clean out and Culvert Break | 2019-05-01 | $5000/nov. 19 | Kriegel Excavating
19-06 | 4094-4108 Suzan Ct- Ditch clean out and Culvert Repairs | 2019-05-01 |  | Kriegel Excavating |  | Completed |  | 3000
19-07 | Capital- Intakes an culverts | 2019-06-05 |  | Kriegel Excavating |  | Completed | seeding needs done
19-08 | Plaza- Intakes an culverts | 2019-06-05 |  | Kriegel Excavating |  | Completed
19-09 | Barbara 2 culverts at camp ground, clean out ditches | 2019-06-05 |  | Kriegel Excavating |  | Completed |  | 4000
19-10 | Banzoff- Culvert and rock ditch | 2019-06-05 |  | Kriegel Excavating | 2019-06-05 | Completed |  | 2200
19-11 | 1190 East Ridge- Ditch clean out and erosion control | 2019-07-03
19-12 | Duck Park- Ditch Clean Out- (Larry's dr) | 2019-07-03 |  | Kriegel Excavating |  | Complete
19-13 | 5191 Delta Drive- Ditch Clean out- culvert work | 2019-07-03
19-14 | 6237 Woody Dr- Ditch clean out- Culvert is Plugged | 2019-07-03 | $2500.00- 10/2/19 | Kriegel Excavation |  | Complete
19-15 | Barbara dr. Tree clean out | 2019-07-03 |  | FAAS Construction | Sept. 2019 | Completed
19-16 | Earl Thomas- Ditch Clean out | 2019-07-03 |  | Kriegel Excavating | Sept. 2019 | completed
19-17 | Corner of S.Lakeshore cut off Riser | 2019-07-03 |  | FAAS Construction |  | completed
19-18 | Povilic culvert extension and Rock | 2019-09-04 |  | Kriegel Excavating | 2019-09-04 | Complete
19-19 | Herbert Drive- Ditch Cleanout (Bob Smith) east drive way south 585 ft down to crossroad culvert at south Lakeshore and move culvert, rock driveway. Clean out around standpipe south of Dee and South Lakeshore. | 2019-10-02 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Complete
19-20 | 4209 Tracy and West Lakeshore- Ditch cleanout from west Lakeshore to new driveway on Tracy. 30ft | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Complete
19-21 | Lawnmower Joes and Shannon Hersey- Cut break in culvert North of Joes driveway and reshape Joes Driveway, | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16
19-22 | NE Lakeshore and Korn's- Ditch Cleanout both ends of culvert on Korns 50ft.(both ways). Rack up Korns on north side as needed. | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Completed
19-23 | Kerry Barry- Ditch Cleanout east side of driveway's 50ft. | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 |  | This project has been tabled for a later date.
19-24 | Andy Boat Ramp- Big Rock needed to stop erosion | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Completed
19-25 | Norm DeGeeter's Lot 1189- Ditch Clean out | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-26 | Larry's Dr. North side raise and clean silt pond | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-27 | Lot 4044 South Lakeshore and Dee to the east | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-28 | Woodland Hill Dr, North of Phills Dr, west side. Ditch Clean out | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-29 | North Lakeshore Dr. between sunrise and Drake. Lower shoulder 200ft on north side and 100ft on south side | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-30 | South Lakeshore Dr and new raise road, Clean out hillside 200Ft. | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed | 1500
19-31 | South Boat Ramp- Sink hole and shore line siding into lake. ( Emergency project) | 2019-11-25 | 2019-11-25 | Rick Kriegel Excavating | 2019-11-25 | Completed | $7426.24- 11/27/19
2021
21-01 | Burn tree pile on Dennis Moons Lot 2306. Place in a hole and bury the trees | 2021-03-03 | $4500.00/ 3/3/21 | FAAS Construction
21-02 | remove 8,000 cubic yards of sediment from Poe’s & Bob’s Coves | 2021-04-07 | $106,461.00 4/7/2021 | Mid-American Dredging | 2021-11-03 | Completed
21-03 | prepare Bob’s sediment retention basin to receive 4,000 cubic yards of sediment | 2021-04-07 | 37725 | FAAS Construction | 2021-07-07 | Completed
21-04 | Holiday Lake Tire reef removal | 2021-05-05 | $10, 276.00 | Blake | 2021-07-07 | Completed
21-05 | Brian Cline Erosion- Culvert | 2021-05-05 | 24000 | FAAS Construction | 2021-09-01 | Completed | 25170
21-06 | Sean Mcintyre- Dig out ditch- Drain Erosion | 2021-05-05 | 11970 | FAAS Construction | 2021-07-07 | Completed
21-07 | owner of 3066 Joan Dr would like to relocate culvert due to wanting to build new garage. Get it back on property line. | 2021-06-02 | 3300 | FAAS Construction | 2021-06-02 | Completed
21-08 | Prepare Hap’s Cove sediment basin | 2021-07-07 | 58000 | FAAS Construction | 2021-07-07 | Completed | 58000
21-09 | Put a swell in the Road across from Unit 1 lot 54 to help with water way. 3 drive ways. | 2021-08-04 |  | Rick Kriegel Excavating |  | No longer needed
21-10 | Main outlet for water overflow for the dam- Concrete repair | 2021-10-06
Project Number | Description | RIZ Approved | Quoted Bid for Project/Date | Awarded to/Date | Approved to Pay | Status | Fully Paid
2022
22-01 | Aquatic Ecosystem Consultants ($19,175) Help in protecting lake Vegetation and two ponds ( Bozo and Andy) | 2022-02-02 |  | Aquatic Systems | 2022-02-02
22-02 | Beach E.coli testing and Micro sampling for water quality (Simular to DNR) | 2022-02-02
22-03
22-04
22-05
22-06
22-07
22-08
22-09