## 2015-2016
Rural Improvement Zone |  | END OF SEASON PROJECT STATUS
Project Number | Description | RIZ Approved | Awarded to | Approved to Pay | Status | Fully Paid
2015
15-01 | Cleanng of ditch on Barbara across from Wieland's/includes installation of culvert | 2015-10-07 | Kriegel Excavating | 2015-10-07 | COMPLETE | 6/3 1184
15-02 | Corner of Lakeshore and Sunrise - clean out ditches up hill on Sunrise and south on Lakeshore | 2015-10-07 | Kriegel Excavating | 2015-10-07 | COMPLETE | paid Aug
15-03 | Install 40' culvert and rock at 4310 Shady Lane Dr | 2015-11-24 | Kriegel Excavating | 2015-11-24 | COMPLETE | 2015-11-24
15-04 | Catch basin on east side of Waukonda - Unit 6 Lot 6 (Kriegel's Driveway) | 2016-07-06 | Kriegel Excavating | 2016-07-06 | Time & Material
15-05 | Holiday Road Closing |  | ??FAAS?? |  | COMPLETE | 6/15 1188
15-06 | Dam construction for erosion control on lots 6187, 6188, 6202. Minimal trees to be removed | 2016-07-06 | Faas Construction | 2016-07-06 | COMPLETE | #1204
15-07 | Larry's Drive - clean out silt pond | 2015-09-05 | Faas Construction | 2015-09-02 | COMPLETE | 2016-04-12
15-08 | NE Lakeshore from Shady Dr East (in front of abandoned property) | 2015-10-07 | Kriegel Excavating | 2015-10-07 | COMPLETE | Paid/Complete
15-09 | Demolition of Dillavou property | 2015-11-04 | Kriegel Excavating | 2015-11-04 | COMPLETE | 2015-11-24
2016
16-01 | Unit 2 Lot 291 (former Dillavou) Clean out and expand silt pond. Work outlined per bid sheets received 5-4-16. | 2016-04-06 | Faas Construction | 2016-05-04 | COMPLETE | #1200 Paid
16-02 | Andy's Boat Ramp erosion control issues - joint project to seal coat. | 2016-04-06 | Kriegel Excavating | 2016-05-04 | COMPLETE | 6/10 1186
16-03 | Herbert Dr & S Lakeshore - Ditch clean out & re-seed | 2016-04-06 | Kriegel Excavating | 2016-04-06 | COMPLETE | #1195
16-04 | Sunrise & Lakeshore - East side ditch clean out, line with rock and re-seed To bec completed in conjunction with 15-02 and 16-05 | 2016-04-06 | Kriegel Excavating | 2016-04-06 | COMPLETE | 6/3 1183 with 16-05
16-05 | North boat ramp erosion control issues - 60' culvert needed - joint project to seal coat. | 2016-04-06 | Kriegel Excavating | 2016-05-04 | COMPLETE | 6/3 1183
16-06 | Ditch clean out - Caron & Barbara Unit 3 - 139, 140 & 141. Clean out, reshape & seed. | 2016-05-04 | Kriegel Excavating | 2016-06-01 | COMPLETE | 6/10 1187
16-07 | Load of Rock for driveway damage at Banzhaf Dam . | 2016-05-04 | Faas Construction | 2016-05-04 | COMPLETE | 6/15 1189
16-08 | Ditch clean out - NE Lakeshore from Woody Dr in Unit 6 - 107 to 121. (By Herb Richards & Reeves) |  |  |  | COMPLETE
16-09 | Ditch clean out Echo Dr. Unit 5 - 53 to 60. West side needs a ditch for proper drainage. |  |  |  | Can do nothing here
16-10 | Ditch clean out - Franklin Dr #1. Unit 2 - 1 to 7, 85/86 & 209, 210, 213 & 214. | 2016-07-06 | Time and Material - Kriegel | 2016-07-06
16-11 | Ditch clean out - E Lakeshore & Caron Dr - Unit 3 lots 85 - 88 west to intake 100' between lots 88/89 (Alligator campsite) | 2016-07-06 | Time and Material - Kriegel | 2016-07-06 | COMPLETE | 1206 Nov
16-12 | Ditch clean out - Wilson Ave. Unit 1 - 368 to 372. | 2016-05-04 | Kriegel Excavating | 2016-06-01
16-13 | Ditch clean out - Lakeshore Dr. Unit 1 - 182 & 183. Ditch below Becky Payne property is filled in. | 2016-05-04 | Kriegel Excavating | 2016-07-06
16-14 | Ditch clean out - Tracy Dr (in front of new construction) both sides of road to S Lakeshore. 375' and 412' | HOLD |  |  | Put on hold until construction equipment is no longer needed
16-15 | Ditch clean out - Caron Dr to Lakeshore. Unit 1 - 133 & 134. | 2016-05-04 | Kriegel Excavating | 2016-06-01
16-16 | Silt basin on So. Lakeshore - clean out. Unit 2 - 370 & 371. | HOLD |  |  | In development and review
16-17 | Ditch clean out across from 2057 | 2016-06-01 | Kriegel Excavating | 2016-06-01 | COMPLETE | #1193
16-18 | Ditch clean out - Franklin Dr - Unit 2 from lot 213 down to S Lakeshore, around corner to lot 96. 447' & 65' | 2016-07-06 | Time and Material - Kriegel | 2016-07-06
16-19 | Ditch clean out - Franklin Dr Unit 2 lots 31/32 - widen ditch and line with rock west and down the hill. At Beatty's driveway, cut curb off to intake, then intake at top of driveway at Unit 2 lots 31 & 33 and cut curb. From lot 30, down hill 575' to intake on Larry's Dr. widen ditch ad rock dam every 30' to 40' and seed in between | 2016-07-06 |  | 2016-07-06 | Table for next season
16-20 | Ditch clean out - Park Ct Unit 1 lot 234. Clean both side of road - curb work and possible culvert |  |  |  | Need to develop project
16-21 | Ditch clean out - Caron Dr Unit 1 from lot 421 to orange stand pipe on east side 440' | 2016-07-06 | Time and Material - Kriegel | 2016-07-06 | COMPLETE
16-22 | Ditch clean out - Caron Dr & E Lakeshore clean out from rock waterway on Caron 100' to orange stand pipe on E Lakeshore | 2016-07-06 | Time and Material - Kriegel | 2016-07-06 | COMPLETE | 1207 Nov
16-23 | Ditch clean out - Holiday Lane & Franklin Dr - south side of Franklin from steel stake west down to Larry's Dr. Then down Larry's Dr on east side 225' to Unit 2 lot 81. Rock needed also | 2016-07-06 | Time and Material - Kriegel | 2016-07-06 | COMPLETE | 1208 Nov
16-24 | Add extension to culvert at Barbara Dr where road is eroding - build up area around culvert extension to prevent further damage to road - west of JC Miller property | 2016-07-06 | Faas Construction | 2016-07-06 | COMPLETE | 1903-04-18
16-25 | Install culvert and 2 intakes at Unit 1 lot 111 |  |  |  | Need to develop project
16-26 | Extend culvert to lake and reshape intake - Unit 2 between lots 101/102 to improve drainage to area. |  |  |  | Being surveyed and then will review action needed.
16-27 | New culvert at Dillavou Project | 2016-07-06 | Time and Material - Faas | 2016-07-06 | COMPLETE | #1199
16-28 (16-30) | Drake Drive Ditch clean out both sides plus rock |  | Time & Material |  | COMPLETE | 1209 Nov
16-29 | Repairs to misc wash outs on projects completed before seeding grew to hold in place. Rock/shaping, etc. | 2016-07-06 | Time and Material - Kriegel | 2016-07-06 | COMPLETE | #1194 + 1205
16-30 | Used on billing for Drake Dr. 16-28 |  |  | 2016-11-02 | COMPLETE | 1209 Nov
16-31 | Lakeshore Dr across from Herb Richards - ditch clean out |  | Time & Material | 2016-11-02 | COMPLETE | 1210 Nov

## 2017
Rural Improvement Zone
Project Number | Description | RIZ Approved | Awarded to | Approved to Pay | Status | Fully Paid
17-01 | West sde of Sunrise down to Lakeshore and around corner - clean out ditch and possibly replace culvert. | 2016-04-01 | Time and Material - Kriegel | 2017-10-04 | dropped off 16-04 when east side was completed | Completed $9,449.32 Oct Ck# 1236 | 12000
17-02 | Madonna Park Project - Proposal #1 - Repair of existing pond on Moon property. Includes tree removal, pipe and shaping of dam, rock, seeding. East and West Draw. FAAS Proposal #1 | 2017-04-05 | FAAS Construction & Excavating | 7/5/17 &;8/2/2017 | To proceed ASAP - $61,500 | Completed: Partial Pmt $39,000; Final $22,500 8-2-17 #1233
17-03 | Misc touch-ups on previous projects - spring work as needed (Andy's boat ramp area rock) | 2017-04-05 | Time and Material - Kriegel |  | 2017 | $1,180 - Ck 1235 | 1000
17-04 | Madonna Park Project - Proposal #2 - Silt basin below Moen's West Pond - Clearing, tile pipe through dam, shaping and seeding | 2017-07-05 | FAAS Construction & Excavating - $51,500 | 2017-10-04 | Proceed before 17-06 | Completed - $51,500 Ck# 1242
17-05 | Madonna Park Project - Proposal # 3 - Existing basin #1 - clean out basin to dimensions on plan, clear any trees to pile dirt for later use, seeding. |  | FAAS Construction & Excavating - $13,500 |  | In Review
17-06 | Madonna Park Project - Proposal #4 - New east silt pond (Moon). Clear trees, core pond, shaping and seeding | 2017-05-03 | FAAS Construction & Excavating - $38,500 | 2017-10-04 | In conjunction with 17-02. After 17-04 | Completed $38,500 Ck# 1241
17-07 | Madonna Park Project - Proposal #5 - New pond East of Terry O - Off Wesley Dr Lots 4001-4005 |  | FAAS Construction & Excavating - $38,500 |  | To be done later as funds allow - In Review
17-08 | Madonna Park Project - Proposal #6 - Raise road west of Andy's Lake 8'. Includes improved drainage, culverts, clearing of trees, rock, seeding, etc. |  | FAAS Construction & Excavating - $116,800 |  | To be done later as funds allow - In Review
17-09 | Martin Dr - ditch clean out - may have to replace culverts | 2017-04-05 | Time and Material - Kriegel |  | 2018 |  | 6000
17-10 | Erosion by main boat dock and beach area requires stone to stop the erosion from further wearing away around walking path. | 2017-05-03 | Kriegel | 2017-05-03 | Completed | Completed June 2017 $1,000 Ck# 1225
17-11 | N Lakeshore Drainage - Culverts and intakes crossing Cline property to lake. Dredging of lake at base of Fleur Drive to allow depth for culvert. | 2017-07-05 | Faas Construction & Excavating | 8/2/2017 and 10/4/17 | Completed | Completed $18,136.60 Ck# 1247, $33,893.50 Ck# 1248 & $2,247.20 Ck# 1243 | 19000
17-12 | Capital Dr ditch clean out - culvert and rock of slopes | 2017-09-06 | Kriegel | 2017-09-06 | Planned Dec 2017
17-13 | North boat ramp - erosion stone | 2017-10-04 | Kriegel | 2017-10-04 | Completed | $3,058.44 Ck# 1237 | 5000
17-14 | Skyline Dr - Ditch cleanout from Unit 5 262 to 263 | 2017-11-29 | Kriegel | 2017-11-29 | Completed | $954.00 Ck#1250

## 2018
Rural Improvement Zone
Project Number | Description | RIZ Approved | Awarded to | Approved to Pay | Status | Fully Paid
2018
18-01 | Skyline/Buena Vista - Unit 5 lot 170 - Ditch clean out | 2018-04-04 | Time & material Kriegel Excavating | 2018-04-04 | Completed | Paid Ck 1265 - $1650
18-02 | Skyline Dr - Unit 5 lot 263 - Ditch clean out and erosion repair | 2018-04-04 | Time & material Kriegel Excavating | 2018-04-04 | Completed | Paid Ck 1266 - $950
18-03 | North boat ramp/public access ditch & in front of Unit 5 lot 219 - clean ditches for improved water flow to stop erosion. Seed when completed. | 2018-06-06 | Time & material Kriegel Excavating | 2018-06-06 | Completed | Paid Ck 1267 - $983
18-04 | Ditch or catch basin needed on Skyline Drive from Drake to Buena Vista on North side of roadway. Culverts may be needed at driveways and/or to cross road to divert water flow. | 2018-06-06 | Time & material Kriegel Excavating | 2018-06-06 | Completed | Paid Ck 1268 - $1660.50
18-05 | Lakeshore & Woody Dr - install intake & ditch clean out. Owner pays for culvert. | 2018-07-11 | Time & material Kriegel Excavating | 2018-07-11
18-06 | Buena Vista & Lakeshore North Side - Culvert and ditch clean out. Owner pays for culvert. | 2018-07-11 | Time & material Kriegel Excavating | 2018-07-11
18-07 | Watering of seeding for 2018 season projects as needed. | 2018-07-11 | Time & material Kriegel Excavating | 2018-07-11 | Completed | Ck#1272 - $2500 Ck# 1279 - $400 CK#1278 $2,200
18-08 | Capital & Lakeshore Dr top side - clean out curbs. Same is needed at Barbara & Lakeshore. Ditch clean out also needed in both areas. | 2018-07-11 | Time & material Kriegel Excavating | 2018-07-11 | Completed | Ck#1271 - $2328
18-09 | Review all Holiday Lake road projects as they are completed and determine if ditch clean out is needed as well. | 2018-07-11 | Time & material Kriegel Excavating | 2018-07-11 | Closed
18-10 | Skyline Dr - Unit 5 lot 263 - Replace 8" culvert with larger culvert to handle water flow. Phase 2 | 2018-06-06 | Time & material Kriegel Excavating | 2018-07-11 | Completed - tracking additional cost to 18-02
18-11 | North Lakeshore evaluate intake - Unit 6 lots 145 - 147 | 2018-09-05 |  |  | Completed
18-12 | Remove silt from retention pond at Larry's Drive and cut off tile. Clean out culverts and silt near stand pipe. | 2018-09-05 | Faas to do while in area | 2018-09-05 | Completed
18-13 | 6129 N Lakeshore Dr - Water coming into home - Evaluate solution by cleaning ditches/adding culverts/intake - also evaluate intake near 3171/172 | 2018-09-05 |  |  | Culvert to Lake in Spring 2019
18-14 | 3032 E Lakeshore Drive - build up area at street to divert water | 2018-09-05 | Time & material Kriegel Excavating |  | Project Dropped
18-15 | 1190/1191 - East Ridge - evaluate diitches and water diversion | 2018-09-05 | Time & material Kriegel Excavating |  | Project(s) to be determined
18-16 | Seeding of ditch between Hard's driveways | 2018-10-03 | Time & material Kriegel Excavating | 2018-10-03 | Completed | $325.00 - #1284
18-17 | Replace Culvert under road at N Lakeshore 6143 and place 18" culvert at Povlick Driveway to divert water to stand pipe. | 2018-10-03 | Time & material Kriegel Excavating | 2018-10-03 | Completed
18-18 | Seeding at 3051 E Lakeshore after Holiday Lake Maintenance does road work. | 2018-10-03 | Time & material Kriegel Excavating | 2018-10-03 |  | re-evaluate
18-19 | North Boat Ramp Dredging |  | Faas | 2019-04-03
18-20 | Fluer Drive Dredging |  | Faas | 2019-04-03
18-21 | Beach Boat ramp- Dredging |  | Faas | 2019-04-03

## 2019
Rural Improvement Zone
Project Number | Description | RIZ Approved | Quoted Bid for Project/Date | Awarded to/Date | Approved to Pay | Status | Fully Paid
2019
19-01 | North Boat Ramp Dredging | 2019-04-03 |  | FAAS Construction |  | Completed
19-02 | Fluer Drive Dredging | 2019-04-03 |  | FAAS Construction |  | Completed
19-03 | Beach Boat ramp- Dredging | 2019-04-03 |  | FAAS Construction |  | Completed
19-04 | 5215 North Lakeshore- Ditch Clean out | 2019-05-01 |  | Kriegel Excavating |  | Completed
19-05 | 2159-60 E Lakeshore- Ditch Clean out and Culvert Break | 2019-05-01 | $5000/nov. 19 | Kriegel Excavating |  | Complete | 5300 | 4500
19-06 | 4094-4108 Suzan Ct- Ditch clean out and Culvert Repairs | 2019-05-01 |  | Kriegel Excavating |  | Completed |  | 3000
19-07 | Capital- Intakes an culverts | 2019-06-05 |  | Kriegel Excavating |  | Completed | seeding needs done
19-08 | Plaza- Intakes an culverts | 2019-06-05 |  | Kriegel Excavating |  | Completed
19-09 | Barbara 2 culverts at camp ground, clean out ditches | 2019-06-05 |  | Kriegel Excavating |  | Completed |  | 4000
19-10 | Banzoff- Culvert and rock ditch | 2019-06-05 |  | Kriegel Excavating | 2019-06-05 | Completed |  | 2200
19-11 | 1190 East Ridge- Ditch clean out and erosion control | 2019-07-03
19-12 | Duck Park- Ditch Clean Out- (Larry's dr) | 2019-07-03 |  | Kriegel Excavating |  | Complete
19-13 | 5191 Delta Drive- Ditch Clean out- culvert work | 2019-07-03
19-14 | 6237 Woody Dr- Ditch clean out- Culvert is Plugged | 2019-07-03 | $2500.00- 10/2/19 | Kriegel Excavation |  | Complete
19-15 | Barbara dr. Tree clean out | 2019-07-03 |  | FAAS Construction | Sept. 2019 | Completed
19-16 | Earl Thomas- Ditch Clean out | 2019-07-03 |  | Kriegel Excavating | Sept. 2019 | completed
19-17 | Corner of S.Lakeshore cut off Riser | 2019-07-03 |  | FAAS Construction |  | completed
19-18 | Povilic culvert extension and Rock | 2019-09-04 |  | Kriegel Excavating | 2019-09-04 | Complete
19-19 | Herbert Drive- Ditch Cleanout (Bob Smith) east drive way south 585 ft down to crossroad culvert at south Lakeshore and move culvert, rock driveway. Clean out around standpipe south of Dee and South Lakeshore. | 2019-10-02 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Complete
19-20 | 4209 Tracy and West Lakeshore- Ditch cleanout from west Lakeshore to new driveway on Tracy. 30ft | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Complete
19-21 | Lawnmower Joes and Shannon Hersey- Cut break in culvert North of Joes driveway and reshape Joes Driveway, | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16
19-22 | NE Lakeshore and Korn's- Ditch Cleanout both ends of culvert on Korns 50ft.(both ways). Rack up Korns on north side as needed. | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Completed
19-23 | Kerry Barry- Ditch Cleanout east side of driveway's 50ft. | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 |  | This project has been tabled for a later date.
19-24 | Andy Boat Ramp- Big Rock needed to stop erosion | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Completed
19-25 | Norm DeGeeter's Lot 1189- Ditch Clean out | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-26 | Larry's Dr. North side raise and clean silt pond | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-27 | Lot 4044 South Lakeshore and Dee to the east | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-28 | Woodland Hill Dr, North of Phills Dr, west side. Ditch Clean out | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-29 | North Lakeshore Dr. between sunrise and Drake. Lower shoulder 200ft on north side and 100ft on south side | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-30 | South Lakeshore Dr and new raise road, Clean out hillside 200Ft. | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06
19-31 | South Boat Ramp- Sink hole and shore line siding into lake. ( Emergency project) | 2019-11-25 | 2019-11-25 | Rick Kriegel Excavating | 2019-11-25 | Completed | $7426.24- 11/27/19

## 2020
Rural Improvement Zone
Project Number | Description | RIZ Approved | Quoted Bid for Project/Date | Awarded to/Date | Approved to Pay | Status | Fully Paid
16-10 | Ditch clean out - Franklin Dr #1. Unit 2 - 1 to 7 (BUS STOP & TURN AROUND) | 2016-07-06 |  | Time and Material - Kriegel | 2016-07-06 | Completed August 2018 | Chk 1275 - $2485 | 1500
16-12 | Ditch clean out - Wilson Ave. Unit 1 - 368 to 372. Cut edges off above culverts on top half. | 2016-05-04 | $2500.00- 10/2/19 | Kriegel Excavating | 2016-06-01 | Completed |  | 1400
16-13 | Ditch clean out - Lakeshore Dr. Unit 1 - 182 & 183. Ditch below Becky Payne property is filled in. | 2016-05-04 |  | Kriegel Excavating | 2016-07-06 | Completed |  | 1000
16-15 | Ditch clean out - Caron Dr to Lakeshore. Unit 1 - 133 & 134. Establish ditch, cut edges and grass on North side. | 2016-05-04 |  | Kriegel Excavating | 2016-06-01 | Completed | $2,185.00 - #1285 | 2000
16-18 | Ditch clean out - Franklin Dr - Unit 2 from lot 213 down to S Lakeshore, around corner to lot 96. 447' & 65' (Down hill in front of Wayne Johannes Residence) | 2016-07-06 |  | Time and Material - Kriegel | 2016-07-06 | Completed | $4,482 - #1287 | 12000
16-20 | Ditch clean out - Park Ct Unit 1 lot 234. Establish ditch on south side, cut grass edges of ditch on north side. Need culverts added on south side for 2 campers. | [5 empty] | Need to re-evaluate
16-21 | Ditch clean out - Caron Dr Unit 1 from lot 421 to orange stand pipe on east side 440' | 2016-07-06 |  | Time and Material - Kriegel | 2016-07-06 | Completed | $2,289.00 - #1286 | 1000
16-25 | Install culverts and intakes in the area of Unit 1 lot 111 between Schwab's and Robinson's property. | 2017-05-03 |  | Kriegel Excavating | 2017-05-03 | Completed Paid Ck#1251 | 7835 | 7605
17-04 | Madonna Park Project - Proposal #2 - Silt basin below Moen's West Pond - Clearing, tile pipe through dam, shaping and seeding | 2017-07-05 |  | FAAS Construction & Excavating - $51,500 | 2017-10-04 | Proceed before 17-06 | Completed - $51,500 Ck# 1242 ck#1277 - $8208 CK#1282 $15,687.04 Ck# 1277 $8,208.00
17-05 | Madonna Park Project - Proposal # 3 - Existing basin #1 - clean out basin to dimensions on plan, clear any trees to pile dirt for later use, seeding. |  |  | FAAS Construction & Excavating - $13,500 |  | Completed | 14850
17-07 | Madonna Park Project - Proposal #5 - New pond East of Terry O - Off Wesley Dr Lots 4001-4005 |  |  | FAAS Construction & Excavating - $38,500 |  | Completed
17-08 | Madonna Park Project - Proposal #6 - Raise road west of Andy's Lake 8'. Includes improved drainage, culverts, clearing of trees, rock, seeding, etc. |  |  | FAAS Construction & Excavating - $116,800 |  | Completed | 128480
17-09 | Martin Dr - ditch clean out | 2017-04-05 |  | Time and Material - Kriegel |  | Completed |  | 6000
17-12 | Capital Dr ditch clean out - rock of slopes | 2017-09-06 |  | Kriegel | 2017-09-06 | Completed | Ck# 1273 $200/Ck#1270 $3305.64
2018
18-01 | Skyline/Buena Vista - Unit 5 lot 170 - Ditch clean out | 2018-04-04 |  | Time & material Kriegel Excavating | 2018-04-04 | Completed | Paid Ck 1265 - $1650
18-02 | Skyline Dr - Unit 5 lot 263 - Ditch clean out and erosion repair | 2018-04-04 |  | Time & material Kriegel Excavating | 2018-04-04 | Completed | Paid Ck 1266 - $950
18-03 | North boat ramp/public access ditch & in front of Unit 5 lot 219 - clean ditches for improved water flow to stop erosion. Seed when completed. | 2018-06-06 |  | Time & material Kriegel Excavating | 2018-06-06 | Completed | Paid Ck 1267 - $983
18-04 | Ditch or catch basin needed on Skyline Drive from Drake to Buena Vista on North side of roadway. Culverts may be needed at driveways and/or to cross road to divert water flow. | 2018-06-06 |  | Time & material Kriegel Excavating | 2018-06-06 | Completed | Paid Ck 1268 - $1660.50
18-05 | Corner of Lakeshore & Woody Dr - install intake & ditch clean out. In stall drop box. Owner pays for culvert. | 2018-07-11 |  | Rick Kriegel Excavating | 2018-07-11 | Completed |  | 4500
18-06 | Buena Vista & Lakeshore North Side - Culvert and ditch clean out. Owner pays for culvert. | 2018-07-11 |  | Rick Kriegel Excavating | 2018-07-11 | Completed |  | 3000
18-07 | Watering of seeding for 2018 season projects as needed. | 2018-07-11 |  | Time & material Kriegel Excavating | 2018-07-11 | Completed | Ck#1272 - $2500 Ck# 1279 - $400 CK#1278 $2,200
18-08 | Capital & Lakeshore Dr top side - clean out curbs. Same is needed at Barbara & Lakeshore. Ditch clean out also needed in both areas. | 2018-07-11 |  | Time & material Kriegel Excavating | 2018-07-11 | Completed | Ck#1271 - $2328
18-09 | Review all Holiday Lake road projects as they are completed and determine if ditch clean out is needed as well. | 2018-07-11 |  | Time & material Kriegel Excavating | 2018-07-11 | Closed
18-10 | Skyline Dr - Unit 5 lot 263 - Replace 8" culvert with larger culvert to handle water flow. Phase 2 | 2018-06-06 |  | Time & material Kriegel Excavating | 2018-07-11 | Completed - tracking additional cost to 18-02
18-11 | North Lakeshore evaluate intake - Unit 6 lots 145 - 147 | 2018-09-05 |  |  |  | Completed
18-12 | Remove silt from retention pond at Larry's Drive and cut off tile. Clean out culverts and silt near stand pipe. | 2018-09-05 |  | Faas to do while in area | 2018-09-05 | Completed
18-13 | 6129 N Lakeshore Dr - Water coming into home - Evaluate solution by cleaning ditches/adding culverts/intake - also evaluate intake near 3171/172 | 2018-09-05 |  | Rick Kriegel Excavating | 2019-06-05 | Completed
18-15 | 1190/1191 - East Ridge - evaluate ditches and water diversion | 2018-09-05 |  | Rick Kriegel Excavating |  | Project(s) to be determined
18-16 | Seeding of ditch between Hard's driveways | 2018-10-03 |  | Time & material Kriegel Excavating | 2018-10-03 | Completed | $325.00 - #1284
18-17 | Replace Culvert under road at N Lakeshore 6143 and place 18" culvert at Povlick Driveway to divert water to stand pipe. | 2018-10-03 |  | Time & material Kriegel Excavating | 2018-10-03 | Completed
2019
19-01 | North Boat Ramp Dredging | 2019-04-03 |  | FAAS Construction |  | Completed
19-02 | Fluer Drive Dredging | 2019-04-03 |  | FAAS Construction |  | Completed
19-03 | Beach Boat ramp- Dredging | 2019-04-03 |  | FAAS Construction |  | Completed
19-04 | 5215 North Lakeshore- Ditch Clean out | 2019-05-01 |  | Kriegel Excavating |  | Completed
19-05 | 2159-60 E Lakeshore- Ditch Clean out and Culvert Break | 2019-05-01 | $5000/nov. 19 | Kriegel Excavating
19-06 | 4094-4108 Suzan Ct- Ditch clean out and Culvert Repairs | 2019-05-01 |  | Kriegel Excavating |  | Completed |  | 3000
19-07 | Capital- Intakes an culverts | 2019-06-05 |  | Kriegel Excavating |  | Completed | seeding needs done
19-08 | Plaza- Intakes an culverts | 2019-06-05 |  | Kriegel Excavating |  | Completed
19-09 | Barbara 2 culverts at camp ground, clean out ditches | 2019-06-05 |  | Kriegel Excavating |  | Completed |  | 4000
19-10 | Banzoff- Culvert and rock ditch | 2019-06-05 |  | Kriegel Excavating | 2019-06-05 | Completed |  | 2200
19-11 | 1190 East Ridge- Ditch clean out and erosion control | 2019-07-03
19-12 | Duck Park- Ditch Clean Out- (Larry's dr) | 2019-07-03 |  | Kriegel Excavating |  | Complete
19-13 | 5191 Delta Drive- Ditch Clean out- culvert work | 2019-07-03
19-14 | 6237 Woody Dr- Ditch clean out- Culvert is Plugged | 2019-07-03 | $2500.00- 10/2/19 | Kriegel Excavation |  | Complete
19-15 | Barbara dr. Tree clean out | 2019-07-03 |  | FAAS Construction | Sept. 2019 | Completed
19-16 | Earl Thomas- Ditch Clean out | 2019-07-03 |  | Kriegel Excavating | Sept. 2019 | completed
19-17 | Corner of S.Lakeshore cut off Riser | 2019-07-03 |  | FAAS Construction |  | completed
19-18 | Povilic culvert extension and Rock | 2019-09-04 |  | Kriegel Excavating | 2019-09-04 | Complete
19-19 | Herbert Drive- Ditch Cleanout (Bob Smith) east drive way south 585 ft down to crossroad culvert at south Lakeshore and move culvert, rock driveway. Clean out around standpipe south of Dee and South Lakeshore. | 2019-10-02 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Complete
19-20 | 4209 Tracy and West Lakeshore- Ditch cleanout from west Lakeshore to new driveway on Tracy. 30ft | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Complete
19-21 | Lawnmower Joes and Shannon Hersey- Cut break in culvert North of Joes driveway and reshape Joes Driveway, | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16
19-22 | NE Lakeshore and Korn's- Ditch Cleanout both ends of culvert on Korns 50ft.(both ways). Rack up Korns on north side as needed. | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Completed
19-23 | Kerry Barry- Ditch Cleanout east side of driveway's 50ft. | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 |  | This project has been tabled for a later date.
19-24 | Andy Boat Ramp- Big Rock needed to stop erosion | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Completed
19-25 | Norm DeGeeter's Lot 1189- Ditch Clean out | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-26 | Larry's Dr. North side raise and clean silt pond | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-27 | Lot 4044 South Lakeshore and Dee to the east | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-28 | Woodland Hill Dr, North of Phills Dr, west side. Ditch Clean out | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-29 | North Lakeshore Dr. between sunrise and Drake. Lower shoulder 200ft on north side and 100ft on south side | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-30 | South Lakeshore Dr and new raise road, Clean out hillside 200Ft. | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed | 1500
19-31 | South Boat Ramp- Sink hole and shore line siding into lake. ( Emergency project) | 2019-11-25 | 2019-11-25 | Rick Kriegel Excavating | 2019-11-25 | Completed | $7426.24- 11/27/19
2020
20-01 | Dee & Phelps- Ditch needs cleaned out on both sides of the road to keep the water from running down the road. Replace Culvert | 2020-04-01 | 5087 | Rick Kriegel Excavating April 14, 2020 | June 3,2020 | Completed | 6337.5
20-02 | Park Court- Cle-an out ditch-Replace 1 culvert and install 1 culvert- Unit 1 Lot 232 & 235 | 2020-04-01 | 2568 | Rick Kriegel Excavating April 14, 2020 | June 3,2020 | Completed | 2718
20-03 | South Lakeshore Dr west of angler Court- Clean ditch to keep water off the road. | 2020-04-01 | 2475 | Rick Kriegel Excavating April 14, 2020 | June 3,2020 | Completed | 2475
20-04 | Woodland Hill Between Dee & Phelps- Ditch Clean out | 2020-04-01 | 1837.5 | Rick Kriegel Excavating April 14, 2020 | June 3,2020 | Completed | 1837.5
20-05 | South Lakeshore below Audries- Clean ditch | 2020-04-01 | 1000 | Rick Kriegel Excavating April 14, 2020 | June 3,2020 | Completed | 1150
20-06 | Waukonda Dr & Shady Dr. - Clean ditch and install new Culvert | 2020-04-01 | 3056 | Rick Kriegel Excavating April 14, 2020 | June 3,2020 | Completed | 3206
20-07 | Norm DeGeeter's Lot 1-178-79- Culvert needs to be replaced throug property and ditch. Reseeding or resode. | 2020-06-03 | 15000 | FAAS Construction
20-08 | Silt pond- Dock Park- Clean out pond | 2020-06-03 | 2500 | FAAS Construction | 2020-09-02 | Completed | 2500
20-09 | Larry's Pond. Clean out pond | 2020-06-03 | 5000 | FAAS Construction | 2020-09-02 | Completed | 5000
20-10 | Silt pond by Unit 3-51- Pond needs cleaned out and enlarged if possible | 2020-06-03 | 1500 | Rick Kriegel Exc | 2020-07-02
20-11 | Brian Kline- Unit1-302- Drop inlet needs added to existing culvert to run through property and build burm to divert water. | 2020-06-03 | 4200 | Rick Kriegel Excavating | 2020-11-04 | Completed | 2500
20-12 | Franklin Dr Unit 1-250,251,235,240- Clean out ditchs on North Side. Fix erroded area and Line with rip-rap | 2020-06-03 | 7000 10/7/20 | Rick Kriegel Excavating | 2020-11-04 | Completed | 11000
20-13 | John Nielson- Unit 1-150- Clean ditch and cut grass curb along edge of road. This way water gets into the ditvh | 2020-06-03 | 1500 | Rick Kriegel Excavating | 2020-10-07 | Completed | 1500
20-14 | HLO- Unit 1-194,195,198,201- Clean ditch- If possible divert down hill into Lot 195 to reduce amount of water from the north. | 2020-06-03 | 3200 | Rick Kriegel Excavating | 2020-10-07 | Completed | 3200
20-15 | HLO- Casual Park and Peter's lake- Big rock needs to be place around en of culver. | 2020-06-03 | 1600 | Rick Kriegel Excavating | 2020-10-07 | Completed | 1600
20-16 | West Lakeshore- Unit 4-228 thru 234- Clean ditch so water can get to silt pond. Reseeding will need to be done. Clean out brush | 2020-06-03 | 3000 | Rick Kriegel Excavating | 2020-10-07 | Completed | 3000
20-17 | HLO- Unit 5-248, Clean out silt pond and rip=rap road sides ditches. | 2020-06-03 | 3200 | Rick Kriegel Excavating | 2020-10-07 | Completed | 3750
20-18 | HLO Unit 2-95 & BelAire Dr- Riz will replace culvert across from belaire and install extension on North end | 2020-06-03 | 3500 | Rick Kriegel Excavating | 2020-11-04 | Completed | 3500
20-19 | HLO Unit 5-56-57- Move diversion between lot 56 &57 and possible line with rock or mate. | 2020-06-03 | 1000 | Rick Kriegel Excavating | 2020-10-07 | Completed | 1500
20-20 | HLO- Beach boat ramp- Cement both sides of the boat ramp- Cement cost $1000.00 HLO to pay labor | 2020-06-03 | 1000.00 from Riz
20-21 | Unit 6-220,208,209,145,146- Reseed ditch with hydo malch seeding | 2020-06-03 | For Hydro seeding- $600.00 | Shane Deimerly | 2020-07-02 | Completed | 1500
20-22 | Bryon Sunkle/HLO- Lower area between lake and road has standing water. Riz to pay for culvert, Bryron would install | 2020-06-03 | 1000 | Bryron Sunkle | 2020-07-02 | Completed | 1000
20-23 | HLO Unit 4-321,322,323,369- Reshape hillside and reseed. | 2020-06-03 | 7500 | FAAS Construction
20-24 | Delta-12inch under drive then it when to an 8inch and kit keeps getting plugged. Ditch needs cleaned out, and need to brake away. | 2020-07-02 | 4000.00 9/5/2020 | Rick Kriegel | 2020-11-04 | Completed | 4000
20-25 | Unit 6-129,130-Water from the down spout from the heavy rains caused the water to go under the sod and hit the loose dirt next to the culvert. This washed down to the lake. | 2020-07-11 | 1600 7/2/2020 | Rick Kriegel Excavating | 2020-08-05 | Completed | 1600
20-26 | Unit 6 144- expand silt pond | 2020-08-05 | 1500 10/7/2020 | Rick Kriegel Excavating | 2020-11-04 | Completed | 1500
20-27 | Unit 5 Lot 276-277- Culvert is to high and the water is going over the road. Instate needs to be lowered and reshaped. | 2020-08-05 | 1200 10/7/2020 | Rick Kriegel Excavating | 2020-11-04 | Completed | 1200
20-28 | Lot 5053-54-Create a collection drain and ditch on west side of echo Dr to run water to the collection point | 2020-09-02 | 3500 | Rick Kriegel Excavating | 2020-10-07 | Completed | 4050
20-29 | Sharon Drive.Clean out 260 ft of ditch on lot 4-161. Culvert will need to be removed and reinstalled. | 2020-09-02 | 3000 | Rick Kriegel Excavating | 2020-09-02 | Completed | 3000
20-30 | Prepare Andy's Pond Dredging retention basin to receive 7,259 cubic yards of soft equipement. | 2020-10-07 | 53,000.00 10/7/2020 | FAAS Construction
20-31 | Dredging Andy Pond | 2020-10-07 | 89,702.00 10/7/2020 | Mid American Dredging
20-32 | clean the ditch, install two owner provided culverts, install erosion matting/seeding | 2020-10-15 | 4000 10/15/2020 | Rick Kriegel Excavating | 2020-11-04 | Completed | 4000
20-33 | remove an existing culvert, clean out the ditch, install erosion stone, erosion matting/seeding | 2020-10-15 | 4500 10/15/2020 | Rick Kriegel Excavating | 2020-11-04 | Completed | 4500
20-34 | to clean the ditch above Kroeze’s lot, build a small berm to keep water from running down his driveway, install matting/seeding | 2020-10-15 | 1200 10/15/2020 | Rick Kriegel Excavating | 2020-11-04 | Completed | 1200
20-35 | hire Mapping Networks to perform a post dredge analysis of the sediment removed from Andy’s pond | 2020-10-15 | 3825 10/15/2020

## 2021-2022
Rural Improvement Zone
Project Number | Description | RIZ Approved | Quoted Bid for Project/Date | Awarded to/Date | Approved to Pay | Status | Fully Paid
16-10 | Ditch clean out - Franklin Dr #1. Unit 2 - 1 to 7 (BUS STOP & TURN AROUND) | 2016-07-06 |  | Time and Material - Kriegel | 2016-07-06 | Completed August 2018 | Chk 1275 - $2485 | 1500
16-12 | Ditch clean out - Wilson Ave. Unit 1 - 368 to 372. Cut edges off above culverts on top half. | 2016-05-04 | $2500.00- 10/2/19 | Kriegel Excavating | 2016-06-01 | Completed |  | 1400
16-13 | Ditch clean out - Lakeshore Dr. Unit 1 - 182 & 183. Ditch below Becky Payne property is filled in. | 2016-05-04 |  | Kriegel Excavating | 2016-07-06 | Completed |  | 1000
16-15 | Ditch clean out - Caron Dr to Lakeshore. Unit 1 - 133 & 134. Establish ditch, cut edges and grass on North side. | 2016-05-04 |  | Kriegel Excavating | 2016-06-01 | Completed | $2,185.00 - #1285 | 2000
16-18 | Ditch clean out - Franklin Dr - Unit 2 from lot 213 down to S Lakeshore, around corner to lot 96. 447' & 65' (Down hill in front of Wayne Johannes Residence) | 2016-07-06 |  | Time and Material - Kriegel | 2016-07-06 | Completed | $4,482 - #1287 | 12000
16-20 | Ditch clean out - Park Ct Unit 1 lot 234. Establish ditch on south side, cut grass edges of ditch on north side. Need culverts added on south side for 2 campers. | [5 empty] | Need to re-evaluate
16-21 | Ditch clean out - Caron Dr Unit 1 from lot 421 to orange stand pipe on east side 440' | 2016-07-06 |  | Time and Material - Kriegel | 2016-07-06 | Completed | $2,289.00 - #1286 | 1000
16-25 | Install culverts and intakes in the area of Unit 1 lot 111 between Schwab's and Robinson's property. | 2017-05-03 |  | Kriegel Excavating | 2017-05-03 | Completed Paid Ck#1251 | 7835 | 7605
17-04 | Madonna Park Project - Proposal #2 - Silt basin below Moen's West Pond - Clearing, tile pipe through dam, shaping and seeding | 2017-07-05 |  | FAAS Construction & Excavating - $51,500 | 2017-10-04 | Proceed before 17-06 | Completed - $51,500 Ck# 1242 ck#1277 - $8208 CK#1282 $15,687.04 Ck# 1277 $8,208.00
17-05 | Madonna Park Project - Proposal # 3 - Existing basin #1 - clean out basin to dimensions on plan, clear any trees to pile dirt for later use, seeding. |  |  | FAAS Construction & Excavating - $13,500 |  | Completed | 14850
17-07 | Madonna Park Project - Proposal #5 - New pond East of Terry O - Off Wesley Dr Lots 4001-4005 |  |  | FAAS Construction & Excavating - $38,500 |  | Completed
17-08 | Madonna Park Project - Proposal #6 - Raise road west of Andy's Lake 8'. Includes improved drainage, culverts, clearing of trees, rock, seeding, etc. |  |  | FAAS Construction & Excavating - $116,800 |  | Completed | 128480
17-09 | Martin Dr - ditch clean out | 2017-04-05 |  | Time and Material - Kriegel |  | Completed |  | 6000
17-12 | Capital Dr ditch clean out - rock of slopes | 2017-09-06 |  | Kriegel | 2017-09-06 | Completed | Ck# 1273 $200/Ck#1270 $3305.64
2018
18-01 | Skyline/Buena Vista - Unit 5 lot 170 - Ditch clean out | 2018-04-04 |  | Time & material Kriegel Excavating | 2018-04-04 | Completed | Paid Ck 1265 - $1650
18-02 | Skyline Dr - Unit 5 lot 263 - Ditch clean out and erosion repair | 2018-04-04 |  | Time & material Kriegel Excavating | 2018-04-04 | Completed | Paid Ck 1266 - $950
18-03 | North boat ramp/public access ditch & in front of Unit 5 lot 219 - clean ditches for improved water flow to stop erosion. Seed when completed. | 2018-06-06 |  | Time & material Kriegel Excavating | 2018-06-06 | Completed | Paid Ck 1267 - $983
18-04 | Ditch or catch basin needed on Skyline Drive from Drake to Buena Vista on North side of roadway. Culverts may be needed at driveways and/or to cross road to divert water flow. | 2018-06-06 |  | Time & material Kriegel Excavating | 2018-06-06 | Completed | Paid Ck 1268 - $1660.50
18-05 | Corner of Lakeshore & Woody Dr - install intake & ditch clean out. In stall drop box. Owner pays for culvert. | 2018-07-11 |  | Rick Kriegel Excavating | 2018-07-11 | Completed |  | 4500
18-06 | Buena Vista & Lakeshore North Side - Culvert and ditch clean out. Owner pays for culvert. | 2018-07-11 |  | Rick Kriegel Excavating | 2018-07-11 | Completed |  | 3000
18-07 | Watering of seeding for 2018 season projects as needed. | 2018-07-11 |  | Time & material Kriegel Excavating | 2018-07-11 | Completed | Ck#1272 - $2500 Ck# 1279 - $400 CK#1278 $2,200
18-08 | Capital & Lakeshore Dr top side - clean out curbs. Same is needed at Barbara & Lakeshore. Ditch clean out also needed in both areas. | 2018-07-11 |  | Time & material Kriegel Excavating | 2018-07-11 | Completed | Ck#1271 - $2328
18-09 | Review all Holiday Lake road projects as they are completed and determine if ditch clean out is needed as well. | 2018-07-11 |  | Time & material Kriegel Excavating | 2018-07-11 | Closed
18-10 | Skyline Dr - Unit 5 lot 263 - Replace 8" culvert with larger culvert to handle water flow. Phase 2 | 2018-06-06 |  | Time & material Kriegel Excavating | 2018-07-11 | Completed - tracking additional cost to 18-02
18-11 | North Lakeshore evaluate intake - Unit 6 lots 145 - 147 | 2018-09-05 |  |  |  | Completed
18-12 | Remove silt from retention pond at Larry's Drive and cut off tile. Clean out culverts and silt near stand pipe. | 2018-09-05 |  | Faas to do while in area | 2018-09-05 | Completed
18-13 | 6129 N Lakeshore Dr - Water coming into home - Evaluate solution by cleaning ditches/adding culverts/intake - also evaluate intake near 3171/172 | 2018-09-05 |  | Rick Kriegel Excavating | 2019-06-05 | Completed
18-15 | 1190/1191 - East Ridge - evaluate ditches and water diversion | 2018-09-05 |  | Rick Kriegel Excavating |  | Project(s) to be determined
18-16 | Seeding of ditch between Hard's driveways | 2018-10-03 |  | Time & material Kriegel Excavating | 2018-10-03 | Completed | $325.00 - #1284
18-17 | Replace Culvert under road at N Lakeshore 6143 and place 18" culvert at Povlick Driveway to divert water to stand pipe. | 2018-10-03 |  | Time & material Kriegel Excavating | 2018-10-03 | Completed
2019
19-01 | North Boat Ramp Dredging | 2019-04-03 |  | FAAS Construction |  | Completed
19-02 | Fluer Drive Dredging | 2019-04-03 |  | FAAS Construction |  | Completed
19-03 | Beach Boat ramp- Dredging | 2019-04-03 |  | FAAS Construction |  | Completed
19-04 | 5215 North Lakeshore- Ditch Clean out | 2019-05-01 |  | Kriegel Excavating |  | Completed
19-05 | 2159-60 E Lakeshore- Ditch Clean out and Culvert Break | 2019-05-01 | $5000/nov. 19 | Kriegel Excavating
19-06 | 4094-4108 Suzan Ct- Ditch clean out and Culvert Repairs | 2019-05-01 |  | Kriegel Excavating |  | Completed |  | 3000
19-07 | Capital- Intakes an culverts | 2019-06-05 |  | Kriegel Excavating |  | Completed | seeding needs done
19-08 | Plaza- Intakes an culverts | 2019-06-05 |  | Kriegel Excavating |  | Completed
19-09 | Barbara 2 culverts at camp ground, clean out ditches | 2019-06-05 |  | Kriegel Excavating |  | Completed |  | 4000
19-10 | Banzoff- Culvert and rock ditch | 2019-06-05 |  | Kriegel Excavating | 2019-06-05 | Completed |  | 2200
19-11 | 1190 East Ridge- Ditch clean out and erosion control | 2019-07-03
19-12 | Duck Park- Ditch Clean Out- (Larry's dr) | 2019-07-03 |  | Kriegel Excavating |  | Complete
19-13 | 5191 Delta Drive- Ditch Clean out- culvert work | 2019-07-03
19-14 | 6237 Woody Dr- Ditch clean out- Culvert is Plugged | 2019-07-03 | $2500.00- 10/2/19 | Kriegel Excavation |  | Complete
19-15 | Barbara dr. Tree clean out | 2019-07-03 |  | FAAS Construction | Sept. 2019 | Completed
19-16 | Earl Thomas- Ditch Clean out | 2019-07-03 |  | Kriegel Excavating | Sept. 2019 | completed
19-17 | Corner of S.Lakeshore cut off Riser | 2019-07-03 |  | FAAS Construction |  | completed
19-18 | Povilic culvert extension and Rock | 2019-09-04 |  | Kriegel Excavating | 2019-09-04 | Complete
19-19 | Herbert Drive- Ditch Cleanout (Bob Smith) east drive way south 585 ft down to crossroad culvert at south Lakeshore and move culvert, rock driveway. Clean out around standpipe south of Dee and South Lakeshore. | 2019-10-02 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Complete
19-20 | 4209 Tracy and West Lakeshore- Ditch cleanout from west Lakeshore to new driveway on Tracy. 30ft | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Complete
19-21 | Lawnmower Joes and Shannon Hersey- Cut break in culvert North of Joes driveway and reshape Joes Driveway, | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16
19-22 | NE Lakeshore and Korn's- Ditch Cleanout both ends of culvert on Korns 50ft.(both ways). Rack up Korns on north side as needed. | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Completed
19-23 | Kerry Barry- Ditch Cleanout east side of driveway's 50ft. | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 |  | This project has been tabled for a later date.
19-24 | Andy Boat Ramp- Big Rock needed to stop erosion | 2019-10-16 | 2019-10-16 | Rick Kriegel Excavating | 2019-10-16 | Completed
19-25 | Norm DeGeeter's Lot 1189- Ditch Clean out | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-26 | Larry's Dr. North side raise and clean silt pond | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-27 | Lot 4044 South Lakeshore and Dee to the east | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-28 | Woodland Hill Dr, North of Phills Dr, west side. Ditch Clean out | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-29 | North Lakeshore Dr. between sunrise and Drake. Lower shoulder 200ft on north side and 100ft on south side | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed
19-30 | South Lakeshore Dr and new raise road, Clean out hillside 200Ft. | 2019-11-06 | 2019-11-06 | Rick Kriegel Excavating | 2019-11-06 | Completed | 1500
19-31 | South Boat Ramp- Sink hole and shore line siding into lake. ( Emergency project) | 2019-11-25 | 2019-11-25 | Rick Kriegel Excavating | 2019-11-25 | Completed | $7426.24- 11/27/19
2021
21-01 | Burn tree pile on Dennis Moons Lot 2306. Place in a hole and bury the trees | 2021-03-03 | $4500.00/ 3/3/21 | FAAS Construction
21-02 | remove 8,000 cubic yards of sediment from Poe’s & Bob’s Coves | 2021-04-07 | $106,461.00 4/7/2021 | Mid-American Dredging | 2021-11-03 | Completed
21-03 | prepare Bob’s sediment retention basin to receive 4,000 cubic yards of sediment | 2021-04-07 | 37725 | FAAS Construction | 2021-07-07 | Completed
21-04 | Holiday Lake Tire reef removal | 2021-05-05 | $10, 276.00 | Blake | 2021-07-07 | Completed
21-05 | Brian Cline Erosion- Culvert | 2021-05-05 | 24000 | FAAS Construction | 2021-09-01 | Completed | 25170
21-06 | Sean Mcintyre- Dig out ditch- Drain Erosion | 2021-05-05 | 11970 | FAAS Construction | 2021-07-07 | Completed
21-07 | owner of 3066 Joan Dr would like to relocate culvert due to wanting to build new garage. Get it back on property line. | 2021-06-02 | 3300 | FAAS Construction | 2021-06-02 | Completed
21-08 | Prepare Hap’s Cove sediment basin | 2021-07-07 | 58000 | FAAS Construction | 2021-07-07 | Completed | 58000
21-09 | Put a swell in the Road across from Unit 1 lot 54 to help with water way. 3 drive ways. | 2021-08-04 |  | Rick Kriegel Excavating |  | No longer needed
21-10 | Main outlet for water overflow for the dam- Concrete repair | 2021-10-06
Project Number | Description | RIZ Approved | Quoted Bid for Project/Date | Awarded to/Date | Approved to Pay | Status | Fully Paid
2022
22-01 | Aquatic Ecosystem Consultants ($19,175) Help in protecting lake Vegetation and two ponds ( Bozo and Andy) | 2022-02-02 | 2/2/2022- $19,175 | Aquatic Systems | 2022-02-02 | Completed
22-02 | Beach E.coli testing and Micro sampling for water quality (Simular to DNR) | 2022-02-02 | 4/6/2022- $400.00 | Brad Storm | 2022-04-06 | Completed
22-03 | Dig and install an intake(concrete) | 2022-04-06 | 4/6/22 $12,300.00 | FAAS Construction | 2022-04-06 | Complete
22-04 | Reshape and seed the ditch on lots 1175 & 1176. (Lake to put a layer of asphalt). | 2022-04-06 | 4/6/2022 $1,500.00 | Rick Kriegel Excavating | 2022-04-06 | Completed | 1500
22-05 | Gary Edwards- Eroision coming off the roat at 2292 S.Lakeshore. Install rip rap with geotextile fabric start at S.Lakeshore & Tracy and going 150ft north. | 2022-04-06 | 4/6/22 $22,145.00 | FAAS Construction | 2022-04-06 | Completed | 22145
22-06 | Josh Hobart- 1131 Lakeshore- Multiple erosion concers. Reshape and seed approximatley 170ft of ditch at 1133 Caron Drive. | 2022-04-06 | 4/6/22 $1500.00 | Rick Kriegel Excavating | 2022-04-06 | Completed | 1200
22-07 | replace the rusted out culvert under County Public Rd with a smooth bore double lined plastic culvert and unanimously approved. | 2022-04-26 | 5751.49 | Rick Kriegel Excavating | 2022-08-03 | Completed | 5751.49
22-08 | Lake Dredging- | 2022-07-06 |  | Mid-American Dredging |  | Completed

## 2023
Rural Improvement Zone
Project Number | Description | RIZ Approved | Quoted Bid for Project/Date | Awarded to/Date | Approved to Pay | Status | Fully Paid
2023
23-01 | Aquatic Ecosystem Consultants ($19,175) Help in protecting Main lake Vegetation and two ponds ( Bozo and Andy) | 2023-01-04 | 1/4/2023 $20, | Aquatic Systems | 2023-01-04 | In Progress
23-02
23-03
23-04
23-05
23-06
23-07
23-08
23-09