# CAP 205 Process – Visual Flowchart (SmartArt‑Style)

1. Federal Interest Determination (2016) Mallard Lakes found eligible for CAP 205.

⬇️

2. Non-Federal Sponsor Identified Letter of Intent expressing willingness.

⬇️

3. USACE District Requests Regional HQ Approval Confirms capacity to proceed.

⬇️

4. Compete for Federal PMP Funds (~$50K) 100% Federal funding for PMP.

⬇️

5. USACE Develops Project Management Plan (PMP) Defines scope, schedule, feasibility cost.

⬇️

6. Feasibility Cost Sharing Agreement (FCSA) USACE + Sponsor sign; study begins.

⬇️

7. Feasibility Study (18–36 months) Engineering, economics, environmental analysis.

⬇️

8. Agency Review Milestones (ATR, Division) Quality, policy compliance.

⬇️

9. Tentatively Selected Plan (TSP) Approved alternative identified.

⬇️

10. Detailed Design / Permitting Plans & specifications.

⬇️

11. Project Partnership Agreement (PPA) Required before construction.

⬇️

12. Construction Phase Cost‑shared implementation.

⬇️

13. Project Completion & Turnover Operations & maintenance to sponsor.