Sylvain Gbogbo

**Abstract**

Donation of medical supplies to the health center of Baguida


end project report

United mission to Africa

|  |  |  |  |
| --- | --- | --- | --- |
| Project/ Program Name | Medical Supplies Donation to the Centre Medico-Social de Baguida-TOGO | | |
| Project sponsor | United mission to Africa | | |
| Project/Program Manager | United mission to Africa | | |
| Start date | 01/15/2022 | Completion Date | 07/15/2022 |
| PURPOSE OF THE PROJECT | The project aimed to collect and or buy medical supplies to donate to the health center of Baguida (Centre Medico-Social de Baguida-CMS Baguida). Initially created to provide health services to less than 20 patients per day, the health center has seen an unexpected increase in demand for health services. Donating medical supplies to the health center of Baguida will not only increase patient outcome but also improve staff performance. | | |
| OBJECTIVES ACHIVED/NOT ACHIVED | On July 15, 2022, several medical supplies were donated to the CMS - Baguida. See attached list for medical supplies donated. | | |
| PLANNING & CONTROL | The project was planned, financed, and executed by UMA Board. The execution of the project was conducted by the local UMA team with the help of one board member who traveled from the US to oversee the execution.  Timeline:   * February 2, 2022: First draft approved. * May 20, 2022: Final draft approved for execution. * July 1, 2022: First meeting with the local team * July 5, 2022: Visit to the director of the medical center by the Board representative accompanied by the local team representative * July 11, 2022: authorization was granted by the stakeholders. * July 15, 2022, Execution of the project. The medical supplies were donated to the health center | | |
| ACCEPTANCE & SIGN-OFFS | The receiving party was thankful and expressed the need for additional medical supplies in the future. During his intervention, Mr. Yibokou, who represented the director revealed countless issues that the health center is currently facing to provide proper health services. The two parties signed a *donation agreement* and promised to keep working together for a better and well-equipped health center for the residents of Baguida. | | |
| LESSONS LEARNED | Early involvement of local stakeholders not only would have helped to save time but also to converge the energy for proper planning.  A better structure and more involvement of the UMA local team is also needed. | | |

A picture containing diagram

Description automatically generated



A picture containing table

Description automatically generated

