## Purchased lots (hidden)
Phase | Construction Task | Completion Time | Control measures initially Selected
Initial | Installation of initial Control measures for operator’s activities. | 3 Days | VTC - fabric & rock, permieter - control, Silt fence, enhanced curb cuts; inet protection or curb check controls - Rock sock weighted fabric sock; portable toilets.
| Clearing, grubbing and overlot grading for site balancing, street and lot locations |  | Previously completed by others
Over excavation for soils stabilization (if separate from above).
Interior curb, gutter, road and alley construction paving and initial sidewalks, parking lots.
| Site wide utilities for sewer, storm sewer, water, electrical & et.c | N/A
Interim (detached homes per lot) | Vertical Construction (from foundation through interior finish) | See Appendix B for lot specific schedule (Approximately 120 days per lot)
| Foundation Excavation | 3 – 5 days | Stock pile containment, if needed - Silt fence, berm or ditch, erosion control log.
| Form and Pour Foundation | 14 days | Concrete washout (if not previosuly installed) and cementious materials mangemetn practices
| Back Fill Foundation | 3 – 5 days | Temporary controls where equipment disturbs back of curb
| Frame and interior construction | 5 months | dumpsters and trsh maintainence practices
Interim (attached) | Vertical Construction (from foundation through interior finish)
| Foundation Excavation | 7 - 14 days | Stock pile containment, if needed - Silt fence, berm or ditch, erosion control log.
| Form and Pour Foundation | 21 days | Concrete washout (if not previosuly installed) and cementious materials mangemetn practices
| Back Fill Foundation | 5 – 7 days
| Frame and interior construction per unit | 5 months | dumpsters and trsh maintainence practices
Final | Final sidewalk & alley constuctions | This is responsibility of Developer
| Implementation of final stabilization | 14 days | Landscape material controls. See also final stabilization sections of SWMP
| Removal of Final Control measures . | 3 days | Removal of all control measures not intneded for permanent control.

## small lot(s) development (hidden)
Phase | Construction Task | Completion Time (est.) | Control Measures Initially Selected
Initial | Installation of initial Control measures for operator’s activities. | 3 Days | VTC -rubber & rock - perimeter control, silt fence and compacted berm. Straw wattle. Checkdams, - Rock sock - weighted fabric sock; portable toilets.
| Clearing, grubbing and overlot grading for site balancing, street and lot locations |  | Grade differentials or other control measures to maintain appropriate drainage area to controls ratio, wind erosion controls, additional tracking controls, Rough cut street controls, Temporary stabilization, stockpile containment Temporary sediment basins
| Over excavation for soils stabilization (if separate from above). |  | Rough cut street controls, Temporary stabilization, stockpile containment
| Dentention/ Retention basins and other permantent post construciton control features |  | temorary outlet protection from pipes, linear protection along completed channels, rip rap or other structrues down gradient from disturbed soils, outflow filtering at points of discharge
| Site wide utilities for sewer, storm sewer, water, electrical & etc. |  | Trench spoils placement
| Interior curb, gutter, road and alley construction paving and initial sidewalks, parking lots. |  | Concrete Washout, Protection for all new inlets, additional perimeter controls as curb/gutters and inlets are connected with paved surfaces
Interim (detached homes per lot) | Vertical Construction (from foundation through interior finish)
| Foundation Excavation |  | Stock pile containment, if needed - Silt fence, berm or ditch, erosion control log.
| Form and Pour Foundation |  | Concrete washout (if not previously installed) and Cementous materials management practices
| Back Fill Foundation | 3 – 5 days | Temporary controls where equipment disturbs back of curb
| Frame and interior construction | 5 months | dumpsters and trash maintenance practices,
Interim (attached, per unit) | Vertical Construction (from foundation through interior finish) | See Appendix B for lot specific schedule (Approximately 120 days per lot)
| Foundation Excavation | 7 - 14 days | Stock pile containment, if needed - Silt fence, berm or ditch, erosion control log.
| Form and Pour Foundation | 21 days | Concrete washout (if not previously installed) and cementious materials management practices
| Back Fill Foundation | 5 – 7 days
| Frame and interior construction per unit | 5 months | dumpsters and trash maintenance practices
Final | Final sidewalk & alley construction
| Implementation of final stabilization | 14 days | Landscape material controls. See also final stabilization sections of SWMP
| Removal of Final Control measures . | 3 days | Removal of all control measures not intended for permanent control.

## commercial development
Phase | Construction Task | Completion Time (est.) | Date Started | Control Measures Initially Selected for Specific Phase (Control Measures that continue from one to next phase are not repeated.)
Initial | Installation of initial Control measures for operator’s activities. | 3 Days | 11/7/2019 | VTC - rock - perimeter control, silt fence and compacted berm. Straw wattle. Curb Sock Check dams, - Rock sock - check dam and blocking off Juchem ditch ends. Silt fence, ans designed is not being installed a Ditch to be filled as part of initial grading.
| Clearing, grubbing and overlot grading for site balancing, street and lot locations | 14 days |  | Grade differentials or other control measures to maintain appropriate drainage area to controls ratio, wind erosion controls, additional tracking controls, Rough cut street controls, Temporary stabilization, stockpile containment, Temporary sediment basin. The initial disturbance will include areas west of Robb Street. this will include the filling of Juchem ditch.
| Over excavation for soils stabilization (if separate from above). | NA |  | Rough cut street controls, Temporary stabilization, stockpile containment, additional perimeter controls on eastern side.
| Detention/ Retention basins and other permanent post construction control features | 30 |  | temporary outlet protection from pipes, linear protection along completed channels, rip rap or other structures down gradient from disturbed soils, outflow filtering at points of discharge
| Site wide utilities for sewer, storm sewer, water, electrical & etc. | 90 |  | Trench spoils placement
| Interior curb, gutter, road and alley construction paving and initial sidewalks, parking lots. | 90 |  | Concrete Washout, Protection for all new inlets, additional perimeter controls as curb/gutters and inlets are connected with paved surfaces
Interim (detached homes per lot) | Vertical Construction (from foundation through interior finish)
| Foundation Excavation | 14 |  | Stock pile containment, if needed - Silt fence, berm or ditch, erosion control log.
| Form and Pour Foundation | 15 |  | Concrete washout (if not previously installed) and Cementous materials management practices
| Back Fill Foundation | 15 |  | Temporary controls where equipment disturbs back of curb
| Frame and interior construction | 120 |  | dumpsters and trash maintenance practices,
Final | Robb Street Improvements, parking, curb & gutter with Inlets | 90 |  | As soon as feasible after forms are removed, but no later than concurrent with the first lift of asphalt, inlet protection to be added. As forms removed and back fill performed curbs will be evaluated and back of curb controls added where potential flows transition for exposed soils over the curb.
| Implementation of final stabilization | 90 |  | Landscape material controls. See also final stabilization sections of SWMP
| Removal of Final Control measures . | 3 days |  | Removal of all control measures not intended for permanent control.