# Nehemiah Project

## Ministry Innovation Grant for Seminary Students and pastors

## Program Overview

Vision: Empower future ministry leaders to experiment with innovative approaches to sharing the Gospel and serving communities.

Grant Amount: $500 USD per recipient

Duration: 6 -12 months or, TBD

Number of Recipients:  TBD per cycle

## Eligibility

### Basic Requirements

- Currently enrolled at our Cooperative Program

- Completed at least one year of theological education

- Good academic standing

- Recommended by the Principal or Denominational Leader

### Ministry Requirements

- Proposed ministry should be innovative or experimental

- Clear Gospel focus

- Addresses a real community need

- Applicant must be the primary leader (team allowed)

- Feasible to implement and evaluate within 6 months

## What Qualifies as "Innovative"?

### Examples of Eligible Ministries:

Digital & Technology

- Faith-based apps or online platforms

- Podcasts/YouTube for specific audiences

- Online discipleship tools

Community Transformation

- Creative outreach to marginalized groups

- Community cafes/spaces with Gospel integration

- Environmental stewardship + faith

- Workplace ministry innovations

Cross-Cultural & Generational

- Gen-Z specific worship/fellowship models

- Cross-cultural bridge ministries

- Special needs faith formation

### Not Eligible:

- Replication of existing programs

- Minor tweaks to traditional ministry

- Social service without clear Gospel element

- Projects where applicant is not the primary leader

## Application Process

### Stage 1: Vision Sharing (Letter of Intent - 1,000 words)

Deadline: [Date]

Submit:

- Personal introduction & calling (300 words)

- Ministry concept (500 words)

- Why is this innovative? (200 words)

- Preliminary budget

### Full Proposal

### Required Sections:

- Vision & Mission    What change do you want to see?

- Needs Assessment

  - Who are you serving?

  - What are their needs?

  - What's the current gap?

  - How do you know? (research/interviews)

- Ministry Strategy

  - What will you do?

  - How will you do it?

  - 6-month timeline

  - Required resources

  - Potential partners

- Innovation Element

  - What makes this different?

  - Why might this be more effective?

- Impact Evaluation

  - How will you measure success?

  - Expected reach

  - Feedback collection methods

- Sustainability      How will this continue after 6 months?

  - Is it replicable by you or someone else?

  - Future funding sources?

- Detailed Budget (1 page)

## Selection Criteria (100 points total)

| Criteria | Points | Focus |
| --- | --- | --- |
| Innovation | 25 | Truly creative? Unique insight? |
| Need | 20 | Addresses real need? Well-researched? |
| Feasibility | 20 | Achievable in 6 months? Realistic? |
| Impact | 15 | Expected reach and depth? |
| Spiritual Depth | 10 | Gospel-centered? Theological foundation? |
| Capacity | 10 | Applicant capable? Past experience? |

## 6-Month Implementation Timeline

### Month 1: Launch Phase

Tasks:

- Attend an online one-hour kickoff workshop hosted by Dr. Jeff Lee

- Finalize detailed plan

- Build team (if needed)

- Acquire resources

Deliverable: Revised execution plan

### Months 2-3: Pilot Phase

Tasks:

- Begin ministry execution

- Small-scale testing

- Collect initial feedback

- Adjust strategy

Deliverables:

- Monthly progress reports

- First mentor meeting (if applicable)

### Months 4-5: Expansion Phase

Tasks:

- Full implementation

- Ongoing evaluation

- Document stories/testimonies

Deliverables:

- Mid-term report (end of Month 3)

- Video/photo documentation

- Second mentor meeting (if applicable)

### Month 6: Conclusion Phase

Tasks:

- Complete ministry goals

- Comprehensive evaluation

- Write final report

- Plan future direction

- Prepare presentation

Deliverables:

- Final report

- Financial report

- Final video presentation

## Support Structure

### Mentorship

We strongly encourage each recipient to be paired with an experienced ministry mentor for:

- Guidance and encouragement

- Accountability and support

### Accountability Requirements

WhatsApp Group Communication:

- All participants join a WhatsApp group with donors

- Share monthly progress updates

Video Documentation (5 minutes each):

- Introduction Video (Month 1)

  - Introduce yourself and your team

  - Show the people and place of your project

  - Share your vision

- Mid-Point Video (Month 3)

  - Progress update

  - Challenges and adjustments

  - Initial testimonies

Final Video (Month 6)

- Must include:

  - Executive summary of the project

  - Ministry review

  - Results evaluation (quantitative & qualitative)

  - Spiritual reflections

  - Lessons learned & recommendations

  - Future outlook

  - Financial summary

## Financial Management

### Disbursement

- 50% upon approval

- 30% after mid-term report approval

- 20% after final report approval

### Allowed Expenses

✓ Ministry activity costs

✓ Necessary equipment/materials

✓ Venue rental

✓ Marketing & promotion

✓ Transportation

✓ Reasonable meals (ministry-related)

### Not Allowed

✗ Personal living expenses, self-compensation, or tuition

✗ Luxury items

✗ Non-ministry related expenses

✗ Personal gifts

### Requirements

- Keep all receipts

- Submit final expense report

- Return unused funds or redirect/expand with approval

## FAQ

Q: Can I apply with other students?

A: Yes, but designate one primary leader who receives and manages the grant.

Q: What if my ministry "fails"?

A: We encourage risk-taking. Failure is part of learning. Honest documentation and reflection = success.

Q: Can I use funds for salary?

A: No. This is for ministry, not personal support. But reasonable ministry-related expenses are allowed.

Q: My ministry needs more than 6 months to show results. Can I still apply?

A: Yes, but explain achievable 6-month milestones and how you'll evaluate initial impact.

Q: Do I need church support?

A: Yes. Principal's recommendation is required. Ministry should connect to your church context (but doesn't have to happen inside the church building).

## Contact Information

Program Director: Principal

Email: [email]

Phone: [phone]

## Closing Statement

We look forward to seeing how God will use your creativity and courage to do new things in this generation.

"See, I am doing a new thing! Now it springs up; do you not perceive it? I am making a way in the wilderness and streams in the wasteland."

— Isaiah 43:19

May God bless your ministry!

Application Opens: [Date]

Apply Now: [Application Link/Email]

# 6-Month Implementation Timeline

```

┌─────────────────────────────────────────────────────────────────────────────┐

│                         NEHEMIAH PROJECT TIMELINE                            │

└─────────────────────────────────────────────────────────────────────────────┘

MONTH 1                    MONTHS 2-3                MONTHS 4-5              MONTH 6

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

🚀 LAUNCH PHASE          🧪 PILOT PHASE          📈 EXPANSION PHASE      🎯 CONCLUSION PHASE

┌─────────────┐         ┌─────────────┐         ┌─────────────┐        ┌─────────────┐

│   PREPARE   │────────▶│    TEST     │────────▶│    GROW     │───────▶│  COMPLETE   │

└─────────────┘         └─────────────┘         └─────────────┘        └─────────────┘

TASKS:                   TASKS:                   TASKS:                 TASKS:

• Attend 1-hour         • Begin ministry         • Full                 • Complete all

online kickoff          execution                implementation         ministry goals

workshop

(Dr. Jeff Lee)        • Small-scale            • Ongoing              • Comprehensive

testing                  evaluation             evaluation

• Finalize

detailed plan         • Collect initial        • Document             • Write final

feedback                 stories &              report

• Build team                                       testimonies

(if needed)           • Adjust strategy                               • Plan future

direction

• Acquire

resources                                                             • Prepare

presentation

─────────────────────────────────────────────────────────────────────────────

DELIVERABLES:            DELIVERABLES:            DELIVERABLES:          DELIVERABLES:

📋 Revised              📊 Monthly progress      📹 Mid-term report     📄 Final report

execution plan          reports                  (end of Month 3)

💰 Financial

🎥 Introduction         🤝 First mentor          🎥 Video/photo            report

video                   meeting                  documentation

(5 min)                 (if applicable)                             🎬 Final video

🤝 Second mentor          presentation

meeting                (5 min)

🎥 Mid-point video          (if applicable)

(5 min)

─────────────────────────────────────────────────────────────────────────────

FUNDING:

💵 50% Released         ─────────────────────▶   💵 30% Released       💵 20% Released

(Upon approval)                                  (After mid-term)      (After final

report approval)       report)

─────────────────────────────────────────────────────────────────────────────

MILESTONES:

✓                        ✓                        ✓                    ✓

Project Start          Pilot Launch            Full Scale           Project Complete

│                        │                        │                    │

└────────────────────────┴────────────────────────┴────────────────────┘

6 MONTHS

```

---

## Quick Reference Guide

| **Phase** | **Duration** | **Focus** | **Key Deliverable** |

|-----------|-------------|-----------|---------------------|

| 🚀 **Launch** | Month 1 | Preparation | Execution plan + Intro video |

| 🧪 **Pilot** | Months 2-3 | Testing | Monthly reports + Mid-point video |

| 📈 **Expansion** | Months 4-5 | Growth | Mid-term report + Documentation |

| 🎯 **Conclusion** | Month 6 | Completion | Final report + Final video |

---

Video Documentation Schedule

```

Month 1          Month 3          Month 6

│                │                │

▼                ▼                ▼

🎥 Intro         🎥 Mid-Point    🎥 Final

(5 min)          (5 min)         (5 min)

```

┌─────────────────────────────────────────────────────────────────────────────┐

│                         NEHEMIAH PROJECT TIMELINE                            │

└─────────────────────────────────────────────────────────────────────────────┘

MONTH 1                    MONTHS 2-3                MONTHS 4-5              MONTH 6

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

🚀 LAUNCH PHASE          🧪 PILOT PHASE          📈 EXPANSION PHASE      🎯 CONCLUSION PHASE

┌─────────────┐         ┌─────────────┐         ┌─────────────┐        ┌─────────────┐

│   PREPARE   │────────▶│    TEST     │────────▶│    GROW     │───────▶│  COMPLETE   │

└─────────────┘         └─────────────┘         └─────────────┘        └─────────────┘

TASKS:                   TASKS:                   TASKS:                 TASKS:

• Attend 1-hour         • Begin ministry         • Full                 • Complete all

online kickoff          execution                implementation         ministry goals

workshop

(Dr. Jeff Lee)        • Small-scale            • Ongoing              • Comprehensive

testing                  evaluation             evaluation

• Finalize

detailed plan         • Collect initial        • Document             • Write final

feedback                 stories &              report

• Build team                                       testimonies

(if needed)           • Adjust strategy                               • Plan future

direction

• Acquire

resources                                                             • Prepare

presentation

────────────────────────────────────────────────────────────

DELIVERABLES:            DELIVERABLES:            DELIVERABLES:          DELIVERABLES:

📋 Revised              📊 Monthly progress      📹 Mid-term report     📄 Final report

execution plan          reports                  (end of Month 3)

💰 Financial

🎥 Introduction         🤝 First mentor          🎥 Video/photo            report

video                   meeting                  documentation

(5 min)                 (if applicable)                             🎬 Final video

🤝 Second mentor          presentation

meeting                (5 min)

🎥 Mid-point video          (if applicable)

(5 min)

────────────────────────────────────────────────────────────

FUNDING:

💵 50% Released         ─────────────────────▶   💵 30% Released       💵 20% Released

(Upon approval)                                  (After mid-term)      (After final

report approval)       report)

────────────────────────────────────────────────────────────

MILESTONES:

✓                        ✓                        ✓                    ✓

Project Start          Pilot Launch            Full Scale           Project Complete

│                        │                        │                    │

└────────────────────────┴────────────────────────┴────────────────────┘

6 MONTHS