## Sheet1
SCI Post Tension Cable Repairs
As of 12/8/2025
Change | P/T Cable Repair type & associates repairs | # cables | Total
Order |  | Repaired | Amount
CO#6 | 2 broken cables & 1 lock-off repair | 3 | 19140
CO#7 | Stack 01 - total 11 lock-off repairs | 11 | 12540
CO#8 | Post tension sheathing repairs |  | 3827.69
CO#9 | Rental of 86' lift to carry out P/T repairs on #01 stack |  | 4936.98
CO#10 | Broken P/T cable in #506 closet. Re-do conduit with Media cables | 1 | 21955
CO#11 | 10 P/T cable lock-off repairs | 10 | 11400
CO#12 | Lift rental 1 week to repair 19 P/T lock-offs | 19 | 26596
CO#26 | P/T repairs 11 lock-off & 1 cable stress | 20 | 14100
Phase 3 Projection
46740
| 41 P/T lock-off repairs | 41 | 10000
Contingency
Totals |  | 105 | 171235.67
NOTES:
Post Tension Cable repairs to date have cost $171,235.67 dollars.
No amount was budgeted by the contractor for P/T cable repairs in the original estimate.
Thus far, a total of 105 cables have been repaired with some being replaced
Additional material associated with P/T cable repairs is estimated at about $75,000.00