Kitchen Timeline

Congratulations!

As a Kitchen Head you will have months to plan.  This guide will provide you with a time table to help you along.  As head you are to teach your assistants how to be future Kitchen Heads.  Remember to pray before the start of each meeting.

Months before      # of Meeting

the weekend       with Assistants		Task

5-6		1			With your assistants come up with a menu of what you would like to serve on the weekend.  Plan for the 						following;

Thursday  –  Team Dinner and Snacks for Candidates

(Meatless) Friday  -  Breakfast, Lunch and Dinner

Saturday  -  Breakfast, Lunch- Agape Meal (Ask Rector/a for preference), buffet style Dinner

Sunday  -  Continental Breakfast, Brunch, Conf. Room Sandwiches

Example of “Weekend Menu” in Resource folder on CD - Excel file

Find all the recipes and start putting your Kitchen binder together.  See example of “Weekend Recipes” 	in Head 	Binder on CD – Word Doc.

There are a number of recipes in the “Recipes” Folder on CD.  Choose to your liking.

4		2			You should have all the recipes by now.

Split up recipes with assistants and figure out how much ingredient is needed (per recipe) to serve

(75) people.  Make List. See “Shopping List Spreadsheet” in the Resource folder on CD.

Figure out what & how many utensils and pots or pans are needed for each recipe.  Make List.  See 	“Shopping List Spreadsheet” in the Resource folder on CD.

Decide on Agape Decoration (No De Colores) and purchase prior to the weekend. Simple is BEST, remember it is a 					spiritual event.

Months before      # of Meeting

the weekend       with Assistants		Task

3		3			Go over all list/recipes and make any corrections necessary.

Prepare for Team Meetings.  (Print out the following located in the Team Meeting Forms folder on CD)

“Food Donation Form” – Modify form to what you need.

“Kitchen Workers Handout”- All kitchen workers must receive a copy.

“Sign Up Sheet”- Pass around to get accurate # of servings on meals.

Send out email to Core Team to bring a dish to the first team meeting.

Kitchen head and Assts. will supply utensils, plates, cups, napkins, & drinks to all meetings.  And assign certain 						area to bring dish for next meeting.

2		4			Go over all list/recipes and make any corrections necessary.

Work on Kitchen Schedule- Ask Rector/a for the main schedule and  make sure times are in sync. Fill in when to 	prepare what recipes or any special notes for your weekend.

Start choosing Kitchen Moms/Captains and arrange your teams.

Work on recipes for any special diets.

Ask Liaison for information on candidates with special diets.

Ask Treasurer for Check and Sam’s Club Card.

Check list of supplies available from previous Cursillo inventory and Inspect kitchen at site for adequate 	equipment and proper use.

Months before      # of Meeting

the weekend       with Assistants		Task

1		5			Go over all list/recipes and make any corrections necessary.

Go over weekend schedule with Moms/Captains/ kitchen teams.

Give Kitchen Moms/Captains their kitchen folder/binder.

Begin purchasing non perishable items after taking inventory at St. Mary’s.

Arrange for transportation of food to site.

Week of 				Head out to purchase items.  Have assistants help where needed.

Weekend

Purchase dairy products and fresh fruit and veggies on Thursday just before the weekend.

Finalize team list and schedule.

Assign one of your assistants to make copies of schedule at St. Marys and distribute to team members.

During the weekend let the team Mom’s/ Captain’s take over as long as they are following the recipes and schedules.  You are only there supervise, guide and to answer any questions.  Of course- always be available to help out- if the need arises.  It may work best if you assign yourself and your assistants to one team to answer any questions or issues that may arise.

You’ll have plenty of time to do everything if you start, and get your assistants involved early on.  The hardest job of the kitchen head should be the planning before the weekend.

May God bless you with inspiration and peace.