## Sheet4
Count of Ouput | Column Labels
Row Labels | Acquire Resources | Close Project or Phase | Collect Requirements | Conduct Procurements | Control Costs | Control Procurements | Control Quality | Control Resources | Control Schedule | Control Scope | Create WBS | Define Activities | Define Scope | Determine Budget | Develop Project Charter | Develop Project Management Plan | Develop Schedule | Develop Team | Direct and Manage Project Work | Estimate Activity Durations | Estimate Activity Resources | Estimate Costs | Identify Risks | Identify Stakeholders | Implement Risk Responses | Manage Communications | Manage Project Knowledge | Manage Quality | Manage Stakeholder Engagement | Manage Team | Monitor and Control Project Work | Monitor Communications | Monitor Risks | Monitor Stakeholder Engagement | Perform Integrated Change Control | Perform Qualitative Risk Analysis | Perform Quantitative Risk Analysis | Plan Communications Management | Plan Cost Management | Plan Procurement Management | Plan Quality Management | Plan Resource Management | Plan Risk Management | Plan Risk Responses | Plan Schedule Management | Plan Scope Management | Plan Stakeholder Engagement | Sequence Activities | Validate Scope | Grand Total
Accepted Deliverables |  | 1 | [47 empty] | 1
Close |  | 1 | [47 empty] | 1
Activity Attributes | [16 empty] | 1 |  |  | 1 | 1 | [26 empty] | 1 |  | 4
Plan | [16 empty] | 1 |  |  | 1 | 1 | [26 empty] | 1 |  | 4
Activity List | [16 empty] | 1 |  |  | 1 | [27 empty] | 1 |  | 3
Plan | [16 empty] | 1 |  |  | 1 | [27 empty] | 1 |  | 3
Activity Lists | [20 empty] | 1 | [28 empty] | 1
Plan | [20 empty] | 1 | [28 empty] | 1
Agreements |  | 1 | 1 |  |  |  |  | 1 | [5 empty] | 1 | 1 |  | 1 | [5 empty] | 1 | [7 empty] | 1 | [18 empty] | 8
Close |  | 1 | [47 empty] | 1
Initiate | [14 empty] | 1 | [34 empty] | 1
Monitor/Control | [7 empty] | 1 | [22 empty] | 1 | [18 empty] | 2
Plan |  |  | 1 | [10 empty] | 1 |  |  | 1 | [5 empty] | 1 | [26 empty] | 4
All Components | [42 empty] | 1 | [6 empty] | 1
Plan | [42 empty] | 1 | [6 empty] | 1
Approved Change Request | [6 empty] | 1 | [11 empty] | 1 | [30 empty] | 2
Execute | [18 empty] | 1 | [30 empty] | 1
Monitor/Control | [6 empty] | 1 | [42 empty] | 1
Assumptions Log |  |  | 1 | [9 empty] | 1 |  |  |  | 1 |  |  | 1 | 1 |  | 1 | [12 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 |  | 9
Monitor/Control
Plan |  |  | 1 | [9 empty] | 1 |  |  |  | 1 |  |  | 1 | 1 |  | 1 | [12 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 |  | 9
Basis of Estimates | [13 empty] | 1 |  |  | 1 | [17 empty] | 1 | [14 empty] | 3
Monitor/Control | [34 empty] | 1 | [14 empty] | 1
Plan | [13 empty] | 1 |  |  | 1 | [32 empty] | 2
Benefits Management Plan | [13 empty] | 1 | 1 | [34 empty] | 2
Initiate | [14 empty] | 1 | [34 empty] | 1
Plan | [13 empty] | 1 | [35 empty] | 1
Business Case |  |  | 1 | [10 empty] | 1 | 1 | [34 empty] | 3
Initiate | [14 empty] | 1 | [34 empty] | 1
Plan |  |  | 1 | [10 empty] | 1 | [35 empty] | 2
Business documents |  | 1 | 1 | [11 empty] | 1 | [34 empty] | 3
Close |  | 1 | [47 empty] | 1
Initiate | [14 empty] | 1 | [34 empty] | 1
Plan |  |  | 1 | [46 empty] | 1
Change Log | [18 empty] | 1 | [6 empty] | 1 | [23 empty] | 2
Execute | [18 empty] | 1 | [6 empty] | 1 | [23 empty] | 2
Initiate
Plan
Change Management Plan | [9 empty] | 1 | [24 empty] | 1 | [14 empty] | 2
Monitor/Control | [9 empty] | 1 | [24 empty] | 1 | [14 empty] | 2
Change Requests | [34 empty] | 1 | [14 empty] | 1
Monitor/Control | [34 empty] | 1 | [14 empty] | 1
Communications Management Plan | [25 empty] | 1 | [23 empty] | 1
Execute | [25 empty] | 1 | [23 empty] | 1
Initiate
Monitor/Control
Plan
Configuration Management Plan | [9 empty] | 1 | [24 empty] | 1 | [14 empty] | 2
Execute
Monitor/Control | [9 empty] | 1 | [24 empty] | 1 | [14 empty] | 2
Cost Baseline | 1 |  |  |  | 1 | [17 empty] | 1 | [11 empty] | 1 | [14 empty] | 4
Execute | 1 | [48 empty] | 1
Monitor/Control |  |  |  |  | 1 | [29 empty] | 1 | [14 empty] | 2
Plan | [22 empty] | 1 | [26 empty] | 1
Cost Estimates | [13 empty] | 1 | [6 empty] | 1 |  | 1 | [26 empty] | 3
Plan | [13 empty] | 1 | [6 empty] | 1 |  | 1 | [26 empty] | 3
Cost Forecasts
Plan
Cost Management Plan |  |  |  |  | 1 | [8 empty] | 1 | [7 empty] | 1 | 1 | [26 empty] | 4
Monitor/Control |  |  |  |  | 1 | [44 empty] | 1
Plan | [13 empty] | 1 | [7 empty] | 1 | 1 | [26 empty] | 3
Deliverables | [6 empty] | 1 | [19 empty] | 1 | [22 empty] | 2
Execute | [26 empty] | 1 | [22 empty] | 1
Monitor/Control | [6 empty] | 1 | [42 empty] | 1
Dev Approach | [44 empty] | 1 | 1 |  |  |  | 2
Plan | [44 empty] | 1 | 1 |  |  |  | 2
Duration Estimates | [22 empty] | 1 | [26 empty] | 1
Plan | [22 empty] | 1 | [26 empty] | 1
EEF | 1 |  | 1 |  |  |  | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 |  | 1 |  | 30
Execute | 1 | [16 empty] | 1 | 1 | [6 empty] | 1 | 1 |  |  | 1 | [19 empty] | 6
Initiate | [14 empty] | 1 | [34 empty] | 1
Monitor/Control | [6 empty] | 1 | [23 empty] | 1 | 1 |  |  | 1 | [14 empty] | 4
Plan |  |  | 1 | [7 empty] | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | [12 empty] | 1 |  | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 |  | 1 |  | 19
EEF | [40 empty] | 1 | [8 empty] | 1
Plan | [40 empty] | 1 | [8 empty] | 1
Issue Log | [7 empty] | 1 | [14 empty] | 1 |  |  | 1 |  |  |  | 1 | [19 empty] | 4
Execute | [25 empty] | 1 |  |  |  | 1 | [19 empty] | 2
Initiate
Monitor/Control | [7 empty] | 1 | [41 empty] | 1
Plan | [22 empty] | 1 | [26 empty] | 1
Lessons Learned Register |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | [6 empty] | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 | [18 empty] | 1 | 17
Execute | [17 empty] | 1 | 1 | [6 empty] | 1 | 1 | 1 |  | 1 | [19 empty] | 6
Monitor/Control |  |  |  |  | 1 |  | 1 | 1 | 1 | 1 | [38 empty] | 1 | 6
Plan |  |  | 1 | [13 empty] | 1 |  |  | 1 |  | 1 | 1 | [26 empty] | 5
Milestone List | [16 empty] | 1 |  |  | 1 | [27 empty] | 1 |  | 3
Monitor/Control
Plan | [16 empty] | 1 |  |  | 1 | [27 empty] | 1 |  | 3
OPA | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 |  | 1 |  | 35
Close |  | 1 | [47 empty] | 1
Execute | 1 | [17 empty] | 1 | [6 empty] | 1 | 1 | 1 |  | 1 | [19 empty] | 6
Initiate | [14 empty] | 1 | [34 empty] | 1
Monitor/Control |  |  |  |  | 1 |  | 1 | 1 | 1 | 1 | [20 empty] | 1 | 1 |  |  | 1 | [14 empty] | 8
Plan |  |  | 1 | [7 empty] | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | [12 empty] | 1 |  | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 |  | 1 |  | 19
OPS | [17 empty] | 1 | [24 empty] | 1 | [6 empty] | 2
Execute | [17 empty] | 1 | [31 empty] | 1
Plan | [42 empty] | 1 | [6 empty] | 1
Outputs from Other Processes | [15 empty] | 1 | [33 empty] | 1
Plan | [15 empty] | 1 | [33 empty] | 1
Performance Measurement Baseline |  |  |  |  | 1 |  |  |  | 1 | 1 | [39 empty] | 3
Monitor/Control |  |  |  |  | 1 |  |  |  | 1 | 1 | [39 empty] | 3
Physical Resource Assignments | [7 empty] | 1 | [41 empty] | 1
Monitor/Control | [7 empty] | 1 | [41 empty] | 1
Procurement Documentation |  | 1 | [20 empty] | 1 | [26 empty] | 2
Close |  | 1 | [47 empty] | 1
Plan | [22 empty] | 1 | [26 empty] | 1
Procurement Documentationumentation
Execute
Monitor/Control
Procurement Management Plan | 1 | [48 empty] | 1
Execute | 1 | [48 empty] | 1
Monitor/Control
Proj LC Description | [45 empty] | 1 |  |  |  | 1
Plan | [45 empty] | 1 |  |  |  | 1
Project Calendars | [8 empty] | 1 | [40 empty] | 1
Monitor/Control | [8 empty] | 1 | [40 empty] | 1
Project Charter |  | 1 | 1 | [9 empty] | 1 |  |  | 1 | [21 empty] | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 |  |  |  | 11
Close |  | 1 | [47 empty] | 1
Initiate
Plan |  |  | 1 | [9 empty] | 1 |  |  | 1 | [21 empty] | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 |  |  |  | 10
Project Communications
Monitor/Control
Project Documents |  | 1 | 1 | [6 empty] | 1 | 1 |  | 1 | [5 empty] | 1 | 1 |  |  | 1 |  |  | 1 | 1 |  |  |  | 1 | 1 |  |  | 1 | 1 |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 | 1 | 18
Close |  | 1 | [47 empty] | 1
Execute | [18 empty] | 1 | [6 empty] | 1 | 1 | [22 empty] | 3
Initiate
Monitor/Control | [9 empty] | 1 | [20 empty] | 1 | 1 |  |  | 1 | [13 empty] | 1 | 5
Plan |  |  | 1 | [7 empty] | 1 |  | 1 | [6 empty] | 1 |  |  | 1 | [12 empty] | 1 |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  | 9
Project Funding Requirements |  |  |  |  | 1 | [44 empty] | 1
Monitor/Control |  |  |  |  | 1 | [44 empty] | 1
Project Management Plan |  | 1 | 1 | [6 empty] | 1 | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  | 1 |  |  | 1 | 1 |  |  |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 22
Close |  | 1 | [47 empty] | 1
Execute | [18 empty] | 1 | [6 empty] | 1 | 1 | [22 empty] | 3
Initiate
Monitor/Control | [9 empty] | 1 | [20 empty] | 1 | 1 |  |  | 1 | [13 empty] | 1 | 5
Plan |  |  | 1 | [7 empty] | 1 | 1 | 1 | [6 empty] | 1 |  |  | 1 | [12 empty] | 1 | 1 | 1 |  |  |  |  | 1 |  | 1 | 1 |  | 1 |  | 13
Project Schedule | 1 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 1 | [19 empty] | 1 | [7 empty] | 6
Execute | 1 | [16 empty] | 1 | [31 empty] | 2
Monitor/Control | [7 empty] | 1 | [41 empty] | 1
Plan | [13 empty] | 1 | [7 empty] | 1 | [19 empty] | 1 | [7 empty] | 3
Project Schedule | [8 empty] | 1 | [40 empty] | 1
Monitor/Control | [8 empty] | 1 | [40 empty] | 1
Project Schedule Network Diagram | [16 empty] | 1 | [32 empty] | 1
Plan | [16 empty] | 1 | [32 empty] | 1
Project Scope Statements | [10 empty] | 1 | [38 empty] | 1
Plan | [10 empty] | 1 | [38 empty] | 1
Project Team Assignments | [16 empty] | 1 | 1 |  | 1 | [9 empty] | 1 | [19 empty] | 4
Execute | [17 empty] | 1 | [11 empty] | 1 | [19 empty] | 2
Plan | [16 empty] | 1 |  |  | 1 | [29 empty] | 2
Quality Control Measurements | [27 empty] | 1 | [21 empty] | 1
Execute | [27 empty] | 1 | [21 empty] | 1
Quality Management Plan | [6 empty] | 1 | [14 empty] | 1 | 1 |  |  |  |  | 1 | [13 empty] | 1 |  |  |  | 1 |  |  |  | 6
Execute | [27 empty] | 1 | [21 empty] | 1
Monitor/Control | [6 empty] | 1 | [42 empty] | 1
Plan | [21 empty] | 1 | 1 | [18 empty] | 1 |  |  |  | 1 |  |  |  | 4
Quality Metrics | [6 empty] | 1 | [20 empty] | 1 | [21 empty] | 2
Execute | [27 empty] | 1 | [21 empty] | 1
Monitor/Control | [6 empty] | 1 | [42 empty] | 1
Quality Report | [25 empty] | 1 | [23 empty] | 1
Execute | [25 empty] | 1 | [23 empty] | 1
Quality Reports | [30 empty] | 1 | [17 empty] | 1 | 2
Monitor/Control | [30 empty] | 1 | [17 empty] | 1 | 2
Req Documents | [12 empty] | 1 | [36 empty] | 1
Plan | [12 empty] | 1 | [36 empty] | 1
Requirements Documentation | [9 empty] | 1 | 1 | [11 empty] | 1 | [14 empty] | 1 |  |  | 1 | 1 | [6 empty] | 1 | 7
Execute
Initiate
Monitor/Control | [9 empty] | 1 | [38 empty] | 1 | 2
Plan | [10 empty] | 1 | [11 empty] | 1 | [14 empty] | 1 |  |  | 1 | 1 | [7 empty] | 5
Requirements Management Plan |  |  | 1 | [6 empty] | 1 | [12 empty] | 1 | [17 empty] | 1 | [7 empty] | 1 | 5
Execute
Monitor/Control | [9 empty] | 1 | [38 empty] | 1 | 2
Plan |  |  | 1 | [19 empty] | 1 | [17 empty] | 1 | [8 empty] | 3
Requirements Traceability Matrix | [9 empty] | 1 | [30 empty] | 1 | [7 empty] | 1 | 3
Monitor/Control | [9 empty] | 1 | [38 empty] | 1 | 2
Plan | [40 empty] | 1 | [8 empty] | 1
Resource Breakdown Structure | [7 empty] | 1 | [11 empty] | 1 | [29 empty] | 2
Monitor/Control | [7 empty] | 1 | [41 empty] | 1
Plan | [19 empty] | 1 | [29 empty] | 1
Resource Calendars | 1 | [7 empty] | 1 | [7 empty] | 1 | 1 |  | 1 | 1 | [28 empty] | 6
Execute | 1 | [16 empty] | 1 | [31 empty] | 2
Monitor/Control | [8 empty] | 1 | [40 empty] | 1
Plan | [16 empty] | 1 |  |  | 1 | 1 | [28 empty] | 3
Resource Management Plan | 1 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 | [7 empty] | 1 | [11 empty] | 9
Execute | 1 | [16 empty] | 1 | [7 empty] | 1 |  |  |  | 1 | [19 empty] | 4
Monitor/Control | [7 empty] | 1 | [41 empty] | 1
Plan | [13 empty] | 1 | [6 empty] | 1 |  | 1 | [14 empty] | 1 | [11 empty] | 4
Resource Requirements | 1 | [6 empty] | 1 | [8 empty] | 1 |  |  | 1 |  | 1 | 1 | [26 empty] | 6
Execute | 1 | [48 empty] | 1
Monitor/Control | [7 empty] | 1 | [41 empty] | 1
Plan | [16 empty] | 1 |  |  | 1 |  | 1 | 1 | [26 empty] | 4
Risk Management Plan | [22 empty] | 1 | [12 empty] | 1 | 1 |  | 1 |  | 1 | [8 empty] | 5
Execute
Monitor/Control
Plan | [22 empty] | 1 | [12 empty] | 1 | 1 |  | 1 |  | 1 | [8 empty] | 5
Risk Register | [7 empty] | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 | [13 empty] | 1 |  |  |  |  | 1 | 1 | [7 empty] | 10
Execute
Monitor/Control | [7 empty] | 1 | [41 empty] | 1
Plan | [12 empty] | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 | [13 empty] | 1 |  |  |  |  | 1 | 1 | [7 empty] | 9
Risk Report | [25 empty] | 1 |  | 1 |  |  | 1 | [18 empty] | 3
Execute | [25 empty] | 1 |  | 1 | [21 empty] | 2
Monitor/Control | [30 empty] | 1 | [18 empty] | 1
Plan
Schedule Baseline | [8 empty] | 1 | [27 empty] | 1 | [12 empty] | 2
Monitor/Control | [8 empty] | 1 | [40 empty] | 1
Plan | [36 empty] | 1 | [12 empty] | 1
Schedule Data | [8 empty] | 1 | [40 empty] | 1
Monitor/Control | [8 empty] | 1 | [40 empty] | 1
Schedule Forecasts
Plan
Schedule Management Plan | [8 empty] | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 1 |  |  | 1 | [15 empty] | 1 | [8 empty] | 1 |  | 7
Monitor/Control | [8 empty] | 1 | [40 empty] | 1
Plan | [11 empty] | 1 |  |  |  |  | 1 |  |  | 1 |  |  | 1 | [15 empty] | 1 | [8 empty] | 1 |  | 6
Scope Baseline | [8 empty] | 1 | 1 |  | 1 |  | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | [11 empty] | 1 |  | 1 |  |  |  | 1 | 1 | [5 empty] | 1 | 1 | 15
Monitor/Control | [8 empty] | 1 | 1 | [24 empty] | 1 | [13 empty] | 1 | 4
Plan | [11 empty] | 1 |  | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | [13 empty] | 1 |  |  |  | 1 | 1 | [5 empty] | 1 |  | 11
Scope Management Plan |  |  | 1 | [6 empty] | 1 | 1 |  | 1 | [31 empty] | 1 |  |  |  | 1 | 6
Execute
Monitor/Control | [9 empty] | 1 | [38 empty] | 1 | 2
Plan |  |  | 1 | [7 empty] | 1 |  | 1 | [31 empty] | 1 |  |  |  |  | 4
Seller Proposals
Execute
Stakeholder Engagement Plan |  |  | 1 | [22 empty] | 1 | [14 empty] | 1 | [8 empty] | 3
Execute | [25 empty] | 1 | [23 empty] | 1
Initiate
Monitor/Control
Plan |  |  | 1 | [37 empty] | 1 | [8 empty] | 2
Stakeholder Management Plan | [37 empty] | 1 | [11 empty] | 1
Plan | [37 empty] | 1 | [11 empty] | 1
Stakeholder Register | 1 |  | 1 | [19 empty] | 1 |  |  | 1 | [9 empty] | 1 |  | 1 |  |  | 1 | 1 | 1 | [6 empty] | 9
Execute | 1 | [24 empty] | 1 | [23 empty] | 2
Monitor/Control
Plan |  |  | 1 | [19 empty] | 1 | [12 empty] | 1 |  | 1 |  |  | 1 | 1 | 1 | [6 empty] | 7
Team Charter | [17 empty] | 1 | [11 empty] | 1 | [19 empty] | 2
Execute | [17 empty] | 1 | [11 empty] | 1 | [19 empty] | 2
Team Performance Assessments | [29 empty] | 1 | [19 empty] | 1
Execute | [29 empty] | 1 | [19 empty] | 1
Test and Eval Documents | [6 empty] | 1 | [42 empty] | 1
Monitor/Control | [6 empty] | 1 | [42 empty] | 1
Verified Deliverables | [48 empty] | 1 | 1
Monitor/Control | [48 empty] | 1 | 1
Work Perf Info | [30 empty] | 1 | [18 empty] | 1
Monitor/Control | [30 empty] | 1 | [18 empty] | 1
Work Perf Reports | [34 empty] | 1 | [14 empty] | 1
Monitor/Control | [34 empty] | 1 | [14 empty] | 1
Work Performance Data |  |  |  |  | 1 |  | 1 | 1 | 1 | 1 | [21 empty] | 1 | [16 empty] | 1 | 7
Monitor/Control |  |  |  |  | 1 |  | 1 | 1 | 1 | 1 | [21 empty] | 1 | [16 empty] | 1 | 7
Work Performance Reports | [25 empty] | 1 |  |  |  | 1 | [19 empty] | 2
Execute | [25 empty] | 1 |  |  |  | 1 | [19 empty] | 2
Monitor/Control
Grand Total | 9 | 8 | 14 |  | 7 |  | 9 | 11 | 11 | 13 | 7 | 5 | 9 | 12 | 6 | 4 | 16 | 8 | 7 | 16 | 10 | 9 | 22 |  |  | 14 | 6 | 6 |  | 9 | 8 | 5 |  |  | 11 | 8 | 4 | 9 | 5 |  | 12 | 9 | 7 |  | 6 | 7 |  | 10 | 11 | 360

## Sheet1
Input | Process | Input Project Stage | Ouput | Output Process | Output Project Stage | Tools and Techniques | Tools Process | TT Project Stage
Business documents | Develop Project Charter | Initiate | Proj Charter | Develop Project Charter | Initiate | Expert Judgement | Develop Project Charter | Initiate
Business Case | Develop Project Charter | Initiate | Assumptions Log | Develop Project Charter | Initiate | Data Gathering | Develop Project Charter | Initiate
Benefits Management Plan | Develop Project Charter | Initiate | Project Management Plan | Develop Project Management Plan | Plan | Interpersonal and Team Skills | Develop Project Charter | Initiate
Agreements | Develop Project Charter | Initiate | Deliverables | Direct and Manage Project Work | Execute | Meetings | Develop Project Charter | Initiate
EEF | Develop Project Charter | Initiate | Work Perf Data | Direct and Manage Project Work | Execute | Expert Judgement | Develop Project Management Plan | Plan
OPA | Develop Project Charter | Initiate | Issue Log | Direct and Manage Project Work | Execute | Data Gathering | Develop Project Management Plan | Plan
Project Charter | Develop Project Management Plan | Plan | Change Requests | Direct and Manage Project Work | Execute | Interpersonal and Team Skills | Develop Project Management Plan | Plan
Outputs from Other Processes | Develop Project Management Plan | Plan | Project Management Plan Updates | Direct and Manage Project Work | Execute | Meetings | Develop Project Management Plan | Plan
EEF | Develop Project Management Plan | Plan | Proj Doc Update | Direct and Manage Project Work | Execute | Expert Judgement | Direct and Manage Project Work | Execute
OPA | Develop Project Management Plan | Plan | OPA | Direct and Manage Project Work | Execute | PMIS | Direct and Manage Project Work | Execute
Project Management Plan | Direct and Manage Project Work | Execute | Lessons Learned Registerister | Manage Project Knowledge | Execute | Meetings | Direct and Manage Project Work | Execute
Project Documents | Direct and Manage Project Work | Execute | Project Management Plan Updates | Manage Project Knowledge | Execute | Expert Judgement | Manage Project Knowledge | Execute
Change Log | Direct and Manage Project Work | Execute | OPA Updates | Manage Project Knowledge | Execute | Knowledge Management | Manage Project Knowledge | Execute
Lessons Learned Register | Direct and Manage Project Work | Execute | Work Perf Reports | Monitor and Control Project Work | Monitor/Control | Information Management | Manage Project Knowledge | Execute
Approved Change Request | Direct and Manage Project Work | Execute | Change Requests | Monitor and Control Project Work | Monitor/Control | Interpersonal and Team Skills | Manage Project Knowledge | Execute
EEF | Direct and Manage Project Work | Execute | Project Management Plan Updates | Monitor and Control Project Work | Monitor/Control | Expert Judgement | Monitor and Control Project Work | Monitor/Control
OPA | Direct and Manage Project Work | Execute | Proj Doc Update | Monitor and Control Project Work | Monitor/Control | Data Analysis | Monitor and Control Project Work | Monitor/Control
Project Management Plan | Manage Project Knowledge | Execute | Issue Log | Monitor and Control Project Work | Monitor/Control | Earned Value Analysis | Monitor and Control Project Work | Monitor/Control
Project Documents | Manage Project Knowledge | Execute | Lessons Learned Registerister | Monitor and Control Project Work | Monitor/Control | Trend Analysis | Monitor and Control Project Work | Monitor/Control
Lessons Learned Register | Manage Project Knowledge | Execute | Approved Change Request | Perform Integrated Change Control | Monitor/Control | Variance Analysis | Monitor and Control Project Work | Monitor/Control
Deliverables | Manage Project Knowledge | Execute | Project Management Plan Updates | Perform Integrated Change Control | Monitor/Control | Decision Making | Monitor and Control Project Work | Monitor/Control
EEF | Manage Project Knowledge | Execute | Proj Doc Update | Perform Integrated Change Control | Monitor/Control | Meetings | Monitor and Control Project Work | Monitor/Control
OPA | Manage Project Knowledge | Execute | Final Prod, Srv, or Result Transition | Close Project Or Phase | Close | Expert Judgement | Perform Integrated Change Control | Monitor/Control
Project Management Plan | Monitor and Control Project Work | Monitor/Control | Proj Doc Update | Close Project Or Phase | Close | Change Control Tools | Perform Integrated Change Control | Monitor/Control
Project Documents | Monitor and Control Project Work | Monitor/Control | Lessons Learned Registerister | Close Project Or Phase | Close | Alternative Analysis | Perform Integrated Change Control | Monitor/Control
Quality Reports | Monitor and Control Project Work | Monitor/Control | Final Report | Close Project Or Phase | Close | Cost Benefit Analysis | Perform Integrated Change Control | Monitor/Control
Risk Report | Monitor and Control Project Work | Monitor/Control | OPA Updates | Close Project Or Phase | Close | Meetings | Perform Integrated Change Control | Monitor/Control
Work Perf Info | Monitor and Control Project Work | Monitor/Control | Scope Management Plan | Plan Scope Management | Plan | Decision Making | Perform Integrated Change Control | Monitor/Control
Agreements | Monitor and Control Project Work | Monitor/Control | Requirements Mgmt Plan | Plan Scope Management | Plan | Expert Judgement | Close Project or Phase | Close
EEF | Monitor and Control Project Work | Monitor/Control | Requirements Documentation | Collect Requirements | Plan | Data Analysis | Close Project or Phase | Close
OPA | Monitor and Control Project Work | Monitor/Control | Requirements Traceability Matrix | Collect Requirements | Plan | Document Analysis | Close Project or Phase | Close
Project Management Plan | Perform Integrated Change Control | Monitor/Control | Project Scope Statement | Define Scope | Plan | Regression Analysis | Close Project or Phase | Close
Change Management Plan | Perform Integrated Change Control | Monitor/Control | Proj Doc Update | Define Scope | Plan | Trend Analysis | Close Project or Phase | Close
Configuration Management Plan | Perform Integrated Change Control | Monitor/Control | Assumptions Log | Define Scope | Plan | Variance Analysis | Close Project or Phase | Close
Scope Baseline | Perform Integrated Change Control | Monitor/Control | Requirements Documentation | Define Scope | Plan | Meetings | Close Project or Phase | Close
Cost Baseline | Perform Integrated Change Control | Monitor/Control | Requirements Traceability Matrix | Define Scope | Plan | Data Analysis | Plan Scope Management | Plan
Project Documents | Perform Integrated Change Control | Monitor/Control | Stakeholder Register | Define Scope | Plan | Alternative Analysis | Plan Scope Management | Plan
Basis of Estimates | Perform Integrated Change Control | Monitor/Control | Scope Baseline | Create WBS | Plan | Meetings | Plan Scope Management | Plan
Work Perf Reports | Perform Integrated Change Control | Monitor/Control | Proj Doc Update | Create WBS | Plan | Expert Judgement | Collect Requirements | Plan
Change Requests | Perform Integrated Change Control | Monitor/Control | Assumptions Log | Create WBS | Plan | Data Gathering | Collect Requirements | Plan
EEF | Perform Integrated Change Control | Monitor/Control | Requirements Documentation | Create WBS | Plan | Brainstorming | Collect Requirements | Plan
OPA | Perform Integrated Change Control | Monitor/Control | Accepted Deliverables | Validate Scope | Monitor/Control | Interviews | Collect Requirements | Plan
Project Charter | Close Project or Phase | Close | Work Performance Information | Validate Scope | Monitor/Control | Focus Groups | Collect Requirements | Plan
Project Management Plan | Close Project or Phase | Close | Change Requests | Validate Scope | Monitor/Control | Questionnaires and Surveys | Collect Requirements | Plan
Project Documents | Close Project or Phase | Close | Proj Doc Update | Validate Scope | Monitor/Control | Benchmarking | Collect Requirements | Plan
Accepted Deliverables | Close Project or Phase | Close | Lessons Learned Registerister | Validate Scope | Monitor/Control | Data Analysis | Collect Requirements | Plan
Business documents | Close Project or Phase | Close | Requirements Documentation | Validate Scope | Monitor/Control | Decision Making | Collect Requirements | Plan
Agreements | Close Project or Phase | Close | Requirements Traceability Matrix | Validate Scope | Monitor/Control | Voting | Collect Requirements | Plan
Procurement Documentation | Close Project or Phase | Close | Work Performance Information | Control Scope | Monitor/Control | Multi-Criteria Dec Analysis | Collect Requirements | Plan
OPA | Close Project or Phase | Close | Change Requests | Control Scope | Monitor/Control | Data Representation | Collect Requirements | Plan
Project Charter | Plan Scope Management | Plan | Project Management Plan Updates | Control Scope | Monitor/Control | Affinity Diagrams | Collect Requirements | Plan
Project Management Plan | Plan Scope Management | Plan | Scope Management Plan | Control Scope | Monitor/Control | Mind Mapping | Collect Requirements | Plan
Dev Approach | Plan Scope Management | Plan | Scope Baseline | Control Scope | Monitor/Control | Interpersonal and Team Skills | Collect Requirements | Plan
Proj LC Description | Plan Scope Management | Plan | Schedule Baseline | Control Scope | Monitor/Control | Nominal group techniques | Collect Requirements | Plan
Quality Management Plan | Plan Scope Management | Plan | Cost Baseline | Control Scope | Monitor/Control | Observation/Conversation | Collect Requirements | Plan
EEF | Plan Scope Management | Plan | Proj Doc Update | Control Scope | Monitor/Control | Facilitation | Collect Requirements | Plan
OPA | Plan Scope Management | Plan | Lessons Learned Registerister | Control Scope | Monitor/Control | Context Diagrams | Collect Requirements | Plan
Project Charter | Collect Requirements | Plan | Requirements Documentation | Control Scope | Monitor/Control | Prototypes | Collect Requirements | Plan
Project Management Plan | Collect Requirements | Plan | Requirements Traceability Matrix | Control Scope | Monitor/Control | Expert Judgement | Define Scope | Plan
Scope Management Plan | Collect Requirements | Plan | Schedule Management Plan | Plan Schedule Management | Plan | Data Analysis | Define Scope | Plan
Requirements Management Plan | Collect Requirements | Plan | Activity List | Define Activities | Plan | Alternative Analysis | Define Scope | Plan
Stakeholder Engagement Plan | Collect Requirements | Plan | Activity Attributes | Define Activities | Plan | Decision Making | Define Scope | Plan
Project Documents | Collect Requirements | Plan | Milestone List | Define Activities | Plan | Multi-Criteria Dec Analysis | Define Scope | Plan
Assumptions Log | Collect Requirements | Plan | Change Requests | Define Activities | Plan | Interpersonal and Team Skills | Define Scope | Plan
Lessons Learned Register | Collect Requirements | Plan | Project Management Plan Updates | Define Activities | Plan | Facilitation | Define Scope | Plan
Stakeholder Register | Collect Requirements | Plan | Schedule Baseline | Define Activities | Plan | Product Analysis | Define Scope | Plan
Business documents | Collect Requirements | Plan | Cost Baseline | Define Activities | Plan | Expert Judgement | Create WBS | Plan
Business Case | Collect Requirements | Plan | Proj Schedule Network Diagrams | Sequence Activities | Plan | Decomposition | Create WBS | Plan
Agreements | Collect Requirements | Plan | Proj Doc Update | Sequence Activities | Plan | Inspection | Validate Scope | Monitor/Control
EEF | Collect Requirements | Plan | Activity Attributes | Sequence Activities | Plan | Decision Making | Validate Scope | Monitor/Control
OPA | Collect Requirements | Plan | Activity List | Sequence Activities | Plan | Voting | Validate Scope | Monitor/Control
Project Charter | Define Scope | Plan | Assumptions Log | Sequence Activities | Plan | Data Analysis | Control Scope | Monitor/Control
Project Management Plan | Define Scope | Plan | Milestone List | Sequence Activities | Plan | Variance Analysis | Control Scope | Monitor/Control
Scope Management Plan | Define Scope | Plan | Duration Estimates | Estimate Activity Durations | Plan | Trend Analysis | Control Scope | Monitor/Control
Project Documents | Define Scope | Plan | Basis of Estimates | Estimate Activity Durations | Plan | Expert Judgement | Plan Schedule Management | Plan
Assumptions Log | Define Scope | Plan | Proj Doc Update | Estimate Activity Durations | Plan | Data Analysis | Plan Schedule Management | Plan
Req Documents | Define Scope | Plan | Activity Attributes | Estimate Activity Durations | Plan | Meetings | Plan Schedule Management | Plan
Risk Register | Define Scope | Plan | Assumptions Log | Estimate Activity Durations | Plan | Expert Judgement | Define Activities | Plan
EEF | Define Scope | Plan | Lessons Learned Registerister | Estimate Activity Durations | Plan | Decomposition | Define Activities | Plan
OPA | Define Scope | Plan | Schedule Baseline | Develop Schedule | Plan | Rolling Wave Planning | Define Activities | Plan
Project Management Plan | Create WBS | Plan | Project Schedule | Develop Schedule | Plan | Meetings | Define Activities | Plan
Scope Management Plan | Create WBS | Plan | Schedule Data | Develop Schedule | Plan | Precedence Diagraming Method | Sequence Activities | Plan
Project Documents | Create WBS | Plan | Project Calendars | Develop Schedule | Plan | Dependency Deter and Integration | Sequence Activities | Plan
Project Scope Statements | Create WBS | Plan | Change Requests | Develop Schedule | Plan | Leads and Lags | Sequence Activities | Plan
Requirements Documentation | Create WBS | Plan | Schedule Management Plan | Develop Schedule | Plan | PMIS | Sequence Activities | Plan
EEF | Create WBS | Plan | Cost Baseline | Develop Schedule | Plan | Expert Judgement | Estimate Activity Durations | Plan
OPA | Create WBS | Plan | Activity Attributes | Develop Schedule | Plan | Analogous Estimating | Estimate Activity Durations | Plan
Project Management Plan | Validate Scope | Monitor/Control | Assumptions Log | Develop Schedule | Plan | Parametric Estimating | Estimate Activity Durations | Plan
Scope Management Plan | Validate Scope | Monitor/Control | Duration Estimates | Develop Schedule | Plan | Three-Point Estimates | Estimate Activity Durations | Plan
Requirements Management Plan | Validate Scope | Monitor/Control | Lessons Learned Registerister | Develop Schedule | Plan | Bottom-up Estimating | Estimate Activity Durations | Plan
Scope Baseline | Validate Scope | Monitor/Control | Resource Requirements | Develop Schedule | Plan | Data Analysis | Estimate Activity Durations | Plan
Project Documents | Validate Scope | Monitor/Control | Risk Register | Develop Schedule | Plan | Alternative Analysis | Estimate Activity Durations | Plan
Lessons Learned Register | Validate Scope | Monitor/Control | Work Performance Information | Control Schedule | Monitor/Control | Reserve Analysis | Estimate Activity Durations | Plan
Quality Reports | Validate Scope | Monitor/Control | Schedule Forecasts | Control Schedule | Monitor/Control | Decision Making | Estimate Activity Durations | Plan
Requirements Documentation | Validate Scope | Monitor/Control | Change Requests | Control Schedule | Monitor/Control | Meetings | Estimate Activity Durations | Plan
Requirements Traceability Matrix | Validate Scope | Monitor/Control | Schedule Management Plan | Control Schedule | Monitor/Control | Schedule Network Analysis | Develop Schedule | Plan
Verified Deliverables | Validate Scope | Monitor/Control | Schedule Baseline | Control Schedule | Monitor/Control | Critical Path Method | Develop Schedule | Plan
Work Performance Data | Validate Scope | Monitor/Control | Cost Baseline | Control Schedule | Monitor/Control | Resource Optimization | Develop Schedule | Plan
Project Management Plan | Control Scope | Monitor/Control | Performance Measurement Baseline | Control Schedule | Monitor/Control | Data Analysis | Develop Schedule | Plan
Scope Management Plan | Control Scope | Monitor/Control | Assumptions Log | Control Schedule | Monitor/Control | Leads and Lags | Develop Schedule | Plan
Requirements Management Plan | Control Scope | Monitor/Control | Basis of Estimates | Control Schedule | Monitor/Control | Schedule Compression | Develop Schedule | Plan
Change Management Plan | Control Scope | Monitor/Control | Lessons Learned Registerister | Control Schedule | Monitor/Control | PMIS | Develop Schedule | Plan
Configuration Management Plan | Control Scope | Monitor/Control | Project Schedule | Control Schedule | Monitor/Control | Agile Release Planning | Develop Schedule | Plan
Scope Baseline | Control Scope | Monitor/Control | Resource Calendars | Control Schedule | Monitor/Control | Earned Value Analysis | Control Schedule | Monitor/Control
Performance Measurement Baseline | Control Scope | Monitor/Control | Risk Register | Control Schedule | Monitor/Control | Iteration Burndown Chart | Control Schedule | Monitor/Control
Project Documents | Control Scope | Monitor/Control | Schedule Data | Control Schedule | Monitor/Control | Performance Reviews | Control Schedule | Monitor/Control
Lessons Learned Register | Control Scope | Monitor/Control | Cost Management Plan | Plan Cost Management | Plan | Trend Analysis | Control Schedule | Monitor/Control
Requirements Documentation | Control Scope | Monitor/Control | Cost Estimates | Estimate Costs | Plan | Variance Analysis | Control Schedule | Monitor/Control
Requirements Traceability Matrix | Control Scope | Monitor/Control | Basis of Estimates | Estimate Costs | Plan | What-If Scenario Analysis | Control Schedule | Monitor/Control
Work Performance Data | Control Scope | Monitor/Control | Assumptions Log | Estimate Costs | Plan | Critical Path Method | Control Schedule | Monitor/Control
OPA | Control Scope | Monitor/Control | Lessons Learned Registerister | Estimate Costs | Plan | PMIS | Control Schedule | Monitor/Control
Project Charter | Plan Schedule Management | Plan | Risk Register | Estimate Costs | Plan | Resource Optimization | Control Schedule | Monitor/Control
Project Management Plan | Plan Schedule Management | Plan | Cost Baseline | Determine Budget | Plan | Leads and Lags | Control Schedule | Monitor/Control
Scope Management Plan | Plan Schedule Management | Plan | Project Funding Requirements | Determine Budget | Plan | Schedule Compression | Control Schedule | Monitor/Control
Dev Approach | Plan Schedule Management | Plan | Cost Estimates | Determine Budget | Plan | Expert Judgement | Plan Cost Management | Plan
EEF | Plan Schedule Management | Plan | Project Schedule | Determine Budget | Plan | Data Analysis | Plan Cost Management | Plan
OPA | Plan Schedule Management | Plan | Risk Register | Determine Budget | Plan | Meetings | Plan Cost Management | Plan
Project Management Plan | Define Activities | Plan | Work Performance Information | Control Costs | Monitor/Control | Expert Judgement | Estimate Costs | Plan
Schedule Management Plan | Define Activities | Plan | Cost Forecasts | Control Costs | Monitor/Control | Analogous Estimating | Estimate Costs | Plan
Scope Baseline | Define Activities | Plan | Change Requests | Control Costs | Monitor/Control | Parametric Estimating | Estimate Costs | Plan
EEF | Define Activities | Plan | Cost Management Plan | Control Costs | Monitor/Control | Bottom-up Estimating | Estimate Costs | Plan
OPA | Define Activities | Plan | Cost Baseline | Control Costs | Monitor/Control | Three-Point Estimates | Estimate Costs | Plan
Project Management Plan | Sequence Activities | Plan | Performance Measurement Baseline | Control Costs | Monitor/Control | Alternative Analysis | Estimate Costs | Plan
Schedule Management Plan | Sequence Activities | Plan | Assumptions Log | Control Costs | Monitor/Control | Reserve Analysis | Estimate Costs | Plan
Scope Baseline | Sequence Activities | Plan | Basis of Estimates | Control Costs | Monitor/Control | Cost of Quality | Estimate Costs | Plan
Project Documents | Sequence Activities | Plan | Cost Estimates | Control Costs | Monitor/Control | PMIS | Estimate Costs | Plan
Activity Attributes | Sequence Activities | Plan | Lessons Learned Registerister | Control Costs | Monitor/Control | Decision Making | Estimate Costs | Plan
Activity List | Sequence Activities | Plan | Risk Register | Control Costs | Monitor/Control | Voting | Estimate Costs | Plan
Assumptions Log | Sequence Activities | Plan | Quality Management Plan | Plan Quality Management | Plan | Expert Judgement | Determine Budget | Plan
Milestone List | Sequence Activities | Plan | Quality Metrics | Plan Quality Management | Plan | Cost Aggregation | Determine Budget | Plan
EEF | Sequence Activities | Plan | Risk Management Plan Updates | Plan Quality Management | Plan | Reserve Analysis | Determine Budget | Plan
OPA | Sequence Activities | Plan | Scope Baseline | Plan Quality Management | Plan | Historical Information Review | Determine Budget | Plan
Project Management Plan | Estimate Activity Durations | Plan | Lessons Learned Registerister | Plan Quality Management | Plan | Funding Limit Reconcilation | Determine Budget | Plan
Schedule Management Plan | Estimate Activity Durations | Plan | Requirements Traceability Matrix | Plan Quality Management | Plan | Expert Judgement | Conrol Costs | Monitor/Control
Scope Baseline | Estimate Activity Durations | Plan | Risk Register | Plan Quality Management | Plan | Data Analysis | Conrol Costs | Monitor/Control
Project Documents | Estimate Activity Durations | Plan | Stakeholder Register | Plan Quality Management | Plan | Earned Value Management | Conrol Costs | Monitor/Control
Activity Attributes | Estimate Activity Durations | Plan | Quality Reports | Manage Quality | Execute | Variance Analysis | Conrol Costs | Monitor/Control
Activity List | Estimate Activity Durations | Plan | Test and Eval Documents | Manage Quality | Execute | Trend Analysis | Conrol Costs | Monitor/Control
Assumptions Log | Estimate Activity Durations | Plan | Change Requests | Manage Quality | Execute | Reserve Analysis | Conrol Costs | Monitor/Control
Lessons Learned Register | Estimate Activity Durations | Plan | Quality Management Plan | Manage Quality | Execute | To-Complete Perf Index | Conrol Costs | Monitor/Control
Milestone List | Estimate Activity Durations | Plan | Scope Baseline | Manage Quality | Execute | PMIS | Conrol Costs | Monitor/Control
Project Team Assignments | Estimate Activity Durations | Plan | Schedule Baseline | Manage Quality | Execute | Expert Judgement | Plan Quality Management | Plan
Resource Breakdown Structure | Estimate Activity Durations | Plan | Cost Baseline | Manage Quality | Execute | Benchmarking | Plan Quality Management | Plan
Resource Calendars | Estimate Activity Durations | Plan | Issue Log | Manage Quality | Execute | Interviews | Plan Quality Management | Plan
Resource Requirements | Estimate Activity Durations | Plan | Lessons Learned Registerister | Manage Quality | Execute | Cost Benefit Analysis | Plan Quality Management | Plan
Risk Register | Estimate Activity Durations | Plan | Risk Register | Manage Quality | Execute | Cost of Quality | Plan Quality Management | Plan
EEF | Estimate Activity Durations | Plan | Quality Control Measurements | Control Quality | Monitor/Control | Multi-Criteria Dec Analysis | Plan Quality Management | Plan
OPA | Estimate Activity Durations | Plan | Verified Deliverables | Control Quality | Monitor/Control | Flowcharts | Plan Quality Management | Plan
Schedule Management Plan | Develop Schedule | Plan | Work Performance Information | Control Quality | Monitor/Control | Logical Data Model | Plan Quality Management | Plan
Scope Baseline | Develop Schedule | Plan | Change Requests | Control Quality | Monitor/Control | Matrix Diagrams | Plan Quality Management | Plan
Activity Attributes | Develop Schedule | Plan | Quality Management Plan | Control Quality | Monitor/Control | Mind Mapping | Plan Quality Management | Plan
Activity List | Develop Schedule | Plan | Issue Log | Control Quality | Monitor/Control | Test and Inspection Planning | Plan Quality Management | Plan
Assumptions Log | Develop Schedule | Plan | Lessons Learned Registerister | Control Quality | Monitor/Control | Meetings | Plan Quality Management | Plan
Basis of Estimates | Develop Schedule | Plan | Risk Register | Control Quality | Monitor/Control | Checklists | Manage Quality | Execute
Lessons Learned Register | Develop Schedule | Plan | Test and Eval Documents | Control Quality | Monitor/Control | Alternative Analysis | Manage Quality | Execute
Milestone List | Develop Schedule | Plan | Team Charter | Plan Resource Management | Plan | Document Analysis | Manage Quality | Execute
Project Schedule Network Diagram | Develop Schedule | Plan | Resource Management Plan | Plan Resource Management | Plan | Process Analysis | Manage Quality | Execute
Project Team Assignments | Develop Schedule | Plan | Assumptions Log | Plan Resource Management | Plan | Root Cause Analysis | Manage Quality | Execute
Resource Calendars | Develop Schedule | Plan | Risk Register | Plan Resource Management | Plan | Multi-Criteria Dec Analysis | Manage Quality | Execute
Resource Requirements | Develop Schedule | Plan | Resource Requirements | Estimate Activity Resources | Plan | Affinity Diagrams | Manage Quality | Execute
Risk Register | Develop Schedule | Plan | Basis of Estimates | Estimate Activity Resources | Plan | Cause and Effect Diagrams | Manage Quality | Execute
Agreements | Develop Schedule | Plan | Resource Breakdown Structure | Estimate Activity Resources | Plan | Flowcharts | Manage Quality | Execute
EEF | Develop Schedule | Plan | Activity Attributes | Estimate Activity Resources | Plan | Histograms | Manage Quality | Execute
OPA | Develop Schedule | Plan | Assumptions Log | Estimate Activity Resources | Plan | Matrix Diagrams | Manage Quality | Execute
Schedule Management Plan | Control Schedule | Monitor/Control | Lessons Learned Registerister | Estimate Activity Resources | Plan | Scatter Diagrams | Manage Quality | Execute
Schedule Baseline | Control Schedule | Monitor/Control | Physical Resource Assignments | Acquire Resources | Execute | Audits | Manage Quality | Execute
Scope Baseline | Control Schedule | Monitor/Control | Resource Calendars | Acquire Resources | Execute | Design for X | Manage Quality | Execute
Performance Measurement Baseline | Control Schedule | Monitor/Control | Change Requests | Acquire Resources | Execute | Problem Solving | Manage Quality | Execute
Lessons Learned Register | Control Schedule | Monitor/Control | Resource Management Plan | Acquire Resources | Execute | Quality Improvement Methods | Manage Quality | Execute
Project Calendars | Control Schedule | Monitor/Control | Cost Baseline | Acquire Resources | Execute | Checklists | Control Quality | Monitor/Control
Project Schedule | Control Schedule | Monitor/Control | Lessons Learned Registerister | Acquire Resources | Execute | Check Sheets | Control Quality | Monitor/Control
Resource Calendars | Control Schedule | Monitor/Control | Project Schedule | Acquire Resources | Execute | Statistical Sampling | Control Quality | Monitor/Control
Schedule Data | Control Schedule | Monitor/Control | Resource Breakdown Structure | Acquire Resources | Execute | Questionnaires and Surveys | Control Quality | Monitor/Control
Work Performance Data | Control Schedule | Monitor/Control | Resource Requirements | Acquire Resources | Execute | Performance Reviews | Control Quality | Monitor/Control
OPA | Control Schedule | Monitor/Control | Risk Register | Acquire Resources | Execute | Root Cause Analysis | Control Quality | Monitor/Control
Project Charter | Plan Cost Management | Plan | Stakeholder Register | Acquire Resources | Execute | Inspection | Control Quality | Monitor/Control
Schedule Management Plan | Plan Cost Management | Plan | EEF Updates | Acquire Resources | Execute | Testing/Product Eval | Control Quality | Monitor/Control
Risk Management Plan | Plan Cost Management | Plan | OPA Updates | Acquire Resources | Execute | Cause and Effect Diagrams | Control Quality | Monitor/Control
EEF | Plan Cost Management | Plan | Team Performance Assessments | Develop Team | Execute | Control Charts | Control Quality | Monitor/Control
OPA | Plan Cost Management | Plan | Change Requests | Develop Team | Execute | Histograms | Control Quality | Monitor/Control
Cost Management Plan | Estimate Costs | Plan | Project Management Plan Updates | Develop Team | Execute | Scatter Diagrams | Control Quality | Monitor/Control
Quality Management Plan | Estimate Costs | Plan | Resource Management Plan | Develop Team | Execute | Meetings | Control Quality | Monitor/Control
Scope Baseline | Estimate Costs | Plan | Proj Doc Update | Develop Team | Execute | Expert Judgement | Plan Resource Management | Plan
Lessons Learned Register | Estimate Costs | Plan | Lessons Learned Registerister | Develop Team | Execute | Hierarchical Type Charts | Plan Resource Management | Plan
Project Schedule | Estimate Costs | Plan | Project Schedule | Develop Team | Execute | Responsibility Assignment Matrix | Plan Resource Management | Plan
Resource Requirements | Estimate Costs | Plan | Project Team Assignments | Develop Team | Execute | Text-Oriented Format | Plan Resource Management | Plan
Risk Register | Estimate Costs | Plan | Resource Calendars | Develop Team | Execute | Organizational Theory | Plan Resource Management | Plan
EEF | Estimate Costs | Plan | Team Charter | Develop Team | Execute | Meetings | Plan Resource Management | Plan
OPA | Estimate Costs | Plan | EEF Updates | Develop Team | Execute | Expert Judgement | Estimate Activity Resources | Plan
Cost Management Plan | Determine Budget | Plan | OPA Updates | Develop Team | Execute | Bottom-up Estimating | Estimate Activity Resources | Plan
Resource Management Plan | Determine Budget | Plan | Change Requests | Manage Team | Execute | Analogous Estimating | Estimate Activity Resources | Plan
Scope Baseline | Determine Budget | Plan | Project Management Plan Updates | Manage Team | Execute | Parametric Estimating | Estimate Activity Resources | Plan
Basis of Estimates | Determine Budget | Plan | Resource Management Plan | Manage Team | Execute | Alternative Analysis | Estimate Activity Resources | Plan
Cost Estimates | Determine Budget | Plan | Schedule Baseline | Manage Team | Execute | PMIS | Estimate Activity Resources | Plan
Project Schedule | Determine Budget | Plan | Cost Baseline | Manage Team | Execute | Meetings | Estimate Activity Resources | Plan
Risk Register | Determine Budget | Plan | Proj Doc Update | Manage Team | Execute | Multi-Criteria Dec Analysis | Acquire Resources | Execute
Business Case | Determine Budget | Plan | Issue Log | Manage Team | Execute | Interpersonal and Team Skills | Acquire Resources | Execute
Benefits Management Plan | Determine Budget | Plan | Lessons Learned Registerister | Manage Team | Execute | Negotiations | Acquire Resources | Execute
Agreements | Determine Budget | Plan | Project Team Assignments | Manage Team | Execute | Pre-Assignment | Acquire Resources | Execute
EEF | Determine Budget | Plan | EEF Updates | Manage Team | Execute | Virtual teams | Acquire Resources | Execute
OPA | Determine Budget | Plan | Work Performance Information | Control Resources | Monitor/Control | Colocation | Develop Team | Execute
Cost Management Plan | Control Costs | Monitor/Control | Change Requests | Control Resources | Monitor/Control | Virtual teams | Develop Team | Execute
Cost Baseline | Control Costs | Monitor/Control | Project Management Plan Updates | Control Resources | Monitor/Control | Communication Technology | Develop Team | Execute
Performance Measurement Baseline | Control Costs | Monitor/Control | Resource Management Plan | Control Resources | Monitor/Control | Interpersonal and Team Skills | Develop Team | Execute
Lessons Learned Register | Control Costs | Monitor/Control | Schedule Baseline | Control Resources | Monitor/Control | Conflict Management | Develop Team | Execute
Project Funding Requirements | Control Costs | Monitor/Control | Cost Baseline | Control Resources | Monitor/Control | Influencing | Develop Team | Execute
Work Performance Data | Control Costs | Monitor/Control | Proj Doc Update | Control Resources | Monitor/Control | Motivation | Develop Team | Execute
OPA | Control Costs | Monitor/Control | Assumptions Log | Control Resources | Monitor/Control | Negotiations | Develop Team | Execute
Project Charter | Plan Quality Management | Plan | Issue Log | Control Resources | Monitor/Control | Team Building | Develop Team | Execute
Requirements Management Plan | Plan Quality Management | Plan | Lessons Learned Registerister | Control Resources | Monitor/Control | Recognition and Rewards | Develop Team | Execute
Risk Management Plan | Plan Quality Management | Plan | Physical Resource Assignments | Control Resources | Monitor/Control | Training | Develop Team | Execute
Stakeholder Engagement Plan | Plan Quality Management | Plan | Resource Breakdown Structure | Control Resources | Monitor/Control | Individual and Team Assessments | Develop Team | Execute
Scope Baseline | Plan Quality Management | Plan | Risk Register | Control Resources | Monitor/Control | Meetings | Develop Team | Execute
Assumptions Log | Plan Quality Management | Plan | Communications Management Plan | Plan Communication Management | Plan | Interpersonal and Team Skills | Manage Team | Execute
Requirements Documentation | Plan Quality Management | Plan | Project Management Plan Updates | Plan Communication Management | Plan | Conflict Management | Manage Team | Execute
Requirements Traceability Matrix | Plan Quality Management | Plan | Stakeholder Engagement Plan | Plan Communication Management | Plan | Decision Making | Manage Team | Execute
Risk Register | Plan Quality Management | Plan | Proj Doc Update | Plan Communication Management | Plan | Emotional Intelligence | Manage Team | Execute
Stakeholder Register | Plan Quality Management | Plan | Project Schedule | Plan Communication Management | Plan | Influencing | Manage Team | Execute
EEF | Plan Quality Management | Plan | Stakeholder Register | Plan Communication Management | Plan | Leadership | Manage Team | Execute
OPA | Plan Quality Management | Plan | Project Communications | Manage Communications | Execute | PMIS | Manage Team | Execute
Quality Management Plan | Manage Quality | Execute | Project Management Plan Updates | Manage Communications | Execute | Data Analysis | Control Resources | Monitor/Control
Lessons Learned Register | Manage Quality | Execute | Communications Management Plan | Manage Communications | Execute | Alternative Analysis | Control Resources | Monitor/Control
Quality Control Measurements | Manage Quality | Execute | Stakeholder Engagement Plan | Manage Communications | Execute | Cost Benefit Analysis | Control Resources | Monitor/Control
Quality Metrics | Manage Quality | Execute | Proj Doc Update | Manage Communications | Execute | Performance Reviews | Control Resources | Monitor/Control
Risk Report | Manage Quality | Execute | Issue Log | Manage Communications | Execute | Trend Analysis | Control Resources | Monitor/Control
OPA | Manage Quality | Execute | Lessons Learned Registerister | Manage Communications | Execute | Problem Solving | Control Resources | Monitor/Control
Quality Management Plan | Control Quality | Monitor/Control | Project Schedule | Manage Communications | Execute | Interpersonal and Team Skills | Control Resources | Monitor/Control
Lessons Learned Register | Control Quality | Monitor/Control | Risk Register | Manage Communications | Execute | Negotiations | Control Resources | Monitor/Control
Quality Metrics | Control Quality | Monitor/Control | Stakeholder Register | Manage Communications | Execute | Influencing | Control Resources | Monitor/Control
Test and Eval Documents | Control Quality | Monitor/Control | Work Performance Information | Monitor Communications | Monitor/Control | PMIS | Control Resources | Monitor/Control
Approved Change Request | Control Quality | Monitor/Control | Change Requests | Monitor Communications | Monitor/Control | Expert Judgement | Plan Communications Management | Plan
Deliverables | Control Quality | Monitor/Control | Project Management Plan Updates | Monitor Communications | Monitor/Control | Communication Req Analysis | Plan Communications Management | Plan
Work Performance Data | Control Quality | Monitor/Control | Project Documents Updates | Monitor Communications | Monitor/Control | Communication Technology | Plan Communications Management | Plan
EEF | Control Quality | Monitor/Control | Risk Management Plan | Plan Risk Management | Plan | Communication Models | Plan Communications Management | Plan
OPA | Control Quality | Monitor/Control | Risk Register | Identify Risks | Plan | Communication Methods | Plan Communications Management | Plan
Project Charter | Plan Resource Management | Plan | Risk Report | Identify Risks | Plan | Interpersonal and Team Skills | Plan Communications Management | Plan
Quality Management Plan | Plan Resource Management | Plan | Proj Doc Update | Identify Risks | Plan | Communications Styles Assessment | Plan Communications Management | Plan
Scope Baseline | Plan Resource Management | Plan | Assumptions Log | Identify Risks | Plan | Political Awareness | Plan Communications Management | Plan
Project Schedule | Plan Resource Management | Plan | Issue Log | Identify Risks | Plan | Cultural Awareness | Plan Communications Management | Plan
Requirements Documentation | Plan Resource Management | Plan | Lessons Learned Registerister | Identify Risks | Plan | Data Representation | Plan Communications Management | Plan
Risk Register | Plan Resource Management | Plan | Proj Doc Update | Perform Qualitative Risk Analysis | Plan | Stakeholder Engagement Assessment Matrix | Plan Communications Management | Plan
Stakeholder Register | Plan Resource Management | Plan | Assumptions Log | Perform Qualitative Risk Analysis | Plan | Meetings | Plan Communications Management | Plan
EEF | Plan Resource Management | Plan | Issue Log | Perform Qualitative Risk Analysis | Plan | Communications Technology | Manage Communications | Execute
OPA | Plan Resource Management | Plan | Risk Register | Perform Qualitative Risk Analysis | Plan | Communications Methods | Manage Communications | Execute
Resource Management Plan | Estimate Activity Resources | Plan | Risk Report | Perform Qualitative Risk Analysis | Plan | Communications Skills | Manage Communications | Execute
Scope Baseline | Estimate Activity Resources | Plan | Risk Report | Perform Quantitative Risk Analysis | Plan | Communication Competence | Manage Communications | Execute
Activity Attributes | Estimate Activity Resources | Plan | Change Requests | Plan Risk Responses | Plan | Feedback | Manage Communications | Execute
Activity Lists | Estimate Activity Resources | Plan | Project Management Plan Updates | Plan Risk Responses | Plan | Nonverbal | Manage Communications | Execute
Assumptions Log | Estimate Activity Resources | Plan | Schedule Management Plan | Plan Risk Responses | Plan | Presentations | Manage Communications | Execute
Cost Estimates | Estimate Activity Resources | Plan | Cost Management Plan | Plan Risk Responses | Plan | PMIS | Manage Communications | Execute
Resource Calendars | Estimate Activity Resources | Plan | Quality Management Plan | Plan Risk Responses | Plan | Project Reporting | Manage Communications | Execute
Risk Register | Estimate Activity Resources | Plan | Procurement Management Plan | Plan Risk Responses | Plan | Interpersonal and Team Skills | Manage Communications | Execute
EEF | Estimate Activity Resources | Plan | Scope Baseline | Plan Risk Responses | Plan | Active Listening | Manage Communications | Execute
OPA | Estimate Activity Resources | Plan | Schedule Baseline | Plan Risk Responses | Plan | Conflict Management | Manage Communications | Execute
Resource Management Plan | Acquire Resources | Execute | Cost Baseline | Plan Risk Responses | Plan | Cultural Awareness | Manage Communications | Execute
Procurement Management Plan | Acquire Resources | Execute | Proj Doc Update | Plan Risk Responses | Plan | Meeting Management | Manage Communications | Execute
Cost Baseline | Acquire Resources | Execute | Assumptions Log | Plan Risk Responses | Plan | Networking | Manage Communications | Execute
Project Schedule | Acquire Resources | Execute | Cost Forecasts | Plan Risk Responses | Plan | Political Awareness | Manage Communications | Execute
Resource Calendars | Acquire Resources | Execute | Lessons Learned Registerister | Plan Risk Responses | Plan | Meeting | Manage Communications | Execute
Resource Requirements | Acquire Resources | Execute | Project Schedule | Plan Risk Responses | Plan | Expert Judgement | Monitor Communications | Monitor/Control
Stakeholder Register | Acquire Resources | Execute | Project Team Assignments | Plan Risk Responses | Plan | Project Management Information System | Monitor Communications | Monitor/Control
EEF | Acquire Resources | Execute | Risk Register | Plan Risk Responses | Plan | Data Representation | Monitor Communications | Monitor/Control
OPA | Acquire Resources | Execute | Risk Report | Plan Risk Responses | Plan | Interpersonal and Team Skills | Monitor Communications | Monitor/Control
Resource Management Plan | Develop Team | Execute | Change Requests | Implement Risk Responses | Execute | Meetings | Monitor Communications | Monitor/Control
Lessons Learned Register | Develop Team | Execute | Proj Doc Update | Implement Risk Responses | Execute | Expert Judgement | Plan Risk Management | Plan
Project Schedule | Develop Team | Execute | Issue Log | Implement Risk Responses | Execute | Data Analysis | Plan Risk Management | Plan
Project Team Assignments | Develop Team | Execute | Lessons Learned Registerister | Implement Risk Responses | Execute | Stakeholder Analysis | Plan Risk Management | Plan
Resource Calendars | Develop Team | Execute | Project Team Assessment | Implement Risk Responses | Execute | Meetings | Plan Risk Management | Plan
Team Charter | Develop Team | Execute | Risk Register | Implement Risk Responses | Execute | Expert Judgement | Identify Risks | Plan
EEF | Develop Team | Execute | Risk Report | Implement Risk Responses | Execute | Data Gathering | Identify Risks | Plan
OPS | Develop Team | Execute | Work Performance Information | Monitor Risks | Monitor/Control | Brainstorming | Identify Risks | Plan
Resource Management Plan | Manage Team | Execute | Change Requests | Monitor Risks | Monitor/Control | Checklists | Identify Risks | Plan
Issue Log | Manage Team | Execute | Project Management Plan Updates | Monitor Risks | Monitor/Control | Interviews | Identify Risks | Plan
Lessons Learned Register | Manage Team | Execute | Proj Doc Update | Monitor Risks | Monitor/Control | Data Analysis | Identify Risks | Plan
Project Team Assignments | Manage Team | Execute | Assumptions Log | Monitor Risks | Monitor/Control | Root Cause Analysis | Identify Risks | Plan
Team Charter | Manage Team | Execute | Issue Log | Monitor Risks | Monitor/Control | Assumption and Constraint Analysis | Identify Risks | Plan
Work Performance Reports | Manage Team | Execute | Lessons Learned Registerister | Monitor Risks | Monitor/Control | SWOT Analysis | Identify Risks | Plan
Team Performance Assessments | Manage Team | Execute | Risk Register | Monitor Risks | Monitor/Control | Document Analysis | Identify Risks | Plan
EEF | Manage Team | Execute | Risk Report | Monitor Risks | Monitor/Control | Interpersonal and Team Skills | Identify Risks | Plan
OPA | Manage Team | Execute | OPA Updates | Monitor Risks | Monitor/Control | Facilitation | Identify Risks | Plan
Resource Management Plan | Control Resources | Monitor/Control | Procurement Management Plan | Plan Procurement Management | Plan | Prompt Lists | Identify Risks | Plan
Issue Log | Control Resources | Monitor/Control | Procurement Strategy | Plan Procurement Management | Plan | Meetings | Identify Risks | Plan
Lessons Learned Register | Control Resources | Monitor/Control | Bid Documents | Plan Procurement Management | Plan | Expert Judgement | Perform Qualitiative Risk Analysis | Plan
Project Schedule | Control Resources | Monitor/Control | Procurement Statemen of Work | Plan Procurement Management | Plan | Data Gathering | Perform Qualitiative Risk Analysis | Plan
Physical Resource Assignments | Control Resources | Monitor/Control | Source Selection Criteria | Plan Procurement Management | Plan | Interviews | Perform Qualitiative Risk Analysis | Plan
Resource Breakdown Structure | Control Resources | Monitor/Control | Make-or-Buy Decisions | Plan Procurement Management | Plan | Data Analysis | Perform Qualitiative Risk Analysis | Plan
Resource Requirements | Control Resources | Monitor/Control | Independent Cost Estimates | Plan Procurement Management | Plan | Risk Data Quality Assessment | Perform Qualitiative Risk Analysis | Plan
Risk Register | Control Resources | Monitor/Control | Change Requests | Plan Procurement Management | Plan | Risk Probability and Impact Assessment | Perform Qualitiative Risk Analysis | Plan
Work Performance Data | Control Resources | Monitor/Control | Proj Doc Update | Plan Procurement Management | Plan | Assessment of Other Risk Parameters | Perform Qualitiative Risk Analysis | Plan
Agreements | Control Resources | Monitor/Control | Lessons Learned Registerister | Plan Procurement Management | Plan | Interpersonal and Team Skills | Perform Qualitiative Risk Analysis | Plan
OPA | Control Resources | Monitor/Control | Milestone List | Plan Procurement Management | Plan | Facilitation | Perform Qualitiative Risk Analysis | Plan
Project Charter | Plan Communications Management | Plan | Requirements Documentation | Plan Procurement Management | Plan | Risk Categorization | Perform Qualitiative Risk Analysis | Plan
Project Management Plan | Plan Communications Management | Plan | Requirements Traceability Matrix | Plan Procurement Management | Plan | Data Representation | Perform Qualitiative Risk Analysis | Plan
Resource Management Plan | Plan Communications Management | Plan | Risk Register | Plan Procurement Management | Plan | Probability and Impact Matrix | Perform Qualitiative Risk Analysis | Plan
Stakeholder Management Plan | Plan Communications Management | Plan | Stakeholder Register | Plan Procurement Management | Plan | Heirarchical-Type Charts | Perform Qualitiative Risk Analysis | Plan
Project Documents | Plan Communications Management | Plan | OPA Updates | Plan Procurement Management | Plan | Meetings | Perform Qualitiative Risk Analysis | Plan
Requirements Documentation | Plan Communications Management | Plan | Selected Sellerts | Conduct Procurements | Execute | Expert Judgement | Perform Quantitative Risk Analysis | Plan
Stakeholder Register | Plan Communications Management | Plan | Agreements | Conduct Procurements | Execute | Data Gathering | Perform Quantitative Risk Analysis | Plan
EEF | Plan Communications Management | Plan | Change Requests | Conduct Procurements | Execute | Interviews | Perform Quantitative Risk Analysis | Plan
OPA | Plan Communications Management | Plan | Project Management Plan Updates | Conduct Procurements | Execute | Interpersonal and Team Skills | Perform Quantitative Risk Analysis | Plan
Project Management Plan | Manage Communications | Execute | Requirements Mgmt Plan | Conduct Procurements | Execute | Facilitation | Perform Quantitative Risk Analysis | Plan
Resource Management Plan | Manage Communications | Execute | Scope Baseline | Conduct Procurements | Execute | Representation of Uncertainty | Perform Quantitative Risk Analysis | Plan
Communications Management Plan | Manage Communications | Execute | Schedule Baseline | Conduct Procurements | Execute | Data Analysis | Perform Quantitative Risk Analysis | Plan
Stakeholder Engagement Plan | Manage Communications | Execute | Cost Baseline | Conduct Procurements | Execute | Simulations | Perform Quantitative Risk Analysis | Plan
Project Documents | Manage Communications | Execute | Proj Doc Update | Conduct Procurements | Execute | Sensitivity Analysis | Perform Quantitative Risk Analysis | Plan
Change Log | Manage Communications | Execute | Lessons Learned Registerister | Conduct Procurements | Execute | Decision Tree Analysis | Perform Quantitative Risk Analysis | Plan
Issue Log | Manage Communications | Execute | Requirements Documentation | Conduct Procurements | Execute | Influence Diagrams | Perform Quantitative Risk Analysis | Plan
Lessons Learned Register | Manage Communications | Execute | Requirements Traceability Matrix | Conduct Procurements | Execute | Expert Judgement | Plan Risk Responses | Plan
Quality Report | Manage Communications | Execute | Resource Calendars | Conduct Procurements | Execute | Data Gathering | Plan Risk Responses | Plan
Risk Report | Manage Communications | Execute | Risk Register | Conduct Procurements | Execute | Interviews | Plan Risk Responses | Plan
Stakeholder Register | Manage Communications | Execute | Stakeholder Register | Conduct Procurements | Execute | Interpersonal and Team Skills | Plan Risk Responses | Plan
Work Performance Reports | Manage Communications | Execute | OPA Updates | Conduct Procurements | Execute | Facilitation | Plan Risk Responses | Plan
EEF | Manage Communications | Execute | Closed Procurements | Control Procurements | Monitor/Control | Strategies for Threats | Plan Risk Responses | Plan
OPA | Manage Communications | Execute | Work Performance Information | Control Procurements | Monitor/Control | Strategies for Opportunities | Plan Risk Responses | Plan
Project Management Plan | Monitor Communications | Monitor/Control | Procurement Documentationumentation Updates | Control Procurements | Monitor/Control | Contingent Response Strategies | Plan Risk Responses | Plan
Project Documents | Monitor Communications | Monitor/Control | Change Requests | Control Procurements | Monitor/Control | Strategies for Overall Project Risk | Plan Risk Responses | Plan
Work Performance Data | Monitor Communications | Monitor/Control | Project Management Plan Updates | Control Procurements | Monitor/Control | Data Analysis | Plan Risk Responses | Plan
EEF | Monitor Communications | Monitor/Control | Risk Management Plan | Control Procurements | Monitor/Control | Alternative Analysis | Plan Risk Responses | Plan
OPA | Monitor Communications | Monitor/Control | Procurement Management Plan | Control Procurements | Monitor/Control | Cost Benefit Analysis | Plan Risk Responses | Plan
Project Charter | Plan Risk Management | Plan | Schedule Baseline | Control Procurements | Monitor/Control | Decision Making | Plan Risk Responses | Plan
Project Management Plan | Plan Risk Management | Plan | Cost Baseline | Control Procurements | Monitor/Control | Multi-Criteria Dec Analysis | Plan Risk Responses | Plan
All Components | Plan Risk Management | Plan | Proj Doc Update | Control Procurements | Monitor/Control | Expert Judgement | Implement Risk Responses | Execute
Project Documents | Plan Risk Management | Plan | Lessons Learned Registerister | Control Procurements | Monitor/Control | Interpersonal and Team Skills | Implement Risk Responses | Execute
Stakeholder Register | Plan Risk Management | Plan | Resource Requirements | Control Procurements | Monitor/Control | Influencing | Implement Risk Responses | Execute
EEF | Plan Risk Management | Plan | Requirements Traceability Matrix | Control Procurements | Monitor/Control | PMIS | Implement Risk Responses | Execute
OPS | Plan Risk Management | Plan | Risk Register | Control Procurements | Monitor/Control | Data Analysis | Monitor Risks | Monitor/Control
Project Management Plan | Identify Risks | Plan | Stakeholder Register | Control Procurements | Monitor/Control | Technical Performance Analysis | Monitor Risks | Monitor/Control
Requirements Management Plan | Identify Risks | Plan | OPA Updates | Control Procurements | Monitor/Control | Reserve Analysis | Monitor Risks | Monitor/Control
Schedule Management Plan | Identify Risks | Plan | Stakeholder Register | Identify Stakeholders | Initiate | Audits | Monitor Risks | Monitor/Control
Cost Management Plan | Identify Risks | Plan | Change Requests | Identify Stakeholders | Initiate | Meetings | Monitor Risks | Monitor/Control
Resource Management Plan | Identify Risks | Plan | Project Management Plan Updates | Identify Stakeholders | Initiate | Expert Judgement | Plan Procurement Management | Plan
Risk Management Plan | Identify Risks | Plan | Requirements Mgmt Plan | Identify Stakeholders | Initiate | Data Gathering | Plan Procurement Management | Plan
Quality Management Plan | Identify Risks | Plan | Communications Management Plan | Identify Stakeholders | Initiate | Market Research | Plan Procurement Management | Plan
Scope Baseline | Identify Risks | Plan | Risk Management Plan | Identify Stakeholders | Initiate | Data Analysis | Plan Procurement Management | Plan
Cost Baseline | Identify Risks | Plan | Stakeholder Engagement Plan | Identify Stakeholders | Initiate | Make-or-Buy Analysis | Plan Procurement Management | Plan
Project Documents | Identify Risks | Plan | Proj Doc Update | Identify Stakeholders | Initiate | Source Selection Analysis | Plan Procurement Management | Plan
Assumptions Log | Identify Risks | Plan | Assumptions Log | Identify Stakeholders | Initiate | Meetings | Plan Procurement Management | Plan
Cost Estimates | Identify Risks | Plan | Issue Log | Identify Stakeholders | Initiate | Expert Judgement | Conduct Procurements | Execute
Duration Estimates | Identify Risks | Plan | Risk Register | Identify Stakeholders | Initiate | Advertising | Conduct Procurements | Execute
Issue Log | Identify Risks | Plan | Stakeholder Engagement Plan | Plan Stakeholder Engagement | Plan | Bidder Conferences | Conduct Procurements | Execute
Lessons Learned Register | Identify Risks | Plan | Change Requests | Manage Stakeholder Engagement | Execute | Data Analysis | Conduct Procurements | Execute
Requirements Documentation | Identify Risks | Plan | Project Management Plan Updates | Manage Stakeholder Engagement | Execute | Proposal Evaluation | Conduct Procurements | Execute
Resource Requirements | Identify Risks | Plan | Communications Management Plan | Manage Stakeholder Engagement | Execute | Interpersonal and Team Skills | Conduct Procurements | Execute
Stakeholder Register | Identify Risks | Plan | Stakeholder Engagement Plan | Manage Stakeholder Engagement | Execute | Negotiations | Conduct Procurements | Execute
Agreements | Identify Risks | Plan | Proj Doc Update | Manage Stakeholder Engagement | Execute | Expert Judgement | Control Procurements | Monitor/Control
Procurement Documentation | Identify Risks | Plan | Change Log | Manage Stakeholder Engagement | Execute | Claims Administration | Control Procurements | Monitor/Control
EEF | Identify Risks | Plan | Issue Log | Manage Stakeholder Engagement | Execute | Data Analysis | Control Procurements | Monitor/Control
OPA | Identify Risks | Plan | Lessons Learned Registerister | Manage Stakeholder Engagement | Execute | Performance Reviews | Control Procurements | Monitor/Control
Project Management Plan | Perform Qualitative Risk Analysis | Plan | Stakeholder Register | Manage Stakeholder Engagement | Execute | Earned Value Analysis | Control Procurements | Monitor/Control
Risk Management Plan | Perform Qualitative Risk Analysis | Plan | Work Performance Information | Monitor Stakeholder Engagement | Monitor/Control | Trend Analysis | Control Procurements | Monitor/Control
Project Documents | Perform Qualitative Risk Analysis | Plan | Change Requests | Monitor Stakeholder Engagement | Monitor/Control | Inspection | Control Procurements | Monitor/Control
Assumptions Log | Perform Qualitative Risk Analysis | Plan | Project Management Plan Updates | Monitor Stakeholder Engagement | Monitor/Control | Audits | Control Procurements | Monitor/Control
Risk Register | Perform Qualitative Risk Analysis | Plan | Resource Management Plan | Monitor Stakeholder Engagement | Monitor/Control | Expert Judgement | Identify Stakeholders | Initiate
Stakeholder Register | Perform Qualitative Risk Analysis | Plan | Communications Management Plan | Monitor Stakeholder Engagement | Monitor/Control | Data Gathering | Identify Stakeholders | Initiate
EEF | Perform Qualitative Risk Analysis | Plan | Stakeholder Engagement Plan | Monitor Stakeholder Engagement | Monitor/Control | Quesionnaires and Surveys | Identify Stakeholders | Initiate
OPA | Perform Qualitative Risk Analysis | Plan | Proj Doc Update | Monitor Stakeholder Engagement | Monitor/Control | Brainstorming | Identify Stakeholders | Initiate
Project Management Plan | Perform Quantitative Risk Analysis | Plan | Issue Log | Monitor Stakeholder Engagement | Monitor/Control | Data Analysis | Identify Stakeholders | Initiate
Risk Management Plan | Perform Quantitative Risk Analysis | Plan | Lessons Learned Registerister | Monitor Stakeholder Engagement | Monitor/Control | Stakeholder Analysis | Identify Stakeholders | Initiate
Scope Baseline | Perform Quantitative Risk Analysis | Plan | Risk Register | Monitor Stakeholder Engagement | Monitor/Control | Document Analysis | Identify Stakeholders | Initiate
Schedule Baseline | Perform Quantitative Risk Analysis | Plan | Stakeholder Register | Monitor Stakeholder Engagement | Monitor/Control | Data Representation | Identify Stakeholders | Initiate
Cost Baseline | Perform Quantitative Risk Analysis | Plan |  |  |  | Stakeholder Mapping/Prepresentation | Identify Stakeholders | Initiate
Project Documents | Perform Quantitative Risk Analysis | Plan |  |  |  | Meetings | Identify Stakeholders | Initiate
Assumptions Log | Perform Quantitative Risk Analysis | Plan |  |  |  | Expert Judgement | Plan Stakeholder Engagement | Plan
Basis of Estimates | Perform Quantitative Risk Analysis | Plan |  |  |  | Data Gathering | Plan Stakeholder Engagement | Plan
Cost Estimates | Perform Quantitative Risk Analysis | Plan |  |  |  | Benchmarking | Plan Stakeholder Engagement | Plan
Cost Forecasts | Perform Quantitative Risk Analysis | Plan |  |  |  | Data Analysis | Plan Stakeholder Engagement | Plan
Duration Estimates | Perform Quantitative Risk Analysis | Plan |  |  |  | Assumption and Constraint Analysis | Plan Stakeholder Engagement | Plan
Milestone List | Perform Quantitative Risk Analysis | Plan |  |  |  | Root Cause Analysis | Plan Stakeholder Engagement | Plan
Resource Requirements | Perform Quantitative Risk Analysis | Plan |  |  |  | Decision Making | Plan Stakeholder Engagement | Plan
Risk Register | Perform Quantitative Risk Analysis | Plan |  |  |  | Priorities/Ranking | Plan Stakeholder Engagement | Plan
Risk Report | Perform Quantitative Risk Analysis | Plan |  |  |  | Data Representation | Plan Stakeholder Engagement | Plan
Schedule Forecasts | Perform Quantitative Risk Analysis | Plan |  |  |  | Mindmapping | Plan Stakeholder Engagement | Plan
EEF | Perform Quantitative Risk Analysis | Plan |  |  |  | Stakeholder Engagement Assessment Matrix | Plan Stakeholder Engagement | Plan
OPA | Perform Quantitative Risk Analysis | Plan |  |  |  | Meetings | Plan Stakeholder Engagement | Plan
Project Management Plan | Plan Risk Responses | Plan |  |  |  | Expert Judgement | Manage Stakeholder Engagement | Execute
Resource Management Plan | Plan Risk Responses | Plan |  |  |  | Communication Skills | Manage Stakeholder Engagement | Execute
Risk Management Plan | Plan Risk Responses | Plan |  |  |  | Feedback | Manage Stakeholder Engagement | Execute
Cost Baseline | Plan Risk Responses | Plan |  |  |  | Interpersonal and Team Skills | Manage Stakeholder Engagement | Execute
Project Documents | Plan Risk Responses | Plan |  |  |  | Conflict Management | Manage Stakeholder Engagement | Execute
Lessons Learned Register | Plan Risk Responses | Plan |  |  |  | Cultural Awareness | Manage Stakeholder Engagement | Execute
Project Schedule | Plan Risk Responses | Plan |  |  |  | Negotiations | Manage Stakeholder Engagement | Execute
Project Team Assignments | Plan Risk Responses | Plan |  |  |  | Observation/Conversation | Manage Stakeholder Engagement | Execute
Resource Calendars | Plan Risk Responses | Plan |  |  |  | Political Awareness | Manage Stakeholder Engagement | Execute
Risk Register | Plan Risk Responses | Plan |  |  |  | Ground rules | Manage Stakeholder Engagement | Execute
Risk Report | Plan Risk Responses | Plan |  |  |  | Meetings | Manage Stakeholder Engagement | Execute
Stakeholder Register | Plan Risk Responses | Plan |  |  |  | Data Analysis | Monitor Stakeholder Engagement | Monitor/Control
EEF | Plan Risk Responses | Plan |  |  |  | Alternative Analysis | Monitor Stakeholder Engagement | Monitor/Control
OPA | Plan Risk Responses | Plan |  |  |  | Root Cause Analysis | Monitor Stakeholder Engagement | Monitor/Control
Project Management Plan | Implement Risk Responses | Execute |  |  |  | Stakeholder Analysis | Monitor Stakeholder Engagement | Monitor/Control
Risk Management Plan | Implement Risk Responses | Execute |  |  |  | Decision Making | Monitor Stakeholder Engagement | Monitor/Control
Project Documents | Implement Risk Responses | Execute |  |  |  | Multi-Criteria Dec Analysis | Monitor Stakeholder Engagement | Monitor/Control
Lessons Learned Register | Implement Risk Responses | Execute |  |  |  | Voting | Monitor Stakeholder Engagement | Monitor/Control
Risk Register | Implement Risk Responses | Execute |  |  |  | Data Representation | Monitor Stakeholder Engagement | Monitor/Control
Risk Report | Implement Risk Responses | Execute |  |  |  | Stakeholder Engagement Assessment Matrix | Monitor Stakeholder Engagement | Monitor/Control
OPA | Implement Risk Responses | Execute |  |  |  | Communication Skills | Monitor Stakeholder Engagement | Monitor/Control
Project Management Plan | Monitor Risks | Monitor/Control |  |  |  | Feedback | Monitor Stakeholder Engagement | Monitor/Control
Risk Management Plan | Monitor Risks | Monitor/Control |  |  |  | Presentations | Monitor Stakeholder Engagement | Monitor/Control
Project Documents | Monitor Risks | Monitor/Control |  |  |  | Interpersonal and Team Skills | Monitor Stakeholder Engagement | Monitor/Control
Issue Log | Monitor Risks | Monitor/Control |  |  |  | Active Listening | Monitor Stakeholder Engagement | Monitor/Control
Lessons Learned Register | Monitor Risks | Monitor/Control |  |  |  | Cultural Awareness | Monitor Stakeholder Engagement | Monitor/Control
Risk Register | Monitor Risks | Monitor/Control |  |  |  | Leadership | Monitor Stakeholder Engagement | Monitor/Control
Risk Report | Monitor Risks | Monitor/Control |  |  |  | Networking | Monitor Stakeholder Engagement | Monitor/Control
Work Performance Data | Monitor Risks | Monitor/Control |  |  |  | Political Awareness | Monitor Stakeholder Engagement | Monitor/Control
Work Performance Reports | Monitor Risks | Monitor/Control |  |  |  | Meetings | Monitor Stakeholder Engagement | Monitor/Control
Project Charter | Plan Procurement Management | Plan
Business documents | Plan Procurement Management | Plan
Business Case | Plan Procurement Management | Plan
Benefits Management Plan | Plan Procurement Management | Plan
Project Management Plan | Plan Procurement Management | Plan
Scope Management Plan | Plan Procurement Management | Plan
Quality Management Plan | Plan Procurement Management | Plan
Resource Management Plan | Plan Procurement Management | Plan
Scope Baseline | Plan Procurement Management | Plan
Project Documents | Plan Procurement Management | Plan
Milestone List | Plan Procurement Management | Plan
Project Team Assignments | Plan Procurement Management | Plan
Requirements Documentation | Plan Procurement Management | Plan
Requirements Traceability Matrix | Plan Procurement Management | Plan
Resource Requirements | Plan Procurement Management | Plan
Risk Register | Plan Procurement Management | Plan
Stakeholder Register | Plan Procurement Management | Plan
EEF | Plan Procurement Management | Plan
OPA | Plan Procurement Management | Plan
Project Management Plan | Conduct Procurements | Execute
Scope Management Plan | Conduct Procurements | Execute
Requirements Management Plan | Conduct Procurements | Execute
Communications Management Plan | Conduct Procurements | Execute
Risk Management Plan | Conduct Procurements | Execute
Procurement Management Plan | Conduct Procurements | Execute
Configuration Management Plan | Conduct Procurements | Execute
Cost Baseline | Conduct Procurements | Execute
Project Documents | Conduct Procurements | Execute
Lessons Learned Register | Conduct Procurements | Execute
Project Schedule | Conduct Procurements | Execute
Requirements Documentation | Conduct Procurements | Execute
Risk Register | Conduct Procurements | Execute
Stakeholder Register | Conduct Procurements | Execute
Procurement Documentationumentation | Conduct Procurements | Execute
Seller Proposals | Conduct Procurements | Execute
EEF | Conduct Procurements | Execute
OPA | Conduct Procurements | Execute
Project Management Plan | Control Procurements | Monitor/Control
Requirements Management Plan | Control Procurements | Monitor/Control
Risk Management Plan | Control Procurements | Monitor/Control
Procurement Management Plan | Control Procurements | Monitor/Control
Change Management Plan | Control Procurements | Monitor/Control
Schedule Baseline | Control Procurements | Monitor/Control
Project Documents | Control Procurements | Monitor/Control
Assumptions Log | Control Procurements | Monitor/Control
Lessons Learned Register | Control Procurements | Monitor/Control
Milestone List | Control Procurements | Monitor/Control
Quality Reports | Control Procurements | Monitor/Control
Requirements Documentation | Control Procurements | Monitor/Control
Requirements Traceability Matrix | Control Procurements | Monitor/Control
Risk Register | Control Procurements | Monitor/Control
Stakeholder Register | Control Procurements | Monitor/Control
Agreements | Control Procurements | Monitor/Control
Procurement Documentationumentation | Control Procurements | Monitor/Control
Approved Change Request | Control Procurements | Monitor/Control
Work Performance Data | Control Procurements | Monitor/Control
EEF | Control Procurements | Monitor/Control
OPA | Control Procurements | Monitor/Control
Project Charter | Identify Stakeholders | Initiate
Business documents | Identify Stakeholders | Initiate
Business Case | Identify Stakeholders | Initiate
Benefits Management Plan | Identify Stakeholders | Initiate
Project Management Plan | Identify Stakeholders | Initiate
Communications Management Plan | Identify Stakeholders | Initiate
Stakeholder Engagement Plan | Identify Stakeholders | Initiate
Project Documents | Identify Stakeholders | Initiate
Change Log | Identify Stakeholders | Initiate
Issue Log | Identify Stakeholders | Initiate
Requirements Documentation | Identify Stakeholders | Initiate
Agreements | Identify Stakeholders | Initiate
EEF | Identify Stakeholders | Initiate
OPA | Identify Stakeholders | Initiate
Project Charter | Plan Stakeholder Engagement | Plan
Project Management Plan | Plan Stakeholder Engagement | Plan
Resource Management Plan | Plan Stakeholder Engagement | Plan
Communications Management Plan | Plan Stakeholder Engagement | Plan
Risk Management Plan | Plan Stakeholder Engagement | Plan
Project Documents | Plan Stakeholder Engagement | Plan
Assumptions Log | Plan Stakeholder Engagement | Plan
Change Log | Plan Stakeholder Engagement | Plan
Issue Log | Plan Stakeholder Engagement | Plan
Project Schedule | Plan Stakeholder Engagement | Plan
Risk Register | Plan Stakeholder Engagement | Plan
Stakeholder Register | Plan Stakeholder Engagement | Plan
Agreements | Plan Stakeholder Engagement | Plan
EEF | Plan Stakeholder Engagement | Plan
OPA | Plan Stakeholder Engagement | Plan
Project Management Plan | Manage Stakeholder Engagement | Execute
Communications Management Plan | Manage Stakeholder Engagement | Execute
Risk Management Plan | Manage Stakeholder Engagement | Execute
Stakeholder Engagement Plan | Manage Stakeholder Engagement | Execute
Project Documents | Manage Stakeholder Engagement | Execute
Change Log | Manage Stakeholder Engagement | Execute
Issue Log | Manage Stakeholder Engagement | Execute
Lessons Learned Register | Manage Stakeholder Engagement | Execute
Stakeholder Register | Manage Stakeholder Engagement | Execute
EEF | Manage Stakeholder Engagement | Execute
OPA | Manage Stakeholder Engagement | Execute
Project Management Plan | Monitor Stakeholder Engagement | Monitor/Control
Resource Management Plan | Monitor Stakeholder Engagement | Monitor/Control
Communications Management Plan | Monitor Stakeholder Engagement | Monitor/Control
Stakeholder Engagement Plan | Monitor Stakeholder Engagement | Monitor/Control
Project Documents | Monitor Stakeholder Engagement | Monitor/Control
Issue Log | Monitor Stakeholder Engagement | Monitor/Control
Lessons Learned Register | Monitor Stakeholder Engagement | Monitor/Control
Project Communications | Monitor Stakeholder Engagement | Monitor/Control
Risk Register | Monitor Stakeholder Engagement | Monitor/Control
Stakeholder Register | Monitor Stakeholder Engagement | Monitor/Control
Work Performance Data | Monitor Stakeholder Engagement | Monitor/Control
EEF | Monitor Stakeholder Engagement | Monitor/Control
OPA | Monitor Stakeholder Engagement | Monitor/Control