## 6th April 2025 - Agenda
SOMERSET PLACE SUBDIVISION - TROY
127 Homes
Meeting Date and Time | 04-06-2025, 10am to 12pm | Meeting Location: | 1679 Greenwich Dr, Troy
Meeting Organizer: | Sunita Kore | Meeting Notes: | Sunita Kore
Expected Attendees
Sunita Kore | David Rusing | James Guisinger | Nabil Hassan
Chandrakanth Kore | Jalal Joulan | Dale Pickett | Eric Zawicki (Riverplace Subdivision President)
Attendees
Sunita Kore | Dale Pickett | James Guisinger | Chandrakanth Kore
Chandrakanth Kore | Jalal Joulan | Nabil Hassan | David Rusing
Agenda
Meet & Greet with Riverplace Subdivision
Distribution of Pond Related Expenses with Riverplace Subdivision
Other Items

## Minutes of Meeting - 6th April
SOMERSET PLACE SUBDIVISION - TROY
127 Homes
Meeting Date and Time | 04-06-2025, 10am to 12pm | Meeting Location: | 1679 Greenwich Dr, Troy
Meeting Organizer: | Sunita Kore | Meeting Notes: | Sunita Kore
Expected Attendees
Sunita Kore | David Rusing | James Guisinger | Nabil Hassan
Chandrakanth Kore | Jalal Joulan | Dale Pickett | Eric Zawicki (Riverplace Subdivision President)
Attendees
Sunita Kore | Dale Pickett | James Guisinger | Chandrakanth Kore
Chandrakanth Kore | Jalal Joulan | Nabil Hassan | David Rusing
Minutes of Meeting
Other Items
Meet & Greet with Riverplace Subdivision | Meet & Greet with Riverplace Subdivision was cancelled as Riverplace Board Members did not show up for the meeting
Distribution of Pond Related Expenses with Riverplace Subdivision | Distribution of Pond related expenses were not discussed in details as Riverplace Board Members did not attend the meeting. Historical documents in regards to expense sharing is attached to the minutes of the meeting.
Fenwick Drive Entrance Maintenance | Details in regards to the maintenance of the Fenwick Drive entrance was discussed in detail. Plan of action is as followed;
ACTION - Jim, Dave & Jalal - Get quote on clean up of the Fenwick Drive entrance. All the trees, shrubs, roots, etc. needs to be removed & area cleaned up for plantation. Once a time is fixed please inform all members of the day & time - so that we can meet at the entrance and any questions or queries can be clarified and decision can be made asap.
ACTION ALL BOARD MEMBERS - Please explore and come out with a plantation idea for the Fenwick Drive. So that plantation can be started as soon as the area is cleared and prepped.
Financial Statement | Dave has gotten all access to the Subdivision bank.
Bank statements and current financial statement will be sent out by Dave in the coming week.
Reiterate to all service providers to provide timely invoices
Fifth Third bank is going to reimburse all the charges in regards to the total account balance falling below $50,000
Mailbox Replacement | Final decision in regards to the Mailbox to be finalised at the 2025 Annual General Meeting
Boards current proposal - Is to get quote from Mailbox suppliers for the mailbox for the following numbers - 2 Stand Mailbox - (2) - 3 Stand mailbox - (19) - 4 Stand mailbox - (14) Get a quote from handyman in regards to installation. Based on the figures Board to discuss how to implement the project. ACTION - All Board Members - Quotes need to be got by end of April.
Annual General meeting - AGM Agenda - Annual Get Together | AGM to be held on 17th May 2025 from 10am to 12pm - Troy Community Center
Agenda
ACTION - Sunita to explore and book the venue for the AGM
Other Matters | ACTION - Jim & Dale to get all invoices to be updated with Dave Ruising's address & contact details
ACTION - Dave to contact Insurance Company to find Contract details
Somerset Place Subdivision has 127 Homes & Riverplace Place Subdivision has 38 Homes