## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Executive Ledger
| Table 1 | Executive Ledger
Road Contracts
| Table 1 | Road Contracts
DLNR Pohoiki
| Table 1 | DLNR Pohoiki
Round 3 Grants
| Table 1 | Round 3 Grants
Records Gaps
| Table 1 | Records Gaps
Dashboard
| Table 1 | Dashboard
Definitions
| Table 1 | Definitions

## Executive Ledger
ID | Sector | Project / Program | Agency | Geography | Funding source / authority | Authorized / funding envelope | Contract / award | Verified expenditure | Implied contract use | Reimbursement received | Physical status | Official % complete | Target / actual completion | Evidence class | What is still missing | Source date | Source URL | Notes
A01 | State recovery | Act 9 Kīlauea recovery subsidy | State B&F / County of Hawaiʻi | Puna | Hawaiʻi Act 9 (2019), §1 | 20000000 |  |  |  |  | Multiple downstream recovery uses; no consolidated expenditure ledger located |  |  | Allocation only / reporting gap | Monthly expenditure reports required by Act 9 §3; transaction ledger; remaining balance | 2019-04-16 | https://data.capitol.hawaii.gov/sessions/sessionlaws/AllIndex/SLH2019_Complete.pdf | Act 9 requires the County to report monthly expenditures to State B&F.
A02 | State recovery | Act 9 Kīlauea recovery loan / federal match | State B&F / County of Hawaiʻi | Puna | Hawaiʻi Act 9 (2019), §2 | 40000000 |  |  |  |  | Used as match mechanism for non-state recovery funds; current draw/repayment ledger not located |  |  | Allocation only / reporting gap | Loan draw schedule, terms, repayments/waivers, monthly expenditure reports | 2019-04-16 | https://data.capitol.hawaii.gov/sessions/sessionlaws/AllIndex/SLH2019_Complete.pdf | Do not add mechanically to project awards; much of it functions as match and can overlap project totals.
R01 | Roads + water | Highway 137A: Hwy 132 / Four Corners to Pohoiki Road | County DPW / DWS | Lower Puna | FEMA-4366-DR-HI Project #46851 PW00055/53 + State match |  | 17796690 |  |  |  | Construction in progress; grading and waterline work reported |  | Q3 2026 | Contract verified; payment gap | Payment applications, invoices, change orders, retainage, FEMA reimbursements, current physical % complete | 2025-08-29 | https://records.hawaiicounty.gov/weblink/1/edoc/150708/2025_09_02_News_Release_Restoration_of_Pohoiki_Road_Begins.pdf | Isemoto Contracting Co. Ltd.; base bid/contract ceiling from County bid record.
R02 | Roads + water | Upper/Lower Pohoiki Road + Leilani Avenue | County DPW / DWS | Lower Puna | FEMA-4366-DR-HI Project #46851 PW00055/53 + State match |  | 32080630.5 |  |  |  | Construction began/staging Aug. 2025; 4.5 miles roadway plus waterline to Isaac Hale |  | Q2 2027 | Contract verified; payment gap | Payment applications, invoices, change orders, retainage, FEMA reimbursements, current physical % complete | 2025-08-29 | https://records.hawaiicounty.gov/weblink/1/edoc/150708/2025_09_02_News_Release_Restoration_of_Pohoiki_Road_Begins.pdf | Nan, Inc.; exact base bid from County bid recap.
R03 | Roads | Construction management for lava-inundated roads | County DPW | Lower Puna | FEMA-4366-DR-HI Project #46851 PW00055 |  | 4400000 |  |  |  | Construction management active for reconstruction program |  |  | Professional-services award; payment gap | Consultant invoices, amendments, paid-to-date, remaining encumbrance | 2024-06-17 | https://records.hawaiicounty.gov/WebLink/1/edoc/136528/Professional%20Services%20Awarded%202023-2024%20-%2020240708.pdf | Weley R. Segawa & Associates, Inc.; County contract C.011809.
R04 | Roads | FEMA public-road damage agreement | FEMA / Hawaiʻi EMA / County DPW | Lower Puna | FEMA Public Assistance reimbursement (75%) + State local match (25%) | 82000000 |  |  |  |  | Program envelope; individual road projects at different stages |  |  | Funding envelope only | Project-level FEMA obligations, draws/reimbursements, deobligations, closeout balances | Current county funding page | https://recovery.hawaiicounty.gov/resources/funding | County reports $61.5m federal share + $20.5m State match. Reimbursement basis.
R05 | Roads | Highway 132 restoration | County DPW / FHWA | Lower Puna | Federal Highway Administration | 5750000 |  |  |  |  | Completed and reopened in 2019 | 100% | 2019 | Physical completion verified; spend gap | Final contract amount, change orders and actual payments/reimbursements | Current county funding page | https://recovery.hawaiicounty.gov/resources/funding | Funding amount should not be treated automatically as final actual cost.
W01 | Water | Lower Puna water infrastructure recovery envelope | County DWS / FEMA | Lower Puna | FEMA Public Assistance (75%) + State match (25%) | 40000000 |  |  |  |  | Some original Kapoho system will not be rebuilt; funds redirected to alternative Puna water projects |  |  | Funding envelope only | Project-by-project obligations, DWS contracts, invoices, FEMA reimbursements and remaining balance | Current county funding page | https://recovery.hawaiicounty.gov/resources/funding | County reports about $30m FEMA + $10m State match.
P01 | Parks | Isaac Kepoʻokalani Hale Beach Park improvements | County Parks / FEMA | Pohoiki, Puna | FEMA + State recovery funds | 4900000 |  |  |  |  | Planning and design in progress; final design, EA, preservation plan and AIS under review |  |  | Design-stage / spend gap | Design consultant contract and invoices; construction estimate; bid date; FEMA reimbursements | 2026-07-16 | https://www.parks.hawaiicounty.gov/office-of-the-director/parks-projects | The $4.9m is the broader FEMA/State parks recovery agreement, not necessarily the final Isaac Hale construction cost.
D01 | Ocean access | Pohoiki Boat Ramp excavation and dredging — Goodfellow | DLNR DOBOR | Pohoiki, Puna | State/FEMA capital funding lines in DLNR contract table | 9580000 | 9580000 |  | 7142404 |  | Excavation/dredging contract substantially drawn by Dec. 1, 2025; launch ramp remains closed until further notice |  |  | Contract balance allows implied use | Final payment ledger, amendments/change orders, retainage, FEMA reimbursement, corrective scope after sediment refill | 2025-12-01 | https://data.capitol.hawaii.gov/CommitteeFiles/HOUSE/FIN/FINfiles/2026_LNR.pdf | DLNR lists four funding lines totaling $9.58m with $2,437,596 outstanding. Implied use = max value minus outstanding balance; not explicitly labeled cash paid.
D02 | Ocean access | Pohoiki Boat Ramp dredging/hazard mitigation — Limtiaco consulting | DLNR DOBOR | Pohoiki, Puna | DLNR LNR801 contract funding lines | 780522 | 780522 |  | 619517.66 |  | Consulting/design work associated with Pohoiki dredging/hazard mitigation |  |  | Contract balance allows implied use | Final consultant invoices/closeout and precise scope by funding line | 2025-12-01 | https://data.capitol.hawaii.gov/CommitteeFiles/HOUSE/FIN/FINfiles/2026_LNR.pdf | Four Limtiaco funding lines total $780,522; outstanding $161,004.34; implied use $619,517.66.
H01 | Housing | CDBG-DR Voluntary Housing Buyout Program | County Housing / HUD | Eruption-impacted Puna | HUD CDBG-DR | 100534000 |  | 87930274.3 |  |  | 693 closings completed; 13 applications active; no primary-home applications active |  |  | Explicit expenditure verified | Final QPR/closeout, remaining program balance, disposition/open-space management costs | 2026-07-29 | https://recovery.hawaiicounty.gov/resources/housing-buyout-program | HUD total CDBG-DR allocation is $107.561m; current buyout program budget listed as $100.534m.
G01 | Community grants | Kīlauea Recovery Grant Program — Round 1 | County Disaster Recovery / Planning | Puna | State recovery allocation + donations |  | 3700000 |  |  |  | Awards made; public page does not publish a consolidated paid-to-date/closeout ledger |  |  | Award only / closeout gap | Grant agreements, installment payments, final expenditure reports, closeouts, unspent returns | County recovery page | https://recovery.hawaiicounty.gov/resources/recovery-grants/kilauearecoverygrantprogram | One listed $104,500 award was declined; reconcile before treating $3.7m as spent.
G02 | Community grants | Kīlauea Recovery Grant Program — Round 2 | County Disaster Recovery / Planning | Puna | State recovery allocation + donations |  | 3293400 |  |  |  | 16 grants awarded; no consolidated payment-to-date or closeout ledger located |  |  | Award only / closeout gap | Grant agreements, installment payments, progress/final reports, closeouts, unspent returns | 2024-07 | https://recovery.hawaiicounty.gov/resources/recovery-grants/kilauearecoverygrantprogram | Award total verified; expenditure is not.
G03 | Community grants | Kīlauea Recovery Grant Program — Round 3 | County Planning / Disaster Recovery | Puna | State recovery allocation + donations |  | 5977773 |  |  |  | Awards approved by County Council March 4, 2026; projects entering implementation |  |  | Award only / closeout gap | Executed grant agreements, installments actually paid, procurement records for capital subprojects, closeouts | 2026-03-04 | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493 | Resolution 459-26 (Draft 2) authorizes $5,977,773.
G04 | Community grants | Puna Strong — public recovery share | County + Hawaiʻi Community Foundation | Puna | County recovery funds sourced from State Legislature | 1200000 |  |  |  |  | Multiple rounds of nonprofit grants/technical assistance |  |  | Program funding summary / spend gap | County contribution paid-to-date by grant, HCF passthrough ledger, closeouts | Current county recovery page | https://recovery.hawaiicounty.gov/resources/recovery-grants | County page says $1.2m public recovery funding plus $400k Oak/HCF; keep private share separate.
E01 | Economic recovery | Puna wastewater solutions planning | County / U.S. EDA | Puna town centers | U.S. Economic Development Administration | 2250000 | 2250000 |  |  |  | Planning/evaluation award, not sewer construction |  |  | Award only / spend gap | Grant drawdowns, consultant contracts/invoices, deliverables, remaining balance | Current county funding page | https://recovery.hawaiicounty.gov/resources/funding | Do not describe this as completed wastewater infrastructure.
E02 | Economic recovery | Economic Recovery Plan | County / U.S. EDA | Puna | U.S. Economic Development Administration | 250000 | 250000 |  |  |  | Planning award |  |  | Award only / spend gap | Grant drawdowns, consultant payments, final deliverable and closeout | Current county funding page | https://recovery.hawaiicounty.gov/resources/funding
E03 | Economic recovery | Rural Placemaking Innovation Challenge | County / USDA | Puna | USDA | 225000 | 225000 |  |  |  | Community development/planning award |  |  | Award only / spend gap | Drawdowns, contracts, deliverables and closeout | Current county funding page | https://recovery.hawaiicounty.gov/resources/funding

## Road Contracts
Project | County job / FEMA project | Prime / consultant | Base contract / award | Verified paid-to-date | Change orders located | Physical status | Official % complete | Completion target | Primary source | Audit note
Highway 137A (Hwy 132 to Pohoiki) | E-4523 / FEMA #46851 PW00055/53 | Isemoto Contracting Co. Ltd. | 17796690 |  | Not yet reconciled | Construction in progress; grading and waterline work reported |  | Q3 2026 | https://records.hawaiicounty.gov/weblink/1/edoc/130213/E-4523%20-%20Bid%20Results%20(2).pdf | Base amount verified; payment applications and FEMA reimbursement draws are critical missing records.
Upper/Lower Pohoiki + Leilani | E-4523A / FEMA #46851 PW00055/53 | Nan, Inc. | 32080630.5 |  | Not yet reconciled | Construction underway; notice to proceed/staging Aug. 2025 |  | Q2 2027 | https://records.hawaiicounty.gov/WebLink/1/edoc/142266/E-4523A%20-%20Bid%20Results%20(2).pdf | Base amount verified; later change orders/payment estimates must be added.
Construction management | C.011809 / FEMA #46851 PW00055 | Weley R. Segawa & Associates, Inc. | 4400000 |  | Not yet reconciled | CM services for lava-inundated roads program |  |  | https://records.hawaiicounty.gov/WebLink/1/edoc/136528/Professional%20Services%20Awarded%202023-2024%20-%2020240708.pdf | Professional-services award is not an expenditure.

## DLNR Pohoiki
Vendor / line | MOF | Max value | Outstanding balance | Implied used | As-of date | Project | Source URL | Interpretive caution
Goodfellow Bros. — line 1 | A | 5400000 | 190230 | 5209770 | 2025-12-01 | Pohoiki boat ramp excavation/dredging | https://data.capitol.hawaii.gov/CommitteeFiles/HOUSE/FIN/FINfiles/2026_LNR.pdf | Max minus outstanding is an inference, not a column labeled cash paid.
Goodfellow Bros. — line 2 | C | 1245000 | 1228174 | 16826 | 2025-12-01 | Pohoiki boat ramp excavation/dredging | https://data.capitol.hawaii.gov/CommitteeFiles/HOUSE/FIN/FINfiles/2026_LNR.pdf
Goodfellow Bros. — line 3 | B | 2635000 | 719192 | 1915808 | 2025-12-01 | Pohoiki boat ramp excavation/dredging | https://data.capitol.hawaii.gov/CommitteeFiles/HOUSE/FIN/FINfiles/2026_LNR.pdf
Goodfellow Bros. — line 4 | B | 300000 | 300000 | 0 | 2025-12-01 | Pohoiki boat ramp excavation/dredging | https://data.capitol.hawaii.gov/CommitteeFiles/HOUSE/FIN/FINfiles/2026_LNR.pdf | Potential amendment/additional line; table max totals $9.58m rather than initial $9.28m award.
Limtiaco — line 1 | C | 402691 | 15927.5 | 386763.5 | 2025-12-01 | Pohoiki dredging/hazard mitigation consulting | https://data.capitol.hawaii.gov/CommitteeFiles/HOUSE/FIN/FINfiles/2026_LNR.pdf
Limtiaco — line 2 | C | 234409 | 10794.88 | 223614.12 | 2025-12-01 | Pohoiki dredging/hazard mitigation consulting | https://data.capitol.hawaii.gov/CommitteeFiles/HOUSE/FIN/FINfiles/2026_LNR.pdf
Limtiaco — line 3 | C | 20000 | 10860.16 | 9139.84 | 2025-12-01 | Pohoiki dredging/hazard mitigation consulting | https://data.capitol.hawaii.gov/CommitteeFiles/HOUSE/FIN/FINfiles/2026_LNR.pdf
Limtiaco — line 4 | B | 123422 | 123421.8 | 0.2 | 2025-12-01 | Pohoiki dredging/hazard mitigation consulting | https://data.capitol.hawaii.gov/CommitteeFiles/HOUSE/FIN/FINfiles/2026_LNR.pdf
| Subtotal | Max value | Outstanding | Implied used
| Goodfellow | 9580000 | 2437596 | 7142404
| Limtiaco | 780522 | 161004.34 | 619517.66

## Round 3 Grants
Category | Organization | Project | Award | Paid to date | Closeout status | Source URL
Capital | Mālama O Puna | Vacationland Road Restoration | 500000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Capital | Hawaiʻi's Volcano Circus | Post-Kīlauea Eruption Restoration of SPACE | 500000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Capital | Puna Rising ʻOhana | Leilani Road Restoration | 500000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Capital | Hoʻoulu Lāhui | Nani Mau Noho Paʻa — subdivision/campus site acquisition | 475000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Capital | Arts and Sciences Center | ASC Campus Expansion — grading/site preparation | 434000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Capital | Mālama O Puna | Hawaiian Shores Water Resiliency Project | 215600 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Capital | Pāhoa Lava Zone Museum | Railroad Avenue Restoration | 203887 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Capital | Mālama O Puna | Kapoho Kai Water System Restoration | 140940 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Capital | SHAC Foundation | Infrastructure for Floriculture Workforce Development | 123626 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Capital | Pāhoa Lava Zone Museum | Holo Lio Road Restoration, Part 2 | 81991 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Capital | Pāhoa Lava Zone Museum | Mālama Road Restoration | 32000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Economic | ʻO Makuʻu Ke Kahua Community Center | ʻO Makuʻu Māla & Farm-to-Market Program | 400000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Economic | SHAC Foundation | Orchid Floriculture Workforce Development | 376373 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Economic | Neighborhood Place of Puna | Puna ʻŌpio Hub | 352007 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Economic | Kupu | Kupu ʻĀina Corps | 300000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Economic | Mālama O Puna | Pāhoa Shared Use Kitchen | 202000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Economic | Pāhoa Lava Zone Museum | Hale Hālāwai O Puna, Phase 2 | 200000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Economic | Puna Rising ʻOhana | ʻIolani Farm Restoration | 69606 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Resilience | Hawaiʻi Environmental Restoration | Puna Perfect Project | 236438 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Resilience | The Food Basket | Kōkua Harvest | 220416 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Resilience | Hawaiʻi Volcano Education & Resilience Institute | Community Resilience / youth, AI, social media and volcano education | 146889 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Resilience | Aloha ʻĪlio Rescue | Puna Pet Support for Community Recovery | 125000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Resilience | Hawaiʻi's Volcano Circus | Red Road Resilience Outreach | 100000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
Resilience | Hawaiʻi's Volcano Circus | Red Road All Communities Disaster Initiative | 42000 |  | Not published in consolidated ledger | https://records.hawaiicounty.gov/WebLink/DocView.aspx?dbid=0&id=1125493
|  |  | Round 3 total | 5977773

## Records Gaps
Priority | Records holder | Record set to obtain | Why it matters | Key identifiers / scope
1 | Hawaiʻi County Finance / Controller | General-ledger transactions, encumbrances, warrants/ACH and vendor payment detail for Act 9 recovery funds from 2019-present | Converts the State's $20m subsidy and $40m loan from appropriations into an auditable cash ledger. | Act 9 (2019); SUB301; all Puna/Kīlauea recovery fund/project codes; include reversals and transfers.
2 | State Department of Budget & Finance | Every monthly expenditure report submitted by Hawaiʻi County under Act 9 §3, plus loan draw/repayment/waiver records | The Legislature explicitly required monthly expenditure reporting; this should be the cleanest State-side audit trail. | Act 9, HB 1180, approved Apr. 16, 2019.
3 | Hawaiʻi County DPW / Finance | All pay estimates, invoices, change orders, retainage and payments for E-4523 and E-4523A | These are the two largest active construction contracts and currently lack public paid-to-date figures. | E-4523 Isemoto $17,796,690; E-4523A Nan $32,080,630.50; FEMA #46851 PW00055/53.
4 | Hawaiʻi County DPW / Finance | All invoices, amendments and payments for construction-management contract C.011809 | Adds soft costs to the road recovery bill and tests whether the $4.4m ceiling has changed. | Weley R. Segawa & Associates; $4.4m award; FEMA #46851 PW00055.
5 | FEMA / HI-EMA / County | Obligation history, reimbursement draws, deobligations and closeout status for FEMA #46851 PW00055/53 and related water/parks PWs | County infrastructure pages publish federal shares but not cash reimbursements actually received. | DR-4366-HI; Project #46851; PW00055/53; roads, water and parks.
6 | County Department of Water Supply | Contracts, invoices and reimbursements for replacement/alternative Lower Puna water projects | The Kapoho network is not being restored as originally configured, so redirected recovery money must be traced project by project. | Pohoiki/Isaac Hale waterline; Highway 137 water work; Kapoho alternatives.
7 | County Parks & Recreation / Finance | Isaac Hale design contract, amendments/invoices, FEMA project worksheet, current construction estimate and procurement schedule | Eight years after the eruption, the principal park reconstruction remains in design; actual design spending is not published. | Isaac Kepoʻokalani Hale Beach Park; Limtiaco Consulting Group.
8 | DLNR / DOBOR | Goodfellow final contract ledger, all amendments/change orders, invoices, retainage, FEMA share and corrective plan for Pohoiki ramp | DLNR's Dec. 1, 2025 table allows an implied $7.142m used, but not a definitive cash-paid figure; ramp remains closed. | Pohoiki Boat Ramp; Goodfellow Bros.; four LNR801 funding lines.
9 | County Disaster Recovery / Planning | Executed agreements, installment payment history, progress/final reports and closeouts for Kīlauea Recovery Grant Rounds 1–3 | Award totals are public; expenditure and project completion are not consolidated. | Rounds 1 ($3.7m), 2 ($3.2934m), 3 ($5.977773m).
10 | County + Hawaiʻi Community Foundation | Puna Strong public-fund contribution ledger and grant closeouts | Separates the $1.2m State-derived County recovery share from private philanthropy and verifies what was actually spent. | Puna Strong; County recovery share $1.2m; private share reported separately.

## Dashboard
PUNA 2018 ERUPTION RECOVERY — AUDIT LEDGER
Key measure | Amount / status | What the ledger proves so far
HUD buyout — explicit expenditure | 87930274.3 | 1. Puna recovery money cannot be represented by one grand total without double-counting. 2. The clearest current cash figure is the HUD buyout program: $87.93 million explicitly expended. 3. The two principal road contracts total $49.877 million before change orders, plus a $4.4 million construction-management award, but public paid-to-date figures were not located. 4. DLNR's contract table exposes max value and outstanding balance, allowing an auditable implied-use calculation for Pohoiki. 5. The largest accountability gap is the absence of a public transaction ledger tying Act 9 money, County vendor payments and FEMA reimbursements to physical completion.
Active road construction base contracts | 49877320.5
Road construction-management award | 4400000
DLNR Pohoiki Goodfellow — implied use (12/1/25) | 7142404
DLNR Pohoiki Limtiaco — implied use (12/1/25) | 619517.66
Act 9 monthly expenditure reports publicly located | NO — critical records gap
IMPORTANT: “Unknown” is not $0. Award, obligation, payment, reimbursement and construction completion are separate stages.

## Definitions
PUNA RECOVERY LEDGER — ACCOUNTING DEFINITIONS
Term | Meaning used in this workbook
Appropriated / Authorized | Legislature or agency made money legally available. This is not an expenditure.
Awarded | A grant or contract was approved for a recipient/vendor. It may not yet have been paid.
Obligated / Encumbered | Money is reserved against a contract or grant agreement. It is not necessarily cash out the door.
Verified expenditure | A source explicitly reports an expenditure/payment amount.
Implied contract use | Calculated as reported contract max value minus reported outstanding balance. It is not treated as definitive cash paid.
Reimbursed | A federal/state agency repaid eligible costs already incurred. Reimbursement should be tracked separately from vendor payments.
Physical completion | What is actually built/open/usable. Financial completion and physical completion are not the same thing.
Evidence rule | Blank means unknown—not zero. The workbook does not invent a paid-to-date figure when the public record publishes only an award or ceiling.
As-of date | August 24, 2026, except where a source has an earlier explicit reporting date.