## Sheet1
SECTION: SUPPLIER LEAD-TIME MATRIX
Component ¦ Category ¦ Lead Time (Weeks) ¦ Supplier Type ¦ Notes
---------------------------------------------------------------------------------------------------------------
DTA-C Hybrid Mass-Ring Cores ¦ Long-Lead ¦ 14–18 ¦ Precision Machining ¦ Critical path item
CF-PB Structural Composites ¦ Long-Lead ¦ 16–22 ¦ Aerospace Composites ¦ Fuselage + spine
Ball4D Harmonic Spine Materials ¦ Long-Lead ¦ 12–16 ¦ Specialty Metals ¦ Central wiring trunk
Gyro Stabilization Hardware ¦ Long-Lead ¦ 10–14 ¦ Marine/Aero Hybrid ¦ Belly-mounted gyro loop
Acoustic Tubular Spine Components ¦ Long-Lead ¦ 8–12 ¦ Acoustic Systems ¦ Resonance + ambiance
Staroof Dome Glass + Frame ¦ Mid-Lead ¦ 8–10 ¦ Aerospace Glassworks ¦ Installed last
Dual-Sphere Pedestal Mounts ¦ Mid-Lead ¦ 8–12 ¦ Precision Fabrication ¦ Cockpit core
Captain’s Chairs ¦ Mid-Lead ¦ 6–10 ¦ Aviation Interiors ¦ Gulfstream geometry
Wrap-Around CVG Mini-Settee ¦ Mid-Lead ¦ 6–8 ¦ Marine Upholstery ¦ Blue-water inspired
Spiral Staircase Assembly ¦ Mid-Lead ¦ 8–12 ¦ Structural Fabricator ¦ Cabin access
Mist-Halo Ambiance Bus Hardware ¦ Short-Lead ¦ 3–5 ¦ Environmental Systems ¦ Lighting + mist
Optical-Weight Sync Line ¦ Short-Lead ¦ 2–4 ¦ Electronics ¦ Latency control
Cockpit Electronics + Displays ¦ Short-Lead ¦ 4–6 ¦ Avionics Supplier ¦ Command suite
Interior Lighting + Trim ¦ Short-Lead ¦ 3–5 ¦ Cabin Interiors ¦ Final finish
SECTION: ASSEMBLY TIMELINE
Phase ¦ Duration (Weeks) ¦ Dependencies ¦ Notes
---------------------------------------------------------------------------------------------------------
Structural Assembly ¦ 6–8 ¦ CF-PB composites, gyro hardware ¦ Fuselage + belly spine
Cockpit Assembly ¦ 4–6 ¦ Pedestal mounts, chairs, settee ¦ Dual-sphere integration
Systems Integration ¦ 8–12 ¦ Wiring, Ball4D spine, avionics ¦ Critical path
Interior + Staroof ¦ 4–6 ¦ Dome glass, cabin trim ¦ Installed last
Testing + Certification Prep ¦ 12–20 ¦ All systems installed ¦ Structural + electrical
SECTION: TOTAL PROGRAM TIMELINE
Scenario ¦ Total Weeks ¦ Notes
-------------------------------------------------------
Best Case ¦ 48–56 ¦ No supplier slips
Standard ¦ 60–72 ¦ Typical aerospace cycle
Extended ¦ 72–90 ¦ Long-lead delays
SECTION: SUPPLY CHAIN DECISION MAP
Decision Area ¦ Strategy
---------------------------------------------------------------
Long-Lead Supplier Lock ¦ Secure DTA-C, CF-PB, Ball4D early
Parallel Fabrication ¦ Composites + mass-ring machining
Early Wiring Routing ¦ Install acoustic + sync lines early
Pedestal Pre-Interior Install ¦ Avoid rework, maintain alignment
Staroof Dome Last ¦ Prevent damage during assembly