## Submittal Log
Submittal Log
Project: |  |  |  | Work Order /contract #: |  |  |  | Last update: | From | Start date
[9 empty] | To | Current date
EMPLOYEE INFORMATION:
Contractor
DPW PM
Submittal # | Division | Description | Date submitted | Due out date (Min 5 work-day review) | Received by | 2nd reviewer/ due date | 3rd reviewer/due date | Date approved | Date rejected | Comments
001 | Site/Util/ATFP | Bollards locations about BFP | 9/9/19 | 9/18/19 | Molina | Fire Dept 9-11-19 | Distro 9-13-19 |  | 9/14/19 | Re-submit - requires corrections -- see transmittal
002 | Gen Cond | Schedule | 2019-09-09 | 2019-09-18 | Molina | n/a | n/a | 2019-09-09 |  | Approved by e-mail dated 9/9/19
003 | Elect
004 | Comm Lines
005 | Site/Util/ATFP | Revision to - Bollards Locations at BFP | 2019-09-15 | 2019-09-22 | Molina | n/a | n/a | 2019-09-15 |  | Approved by e-mail. ----Contractor revisions per comments on submittal 001
006
007
008
009
010
011

## Submittal cover sheet
Submittal Transmittal and cover sheet
Project: |  |  |  | Work Order /contract #: |  |  |  | Date submitted |  | Start date
[8 empty] | Date received |  | Current date
EMPLOYEE INFORMATION: | [7 empty] | Date due out |  | Current date
Contractor
DPW PM
Submittal # | Division | Description | Date submitted | Due out date (Min 5 work-day review) | Received by | 2nd reviewer/ due date | 3rd reviewer/due date | Date approved | Date rejected for corrections | Comments
001 | Site/Util/ATFP | bollards locations about BFP | 9/9/19 | 9/18/19 | Molina | Fire Dept 9-11-19 | Distro 9-13-19 |  | 9/14/19 | Re-submit - see attached comments
Description: SAMPLES ---Construction Schedule ---- Phasing plan---Traffic Control Plan--- Staging ---LED Fixture--- etc….
Reviewer 1 Comments: SAMPLE -- None
COR - or PM comments
Approved (____)
Rejected (____)
| Name/Title of govt. reviewer/ signature / |  |  | Date:
Contractor received | Name/Title/ signature / |  |  | Date: