## Project Charter
Project Charter
Problem Statement | Business Case & Benefits
The Problem Statement should address these questions: What is wrong, not working and not meeting our customer’s needs? When and where do the problems occur? What is the frequency of the problem? What’s the impact of the problem on our customers/business or employees? What is the financial impact of the project and/or problem? | The Business Case should address these questions: Why is this project worth doing? Why is it important to do now? What are the consequences of not doing this project? How does it fit in with business initiatives and targets?
Goal Statement | Timeline
[increase/Decrease] [Unit] from a baseline of [baseline] to a target of [goal level] by [date projected to reach target level] | Phase | Planned Completion Date |  | Actual
Define:
Measure:
Analyze:
Improve:
Control:
Scope - First/Last and In/Out | Team Members
1st Process Step | Position | Person | Title | % of Time
Last Process Step | Team Lead
Sponsor
In Scope: | Team Member
Team Member
Out of Scope: | Team Member
Team Member

## Example 1
Project Charter
Lunch Order Cycle Time
Problem Statement |  | Business Case & Benefits
In the last 3 months we have been receiving customer complaints about how long the food is taking to be delivered during lunch time. Current cycle time average is 28 minutes. If this continues we may lose our business customers who are on a tighter vacation schedule than our vacationers. We could lose revenue. |  | Cycle Time improvement in our food orders for lunch would result in an enhanced client experience. Cycle time improvement could also translate into monetary benefits because we may turn tables quicker and seat more customers, which will increase revenue.
Goal Statement |  | Timeline
Reduce the average time to deliver entrees from an average of 28 minutes to 20 minutes or less by May 10th |  | Phase | Planned Completion Date |  | Actual
|  | Define: | January 14th |  | January 18th
|  | Measure: | January 30th |  | March 10th
|  | Analyze: | April 10th |  | April 12th
|  | Improve: | May 10th |  | May 12th
|  | Control: | June 4th |  | June 20th
Scope In/Out |  | Team Members
1st Process Step | Customer arrives or calls | Position | Person | Title | % of Time
Last Process Step | Deliver order (or pickup) | Team Lead | Elisabeth | Shift Manager | 20%
|  | Sponsor | Julian | Owner | 20%
In Scope: | Food items served, process steps, length of cook time, reallocation of staff resources | Team Member | Scott | Chef | 15%
Out of Scope: | System upgrades and additional hiring, vendor processes and food delivery schedules. | Team Member | Tracy | Server | 15%
|  | Team Member | Sean | Busboy | 15%

## Example 2
Project Charter
Pick-up Order Cycle Time
Problem Statement |  | Business Case & Benefits
The current total lead time for pick-up orders is an average of 27 minutes. This results in customer complaints and limits the capacity for fulfilling orders. |  | Cycle time improvement for pick-up orders will result in an enhanced client experience. Cycle Time improvement could translate into monetary benefits because we will be seen as a more consistent and reliable pick-up option, which could increase customer retention and revenue. This aligns with our mission of providing a tasty slice of island life.
Goal Statement |  | Timeline
Reduce the pick-up order lead time from average of 27 minutes to an average of 20 minutes by the end of Q2 of this year |  | Phase | Planned Completion Date |  | Actual
|  | Define: | 2016-03-02
|  | Measure: | 2016-03-22
|  | Analyze: | 2016-04-13
|  | Improve: | 2016-05-30
|  | Control: | 2016-06-22
Scope In/Out |  | Team Members
1st Process Step | Customer places an order for pick-up | Position | Person | Title | % of Time
Last Process Step | Customer picks up the order at the location | Team Lead | Wesley | Black Belt Candidate | 20%
|  | Sponsor | Elisabeth | Manager | 20%
In: | No new staff or technologies | Team Member | Julie | Processor | 15%
Out: | Job descriptions, layout, process steps | Team Member | Tracy | Waitress | 15%
|  | Team Member | Scott | Chef | 15%
|  | Team Member | Julius | Technician | 15%

## Manufacturing Example
Project Charter
Reduce BSD Scrap Cost
Problem Statement |  | Business Case & Benefits
Scrap $$$ for the Material Handling Dept. has risen to $5850/month in 2015 (January-August) for material marked as Bent/Scratched/Damaged. The Scrap $$$ in 2014 for the same category was just $2141/month. While the costs obviously hurt the bottom line, the inability to push a good quality product in a timely manner impacts delivery to our Assembly/Glazing Plants and eventually; runs the risk of missing Customer Due Dates |  | My organization's Strategy for 2015 was to create a culture of (1) Problem Solving and (2) Continuous Improvement. With B/S/D Scrap $$$ projected to jump almost 300% from 2014 to 2015, this cross-departmental project is our best opportunity to reduce scrap costs across the board while aligning our efforts with the Organizational Strategy. This project could result in $35,000 in Annual Scrap Reduction.
Goal Statement |  | Timeline
Decrease scrap per month from $5850 to $2925 by 12/01/2015 |  | Phase | Planned Completion Date |  | Actual
|  | Define: | 2015-09-28
|  | Measure: | 2015-10-27
|  | Analyze: | 2020-11-16
|  | Improve: | 2015-12-14
|  | Control: | 2015-12-28
Scope In/Out |  | Team Members
1st Process Step | Extrude Parts | Position | Person | Title | % of Time
Last Process Step | Pack Order | Team Lead | Jeff | Engineer | 25%
|  | Team Member | Marquis | Process Owner | 20%
In: | Extrusion, Anodizing, Paint and Pack Departments | Team Member | Justin | Material Handler | 15%
Out: | Receiving Inspection | Team Member | Whitney | Maintenance | 15%
|  | Team Member | Jimmy | Fabrication | 10%
|  | Team Member | Dennis | Production/Welding | 10%

## Finance Example
Project Charter
Reduce number of mail blowbacks
Problem Statement |  | Business Case & Benefits
Biannually, in May and November, notifications are sent out to tax payers when their real estate taxes haven't been paid by the due date(aka Zero Paid Mortgage Letter). The letter grants a 30 day interest and penalty waiver from the date of mailing. The undeliverable mail (aka Blowbacks, approx. 7% of total mailed) is returned to our office and no further research is done. Property owners paid an average of $409.00 in late fees and were late an average of 6 months. |  | Providing taxpayers with equal opportunity to take advantage of the extended deadline contributes to the initiative of Equity and Social Justice. While this project should reduce the amount of penalties paid by taxpayers, it is a way to show taxpayers that we are constantly working towards providing exceptional customer service.
Goal Statement |  | Timeline
Reduce the number blowback (undelivered Zero Paid Mortgage letters) by 50% by December 31st. |  | Phase | Planned Completion Date |  | Actual
|  | Define: | March 31st |  | April 25th
|  | Measure: | July 15th |  | July 15th
|  | Analyze: | August 1st |  | August 1st
|  | Improve: | December 1st |  | December 7th
|  | Control: | December 7th |  | December 7th
Scope In/Out |  | Team Members
1st Process Step | Zero paid mortgage notices are mailed ( May & November) | Position | Person | Title | % of Time
Last Process Step | Locate a better address to mail notice one more time to pay with no late charges | Team Lead | Ana S | Green Belt Candidate | 50%
Sponsor
In Scope: | Research to locate a better address and online applications available | Team Member | Laura W | Green Belt Candidate | 50%
Out of Scope: | Automatic update system used by Recorder's & Assessor's office | Team Member
Team Member

## Healthcare Example
Project Charter
QM Revamp
Problem Statement |  | Business Case & Benefits
Valle del Sol is experiencing rapid growth while resources stay constant. This has led to late deliverables (18%), changing standards (53%), & outdated reports (50%). Internal medical charts do not meet external standards (72%) and have limited Improvement (50%). Voided claims, violations, and monetary sanctions have increased. If this continues, compliance scores may decline and lead to additional loss in revenue and impact patient care. |  | Increased efficiency and efficacy in QM Deliverables would improve timeliness and maintain a high standard of corporate compliance. QM Deliverable improvement could also translate into monetary benefits when VdS hits incentive targets, retain production, and save on overhead. Consequently this increases revenue.
Goal Statement |  | Timeline
The goal is to increase QM Staff (unit) annual deliverables (unit measure) from 283 deliverables (baseline) to 345 deliverables (target) by 4/30/2017 (target date). |  | Phase | Planned Completion Date |  | Actual
|  | Define: | December 31st |  | January 5th
|  | Measure: | January 30th |  | February 8th
|  | Analyze: | February 28th |  | February 15th
|  | Improve: | April 30th |  | May 31st
|  | Control: | June 30th |  | July 6th
Scope In/Out |  | Team Members
1st Process Step | Deliverable is assigned | Position | Person | Title | % of Time
Last Process Step | SOLAR Published | Team Lead | Lynne Emmons |  | 25%
|  | Sponsor | Kurt Sheppard |  | 1%
In Scope: | Audits (tool/sample size/report), technology (free/grant), due dates (internal), Quality Improvement (QM), Arizona, Staff (Existing) | Team Member | Maricela Farias |  | 25%
Out of Scope: |  | Team Member | Heather Jacobs |  | 15%
| Census, technology (cost), due dates (external), Quality Improvement (Non-QM), New Mexico, Staff (New) | Team Member | Paul Decker |  | 5%
Key Take Away: The agency is growing in size and programs and need for more Quality Improvement Time but the QM department will stay the same size.