|  | Project Final Report | Office Use Only State Project No. ...983085..... |
| --- | --- | --- |
|  |  | NHT Project No. |

1. (a)  Project Administration

| Project Title (Use the same title as in original project application) | Regreen the Range |
| --- | --- |

| Name Of Organisation | Willunga Hills Face Landcare Group |
| --- | --- |
| Contact Address | PO Box 215 WILLUNGA SA 5172 |
| Project Manager | Greg Dalton | Ph: 8536 3075 | Fax: 8536 4023 |

|  | Month | Year |  | Month | Year |
| --- | --- | --- | --- | --- | --- |
| Project Duration | Actual Start | Sep 1999 | Actual Finish | Dec 2001 |

1. (b)  Total Project Funding Details

Please provide information over the life of the project on the actual financial and in-kind contributions of the various stakeholders in the project, as set out below (in-kind employment contributions, operating costs and capital costs should be calculated according to the application guidelines that you used for your original funding application).

If you have unspent funds or retain assets these will have to be accounted for.

|  | Proponent Contribution (Funds & In-kind) | Other Contributor 1* (Funds & In-kind) State Tech support | Other Contributor 2* (Funds & In-kind) Landowners | NHT Funds | Total Project Funds |
| --- | --- | --- | --- | --- | --- |
| Approved |  |  |  |  |  |
| Paid employment costs (a) | 0 | 0 | 0 | 77573 | 77573 |
| Operating costs (b) | 4868 | 0 | 509000 | 513616 | 1027484 |
| Capital costs (c) | 0 | 0 | 38100 | 7609 | 45709 |
| Expended (a+b+c) | 4868 | 0 | 547100 | 598798 | 1150766 |
| In-kind employment | 42400 | 22000 | 75550 |  |  |
| Unspent | 0 | 0 | 0 |  |  |
| TOTAL | 47268 | 22000 | 622650 |  |  |

* Provide names of other organisations contributing.

2(a).  Describe the issues or problems addressed by the project

Provide a brief summary of the issues or problems that your project tackled, what you did in your project to resolve these and well it worked.

2(b).  Project Performance against objectives/milestones.

Please provide information on the overall achievements of your project against your planned objectives and milestones.  Indicate important achievements you have made in addition to your planned objectives.  In some cases you may have had difficulties, or were unable to meet all, or some of your objectives.  This should not be regarded as a failure.  Please indicate if this has occurred and give an assessment of factors contributing to the difficulties (eg climatic conditions, group dynamics, late arrival of funds, inappropriate planning, local government regulations).

ACHIEVEMENTS AND IMPEDIMENTS

| What did you set out to do? (List the objectives stated on your funding application) | Comment on the extent to which your objectives were met. | How did you measure your achievements, eg photos, surveys, attendance at seminars. |
| --- | --- | --- |
| Reduced degradation of soils and vegetation | 663 ha was taken out of grazing and planted to native vegetation and woodlots. The degradation of the ha will be reduced as the vegetation grows. Further degradation of the remnant native vegetation will be reduced. | Ha |
| Increased financial returns | 133 ha of woodlots established | Ha |
| Diversification of land use on the Hills face | 663 ha changed to native vegetation, woodlots, reduced grazing and 20 ha of permanent pasture establishment gives 683 ha diversification of land use | Ha |
| Reduction and capture of stormwater runnoff | Long-term objective which cannot be measured in the short-term |  |
| Increased biodiversity | 250 ha native vegetation protected 530 ha revegetated with local native species | Ha |
| Protection of riparian zones | Revegetated areas surround major watercourses |  |
| Reduction of silting of seagrass communities in the Gulf | Long-term effect, not measurable within the confines of this project |  |
| Development of large-scale revegetation processes for other on-ground projects | Revegetation techniques for inaccessible country have been developed | % seedling establishment |
| Skill development within the local community | 34 landholders increasing skills. School children & contractor training | Difficult to measure |
| Increased public awareness of sustainable land use | See publicity and promotion record | Difficult to measure |

3(a)	On-ground Outputs	(total outputs achieved since the start of the project.  Use original application to supply whole of project targets)

| Activity | Total outputs achieved | Project Target |
| --- | --- | --- |

Native vegetation/habitat

| 1) Total area of native vegetation works (Should equal 2) + 3) + 4) | 780 ha | ha |
| --- | --- | --- |
| 2) Remnant protection works (remnants in relatively good condition) | 250 Ha | ha |
| 3) Remnant rehabilitation works (including restoring links) | Ha | ha |
| 4) Revegetation works (predominantly in cleared areas) | 530 Ha | ha |
| 5) Number of plants (not seed) planted. | 424000 No. | No. |
| 6) Length of direct seeding lines | Spots - not in lines Km | km |
| 7) Length of protective fencing | 14 Km | km |
| 8) Area of voluntary management agreements established | Ha | ha |
| 9) Covenanted areas established to protect remnant native vegetation | ha | ha |
| 10) Area of works that protect/enhance threatened species/community habitat | ha | ha |
| 11) Area of 10) protected by agreements as in 8) or 9) | ha | ha |

Waterway or water body management

| 12) Waterway protected by fencing (usually both sides or divide by 2). | km | km |
| --- | --- | --- |
| 13) Length of fenced waterway revegetated. | km | km |
| 14) Benefits downstream of waterway physical works (bed and banks,etc). | km | km |
| 15) Benefits downstream of in-stream habitat works. | km | km |
| 16) Benefits of environmental flows or water provided for wetlands. | ha/km | ha/km |
| 17) Native fish restocking – number of fingerlings. | No. | No. |
| 18) Native fish restocking – age of fingerlings. | months | months |
| 19) Native fish restocking – native to .the area? | Yes/No | Yes/No |
| 20) Other beneficial waterway activities Specify type: | km | km |

21) Pollution Control

| Target Pollutants | Main Source | Initial Levels | Current levels | Target levels | % Improved |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | % |
|  |  |  |  |  | % |
|  |  |  |  |  | % |
|  |  |  |  |  | % |
|  |  |  |  |  | % |

| Activity | Total outputs achieved | Project Target |
| --- | --- | --- |

Control of Rising Watertables)

| 22) Target area for ground water pumping systems installed | ha | ha |
| --- | --- | --- |
| 23) Area drained to control rising water tables | ha | ha |
| 24) Area of planting/establishment in recharge areas | ha | ha |
| 25) Area of planting/establishment in non-recharge areas | ha | ha |
| 26) Using deep-rooted perennial crops/pastures. | ha | ha |
| 27) Using local native species | ha | ha |
| 28) Using non-local native species | ha | ha |
| 29) Using exotic species | ha | ha |

Water-use efficiency improvements

On-farm efficiency?  	(       Or	Off-farm efficiency? (

| 30) By recycling treated effluent | ML % | ML % |
| --- | --- | --- |
| 31) By recycling drainage water | ML % | ML % |
| 32) By use of wastewater | ML % | ML % |
| 33) By use of stormwater | ML % | ML % |
| 34) By more efficient water management systems | ML % | ML % |
| 35) By refurbishment of water supply channels | ML % | ML % |

Stabilisation of wind or water erosion – soil condition

| 36) By revegetation (including fencing out). | 663 ha % | ha % |
| --- | --- | --- |
| 37) By control of grazing pressure. | ha % | ha % |
| 38) By use of cropping technologies. | ha % | ha % |
| 39) Gully erosion control. | ha % | ha % |
| 40) Other Specify: | ha % | ha % |

Improving the use of land within its capability

| 41) Area of land assessed for capability. | 683 ha | ha |
| --- | --- | --- |
| 42) Area of land to be managed according to capability. | 683 ha | ha |

Improved weed and pest management

| 43) Estimated area of effective weed control (including aquatic)? | ha | No. |
| --- | --- | --- |
| 44) Estimated area of effective vertebrate pest control | ha | ha |
| 45) Other specify: | ha | ha |

Farm Forestry for demonstration or trial purposes

| 46) Number of landholders expected to be involved? | 34 No. | No. |
| --- | --- | --- |
| 47) Area of native species for wood production | Ha | ha |
| 48) Area of native species primarily for non-wood production: | Ha | ha |
| 49) Area of exotic species for wood production? | 133 Ha | ha |
| 50) Area of native forest for production? | Ha | ha |

3(b)	Other Outputs

| Achievements (product or service) | Description | Quantity |
| --- | --- | --- |
|  | Total outputs achieved | Project Target |
| Education and awareness (including adoption of best management practices) |  |  |  |
| Type of publication (report, brochure, book) or activity (demonstration, field day) and topic | Target audience and location | Quantity |
| 15 Mar 2000 - Article in Southern Times | Article on the debate surrounding the extent of vegetation on hills prior to European settlement. Evidence as to the fact the hills were previously vegetated cited. |  |  |
| April 2000 - RTR/WHFLCG Display | Youth Convention – South Adelaide Football Club grounds, manned by Simon Beed and Brian Green |  |  |
| 18 April 2000 – Article in Southern Times | Article on local landowner and participant in the Regreen the Range project ‘Bushy’ Martin. Article covered the extensive tree planting Bushy has carried out on his property behind Willunga espousing the benefits he has seen. The article also highlighted the Regreen the Range project which has (in partnership with Bushy) planted up a large proportion of his land. |  |  |
| 28 April 2000 – Display at Mt Compass Field Day | Display of project with RTR brochures available. |  |  |
| May 2000 – Regreen the Range Update | Four page newsletter style publication with photographs. Produced to help inform Regreen the Range partners, government agencies and local people of the current issues/activities/progress of the project. Distributed to all project participants, relevant government agencies and all on the WHFLCG mailing list. |  |  |
| 10 May 2000 – Landcare evening (WHFLCG) | Topic. Revegetation of Creek Lines – speaker Tom Carangis OCWMB |  |  |
| 19 May 2000 – Green corps launch | Official launch of the Regreen the Range Green Corps project. Guest speaker Senator Jeannie Ferris. (30 in attendance) |  |  |
| 6 June 2000 - RTR Display World Environment Day | Display of RTR project at the World Environment day display – Noarlunga City Centre |  |  |
| 7 June 2000 Article in Southern Times | Article on the Green Corps group and the work that they had been carrying out on the Regreen the Range project in weed control and revegetation. |  |  |
| 30 June 2000 – RTR Update | Update included in WHFLCG Newsletter ‘The Green Challenger’ |  |  |
| 30 July 2000 – RTR display and stall | Willunga Almond Blossom Festival. Info stall and display manned from 10.00am –4.00pm. Participation in street parade with banners, planting equipment, seedlings etc. |  |  |
| 31 July 2000 - Regreen the Range Field Tour 1# | A tour organised for all project partners and relevant government agencies. In attendance; Dr. Jill Kerby (Executive Officer – Mt Lofty Ranges Catchment Program), Sally Collins (Technical Officer – Mt Lofty Ranges Catchment Program) Rachel Barratt (Community Liaison Officer – Onkaparinga Catchment Water Management Board), Michael Garrod (Technical Officer - OCWMB), Deborah Just (Councillor – Onkaparinga Council), Scott Douglas (Environment Officer – Onkaparinga Council) Kate Gilbert (Bushcare & Urban Forests Program – Greening Australia), Rachel Bishop (Landcare Officer – Primary Industries & Resources SA), Martyn England (Farm Forestry Consultant – PIRSA), Jane Tassie (Regional Natural Heritage Trust Coordinator – NHT), Peter Michelmore (Senior Manager – Fleurieu Animal & Plant Control Board), Martin Stokes (Senior Water Protection Officer – Environmental protection Agency), Peter Bradley (Onground Works Manager - Regreen the Range), Courtney Davey (Project Assistant RTR), John Campbell (President – Willunga Hills Face Landcare Group), Beryl Gill (Treasurer – WHFLCG), Greg Dalton (Coordination Support – RTR), Rod Dowie (Publicity & Coordination Support RTR). The tour looked at a number of sites in the project and was a forum for discussion on the current needs outcomes and challenges of the project. |  |  |
| 31 July 2000 – Article in Southern Times | Article on Specific Project work of the Green Corps Group – the 150ha conservation planting at Mt Terrible. |  |  |
| 16 August 2000 – Article in Southern Times | Articles showing the research findings of Willunga High students showing that the Willunga Hills were once heavily vegetated. |  |  |
| 18 August 2000 – RTR Update | Update included in WHFLCG Newsletter |  |  |
| 13 Sep 2000 - Landcare Evening (WHFLCG) | Topic - Pest control to protect revegetation of hills face. Speakers; Martin Weidenbach (APCB) & Martyn England (PIRSA) |  |  |
| 13 Oct 2000 - Green Corps Graduation | Graduation of the RTR Green Corps Group. Guest Speakers; John Campbell – President WHFLCG, John Thomas – Hills Face landowner, Terry Peacock –State Manager, Australian Conservation Trust Volunteers |  |  |
| 25 Oct 2000 – RTR Update | Update included in WHFLCG Newsletter |  |  |
| 8 Nov 2000 - Landcare Evening (WHFLCG) | Topic – Saving our Fauna of the Region. Speaker John Hunwick (Threatened Species Network) |  |  |
| 20 Nov 2000 - Regreen the Range Field Tour 2# | Tour of plantings – in attendance; John Hill – Member of Parliament (Kaurna electorate), Steve Gatti – Project manager (Onkaparinga Catchment Water Management Board), Stephen Smith – Planner (OCWMB), Peter Bradley – Onground Works Manager (Regreen the Range project), Naomi Driessen - Landcare Officer (PIRSA), Greg Dalton – Coordination Support (RTR), Rod Dowie – Publicity & Coordination Support (RTR). The tour looked at a range of sites and specifically addressed the needs of the project in continuing plantings on the steeper land at the Southern end of the Range. |  |  |
| 22 Nov 2000 - RTR Forum | Forum for 2001 participants in the RTR project. Speakers – Martyn England (Forestry consultant PIRSA), Peter Bradley (Yeltanna Consulting Services), Martin Weidenbach (APCB), Lee Miller (CFS), John Campbell (President WHFLCG). |  |  |
| 29 Nov 2000 - Regreen the Range Field Day | Field Day for 2001 participants in the Regreen the Range project. Venue John & Jeannie Campbell’s property Willunga Range. |  |  |
| 29 Mar 2001 – Brochure produced | Regreen the Range – “Want to know more” brochure |  |  |
| 25 May 2001 - Robert Brokenshire MP visit/tour | Tour of project site by minister |  |  |
| 29 Aug 2001 – Article in Southern Times | “Regreening the hills at halfway stage” |  |  |
| Oct 2001 – Tour of project partners |  |  |  |
| 6 Dec 2001 – Tour of dignitaries from PIRSA and “Natural Resource Centre for Excellence” |  |  |  |
| Training |
| Purpose and type of training activity | Target audience and location | Number of courses/workshops and number of people trained (and target for project) |
| Planning |
| Name of plan or feasibility study (including project development and marketing strategies) and area of strategy (eg. regional, catchment, subcatchment) | Purpose of plan. Indicate priority issues identified (eg groundwater management, nutrient management, river restoration, salinity, farm forestry feasibility studies etc) | Number published |
| Farm map/plan done for each property | Plan on-ground works | 34 |  |
| Monitoring |  |  |  |
| What is being monitored? | How many sites, how often? Indicate major activities undertaken (eg surveying, mapping, soil sampling) and at what stages. | Number of people who participated |
| Seedling establishment | 34 properties | 3 |  |
| Resource inventory |  |  |  |
| Purpose of inventory | Indicate location. How many sites, how often? Is data to be included on Geographical Information Systems? | Area inventoried |

3(c)	Employee Information and Outputs: Indicate how many salaried staff and/or contract staff were employed in your project, and the length and level of their employment. For each person, indicate the outputs they were responsible for delivering, in order of importance.

|  | Salaried staff | Contractors or consultants |
| --- | --- | --- |
|  | Total achieved | Project Target | Total achieved | Project Target |
| Number, description, length of employment | None |  | 12 contractors engaged for specific tasks |  |
| Outputs (in priority order) |  |  | Project Management and coordination (2) Vegetation surveys (1) Weed control contractors (4) Planting contractors (3) Fencing (2) |  |

4.	Participation

| How many people have been actively involved in your project (include employees and volunteers)? |  | 214 |  |
| --- | --- | --- | --- |

Which stakeholder groups have been involved in the project?  List major groups who contributed to the technical, practical, financial or administrative aspects of the project, eg community groups, schools, tertiary institute, research organisations, local government, State Government, business, Indigenous groups.

| Category | Name of Group | Type of Involvement | Number of Participants |
| --- | --- | --- | --- |
| Catchment Board | Onkaparinga Catchment Water Management Board | Funding, advice and coordination regarding local issues. | 4 |
| Community organisation | Southern Hills Soil Conservation Board | Trainee sponsorship | 1 |
| Community organisation | Willunga Hills Face Landcare Group | Administration, management, coordination, promotion. | 12 |
| Community organisation | Willunga Landcare Centre | Promotion and advice | 30 |
| Community organisation | Trees for Life | On-ground works support | 10 |
| Federally funded program | Green Corps | On-ground works and technical support | 11 |
| Industry | Numerous contracting and consulting services | Surveying, supply of advice and materials, site-works and transport | 14 |
| Local Government | City of Onkaparinga | Funding, advice and coordination regarding local issues. | 3 |
| Participants | Landholders | Provision of land, on-ground works | 34 |
| Regional program | Mt Lofty Ranges Catchment Program | Advice | 2 |
| State Government | National Parks & Wildlife Service | Kangaroo counts | 3 |
| State Government | Animal and Plant Control Board | Weed control and pest animal advice. | 2 |
| State Government | Primary Industries and Resources | Technical advice | 2 |

5.  Implementing Regional, Catchment and Local Area Planning

In what way has your project contributed to the development or implementation of a regional strategy or plan?

LINKS WITH REGIONAL/STATE STRATEGIES AND PLANS Interim State Natural Resource Management Priorities for the State and for the Mt Lofty Ranges 2001-2002 The project addresses many of the key areas and actions from these documents. Community Support Strategy for NHT and Beyond (Dec 2000) The project will meet objectives of this strategy by assisting with the planning of future on ground works, raising community awareness of NRM issues and strategies, and contributing to the development of appropriate community training and educational activities (p16). Onkaparinga Catchment Water Management Plan 2000 Remove grazing from riparian zones, revegetation of watercourses, improvement of water quality and community education and awareness. City of Onkaparinga - Creating Our Future Council is working to restore and enhance the environment in partnership with community environment groups, government, landowners, businesses, schools, tertiary institutions, the Catchment Water Management Authorities for the Onkaparinga and Patawalonga/Sturt Rivers, the Mount Lofty Ranges Catchment Program and others. Environmental Strategies include: Promoting and practicing the conservation of biological diversity on land, in rivers, the Onkaparinga Estuary and the sea. This will include initiatives such as identifying and mapping sensitive areas, trialing marker or information systems, formulating and implementing management plans for Council lands containing remnant vegetation and rare or endangered species, supporting Bushcare, undertaking staff training and encouraging others to conserve biodiversity through grants and the provision of information from an expert adviser. City of Onkaparinga - Environmental Management Plan The aims of the plan are: To identify priority environmental issues and strategies, and actions to address these; To integrate environmental management throughout the Council and all of its functions and operations; and To identify and coordinate community and other initiatives relating to the environment. Under “Better Use of Resources” the aim is to promote more sustainable use of resources. Under “Sustainable Land Management” the aim is to promote sustainable practices and land uses in the rural area.

6.  Use of Project Results

Has your project had any benefits for any other groups?  If so, by whom and in what way.  How has your project been publicised.  Attach copies of media coverage or other publicity.  Has acknowledgment been given to the Natural Heritage Trust?  If you have a photographic record please provide copies.

See publicity and promotion under “Education and Awareness” (above)

7.  Program Administration

Please provide comments on administration of your project and your dealings with relevant government agencies.

Due to the scale and complexity of the project professional services were required for project management, which included administration support.

Fortunately the Landcare Group has highly skilled members who were able to help with financial management, BAS statements, etc.

Support from the local Landcare Officer has been excellent.

8.  Future Action
How is your group planning to maintain the project after funding has ceased?

Landholder contracts include commitment from landholders to maintain revegetated areas

Ongoing support and advice through the Landcare Centre

Do you intend to seek further Natural Heritage Trust funding, or funding from other sources to undertake further activities?

Yes, this project is only part of the long-term objective to revegetate 3,000 ha of the hills face.

9.  Group Declaration:

I declare that I am an authorised representative of the recipient organisation, that the information given on this form is complete and correct and that expenditure of moneys paid under the financial agreement has been solely upon the project and in accordance with the terms of the Agreement and its conditions.

| Name (please print) |  | Name (please print) |  |
| --- | --- | --- | --- |
| Position in Organisation |  | Phone | Position in Organisation |  | Phone |
| Signature |  | Date | Signature |  | Date |

# Text boxes

Regreen the Range tackling about establishing large areas of perennial vegetation to reduce rainfall runoff and increase rainfall infiltration on the Willunga hills face – thereby positively affecting soil erosion and biodiversity on the hills face and surface and aquifer water in the McLaren Vale and Willunga plains.

Needs review