|  | **Community Health Improvement Plan (CHIP) & Tactics – Hardin County Public Health**  |
| --- | --- |
|  | Community Health Assessment results - starting 11/1/2023 to 12/31/2028 |
|   |  **Health Areas of Need (Goals)** |  | **"Specific Actions" to address community health need (Tactics)** | **LEAD** | **Partners** | **Timeframe** | **Performance Indicators: Data Sources/ Collection Timing** |
| **1** | **Mental Health** |
|  **Assess and support depth and breadth of services for Mental Health needs in the communities** | A | Increase providers and access | HFH | Veterans Affairs of Hardin co.,Senior Life Solutions,Mental Health coalition,Hanson Family Hospital, Green Belt Home Care (Public Health) | Year 3-5 | Availability of mental health resources in the community including patient treatment options |
| B | Employment opportunities for providers | Year 3-5 |
| C | Funding reimbursement for shortage – barrier for services | TBD |
| D | Improvement of community responses (example EMT education) | Coalition | Year 1 | Baseline |
| E | Access to transportation to and from services in other communities | (TBD) | Year 2-3 | Availability at certain times or days, even limited at first |
|  | **Progress Notes:**  |  |
| **2** | **Substance Abuse** |
| **Assess and support depth and breadth of services for substance use and abuse in the communities** | A | Assess and create plan for substance abuse prevention and support in the communities | Coalition | Satuci,Hanson Family Hospital, Green Belt Home Care (Public Health) | Year 1-2 | Presence of substance abuse related issues |
| B | Drugs and substance use and presentation services/response | Coalition | Year 3-5 | Actively providing services for the communities (year 1 baseline) |
| C | Increased access to services | (TBD) | Year 3-5 | Increase (15% year over year) from baseline number of services provide and the number of recipients for each service |
|  | **Progress Notes:**  |  |
| **3** | **Childcare Services/ Access** |
| **Address childcare services within the communities**  | A | Investigate the options and opportunities with pediatric health and wellness services and access | Childcare Resource & Referral | Childcare Resource & Referral, Hardin County Child Abuse Prevention CoalitionLocal Childcare providers and Centers | Yer 2-3 | Provide a list of opportunities for potential services in communities |
| B | Continue to collaborate with Partners for the provision of Childcare services – supporting their efforts for availability and education to providers | Coalition | Year 3-5 | Active (systematic) efforts (including knowledge sharing) from partnerships |
|  | **Progress Notes:**  |  |
| **4** | **Knowledge for Preventative Services** |
| **Communicate, convene, and spread information (knowledge) for prevention services**  | A | Providing prevention services (i.e. immunizations) to underserved population and or communities | GBHC | Hanson Family Hospital, Green Belt Home Care (Public Health) | Year 1 | Actively providing services for the underserved communities (year 1 baseline) |
| B | Address the provision of (potential) hospital outreach services to communities outside of Iowa Falls, Iowa. | GBHC | Year 2 | Increase (15% year over year) from baseline number of services provide and the number of recipients for each service  |
| C | Distribution of information and knowledge of services at Community “sharing” meetings | Circle of Life (group) | Year 1 | Active (systematic) efforts (including knowledge sharing) from partnerships |
|  | **Progress Notes:**  |  |
| **5** | **Teen Health / Teen Health Services** |
| **Improvement and availability/ access of services for teen health needs** | A | Assess and create plan for teen health/ services and support in the communities | GBHC | Hanson Family Hospital, Green Belt Home Care (Public Health) | Year 1-2 | Actively providing services for the underserved communities (year 1 baseline) |
| B | Improvement of services through availability and access for teen health  | Increase (15% year over year) from baseline number of services provide and the number of recipients for each service |
| C | Continue to collaborate with Community Coalition | Baseline |
|  | **Progress Notes:** |  |
| **6** | **Health Coalition for County** |
| **Coalition group to address the services and access for community health needs** | A | Assessment for the need of community coalition (“action” group) | gBHC | Hanson Family Hospital, Green Belt Home Care (Public Health) | Year 1 | Provide a list of opportunities for potential services in communities |
| B | Create scope of work and purpose for group that will actively address health needs within the communities | Year 1-5 | Increase (15% year over year) from baseline number of services provide and the number of recipients for each service |
| C | Plan and develop initiatives for community “health” coalition.  | GBHC | Year 1-5 | Baseline |
|  | **Progress Notes:**  |  |