## Draw1
Total Project Budget Spreadsheet Sample
To: |  |  | BORROWER: | Sample Borrower, LLC |  |  | Loan No.: | 1234567890
Loan Officer: |  |  | Project: | Sample Project |  |  | Request No.: | 3
Officer Phone: |  |  | Contact #1: | Jim Smith | Contact Phone: | 770-770-7770 | Period Ending
Officer FAX #: |  |  | Contact #2: | John Smith | Contact FAX: | 770-770-7777 | Date Submitted
A | B | C | D | E | F | G | H | I
| ORIGINAL |  | REVISED | PREVIOUSLY | COMPLETED | TOTAL | BALANCE | %
ITEM | BUDGET | REVISIONS | BUDGET | COMPLETED | THIS PERIOD | COMPLETE | TO FINISH | COMPLETE
SOFT COSTS |  |  | =B + C |  |  | =E + F | =D -G | =G / D
Land | 1000000 | 0 | 1000000 | 1000000 | 0 | 1000000 | 0 | 100%
Civil/Architectural Design Fees | 75000 | 50000 | 125000 | 95000 | 10000 | 105000 | 20000 | 84%
Municipal Fees / Permits | 75000 | 20000 | 95000 | 90000 | 0 | 90000 | 5000 | 94.74%
Insurance/Taxes | 50000 | 0 | 50000 | 45000 | 0 | 45000 | 5000 | 90%
Legal Fees | 50000 | 0 | 50000 | 50000 | 0 | 50000 | 0 | 100%
Appraisal | 10000 | 0 | 10000 | 6000 | 0 | 6000 | 4000 | 60%
Closing Costs / Loan Fees | 75000 | 0 | 75000 | 70000 | 0 | 70000 | 5000 | 93.33%
Sales and Marketing Fees | 100000 | 0 | 100000 | 10000 | 10000 | 20000 | 80000 | 20%
Interest Reserve | 300000 | 0 | 300000 | 45000 | 15000 | 60000 | 240000 | 20%
Consulting/Inspection Fees | 15000 | 0 | 15000 | 2000 | 0 | 2000 | 13000 | 13.33%
Development Fee | 250000 |  | 250000 | 100000 | 25000 | 125000 | 125000 | 50%
Soft Cost Contingency | 150000 | -45000 | 105000 | 0 | 0 | 0 | 105000 | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0
SOFT COST TOTAL | 2150000 | 25000 | 2175000 | 1513000 | 60000 | 1573000 | 602000 | 72.32%
HARD COSTS
Site Work Contract | 350000 | 100000 | 450000 | 200000 | 250000 | 450000 | 0 | 100%
Building Contract | 2000000 | 200000 | 2200000 | 0 | 0 | 0 | 2200000 | 0%
Tenant Improvement Allowance | 500000 | -200000 | 300000 | 0 | 0 | 0 | 300000 | 0%
Owner Furnished Items | 75000 | 0 | 75000 | 15000 | 25000 | 40000 | 35000 | 53.33%
Hard Cost Contingency | 150000 | -100000 | 50000 | 0 | 0 | 0 | 50000 | 0%
HARD COST TOTAL | 3075000 | 0 | 3075000 | 215000 | 275000 | 490000 | 2585000 | 15.93%
TOTAL PROJECT COST | 5225000 | 25000 | 5250000 | 1728000 | 335000 | 2063000 | 3187000 | 88.26%
PROJECT EQUITY | 1250000 | 25000 | 1275000 | 1000000 | 275000 | 1275000 | 0 | 100%
TOTAL LOAN AMOUNT | 3975000 | 0 | 3975000 | 728000 | 60000 | 788000 | 3187000
BORROWER: | Sample Borrower, LLC |  |  |  | 60000 | is hereby requested for disbursement.
Submitted By:_____________________________________________________
Officer / Title |  | Date
Comments: