**JOHNSONBURG MUNICIPAL AUTHORITY**

**REGULAR MEETING**

**WEDNESDAY APRIL 14, 2021**

The meeting was called to order at 4:00 P.M. by Chairman James Reinsburrow, followed by Pledge of Allegiance and moment of silence.

**ROLL CALL** – In attendance were James Reinsburrow, Richard Zeigler, Charles DeStephano, Dennis Asti, Kenneth Polaski, Earl Park, Thomas J. Weaver, Dan Newell, Richard Brown, Kerri Shaffer, and Erica Zimmerman. (Travis Long, and Josh Gunnett via Zoom).

**EXECUTIVE SESSION**- Motion made by and seconded by to enter executive session at PM to discuss personnel. Motion carried unanimously. Motion made by and seconded by to exit session at PM. Motion carried unanimously. Motion made by and seconded by to enter regular session at PM. Motion carried unanimously.

**APPROVAL OF MINUTES FROM THE PREVIOUS MEETING**- The minutes of the March 10, 2021 Regular Meeting was approved as presented. Motion made by and seconded by; motion carried unanimously.

**VISITORS**- Brian Stockman (Ridgway Record Reporter) Al Maletto, and Joyce Maletto (Johnsonburg Press Reporter).

**VISITORS COMMENTS**- None

**MANAGER’S REPORT****-** JMA is currently working with DEP to correct compliance related issues and making corrections where needed per JMA Consent Decree. DEP will be preforming an inspection at the New Water Treatment Plant on April 22-23, 2021. Easements for waterlines have been sent out. Dill Hill pump station has been installed beside the water tank. Erie Avenue has been updated per water service. Continental Construction is performing work to the bottom of Water Street. Todd Mace from PESI is working the JMA staff at the Wastewater Treatment Plant. The Staff was trained by PA Rural Water on Method 334.

**ENGINEER’S REPORT** –JHA and Solicitor Brown continue to address easements for the waterline extension. Permitting packages awaiting from environmental agencies and geotechnical reports which are pending property access. Consent Order items remain ongoing. JMA water staff needs to revise SOP’s. JHA is working with JMA Staff on addressing WWTP water quality issues. Lab instrumentation in needed. Chlorination equipment needs attention and is creating a potential unsafe condition. In-line instrumentation was found to be by and far inoperable. Evaluation of equipment is necessary to determine future applicability for compliance attainment, operational need, or deletion.

**PROJECT ENGINEER’S REPORT-** GD&F are working with USDA on additional waterline replacement areas. Contract No. 1- Intake Building- Waiting for DEP inspection, cleaning, and prepping the interior for Substantial Completion, exterior EFIS system installing. Flocculation Tank- Waiting for DEP inspection the interior for Substantial Completion. Control Building- Finishing plant interior work and clean up, finalizing SCADA and controls for DEP inspection, AOP startup and SCADA startup and commissioning was completed and functioned well, and they did the floor. Site Work- Working on sidewalks and the Borough requested the sidewalks be ADA compliant. Change Order No. 3 the Contractor is requesting a time extension for 54 days. The new Substantial Completion would be May 2, 2021 and the Final Completion would be July 31, 2021. Change Order No. for paving of the Water Treatment Plant access road. Substantial Completion is scheduled to be issued the day that DEP grants the Operational permit for the new plant. Inspection is scheduled for April 22 and April 23. Contract No. 2- Finishing telemetry system this week, readying plant for DEP inspection. Contract No.2 should also be extended to May 2, 2021 and Jul 31, 2021 to match Global’s. Contract No. 3- 3rd Avenue -having trouble filling the tank and meeting the system demand with the Powers Run Plant. Silver Creek- Tank is full and Bacterial testing completed. Contract No. 4- Finished waterline and stormwater line on Mary Street, finished relocation of Dill Hill pump station, small package station startups and troubleshooting are ongoing, and working with Domtar on the waterline replacement on Center Street. Domtar has requested that bore pits be moved 60 feet further into their property on either side of the river to disturb less parking spaces. Domtar has also requested that the waterline on the northern side of the property be completely directionally drilled to avoid impacting the road used for the chip trucks. Requisition #67 to USDA in the amount of $454,468.44.

**SOLICITOR’S REPORT**- None

**COMMITTEE REPORTS –**

1. Administration- None
2. Finance- None
3. Fire Department- None
4. Hiring- None
5. Johnsonburg Borough- None
6. Operations- None

**APPROVAL OF RESOLUTION ACCEPTING THE CONSENT ASSESSENT OF CIVAL PENALTY**- Motion made by and seconded by to pass Resolution 04142021 accepting the consent assessment of civil penalty from March 10, 2021.

**APPROVAL OF TREASURER’S REPORT-**

|  |  |
| --- | --- |
| Revenue Fund- Water & Sewer | $ 200,099.20 |
| Municipal Savings Account- Water | $ 1,165,805.79 |
| Municipal Savings Account- Sewer | $ 76,611.85 |
| Insured Money Funds | $ 64,178.65 |
| Payroll Fund- Northwest | $ 11,689.28 |
| Payroll Fund- CNB | $ 11,257.62 |
| Certificate of Deposit-Sewer- CNB | $ 25,844.35 |
| Hunt Water Sales-CNB-Savings | $ 23,249.26 |
| Line of Credit- Checking | $ 25,908.55 |
| Line of Credit- Waterline Extension | $12.00 |

Motion made by and seconded by, to accept the Treasurer’s report for March 31, 2021, as presented and placed on file for audit; motion carried unanimously.

**APPROVAL OF BILLS-**

Revenue Fund- Water $45,705.46

A motion was made by and seconded by to approve the water bills. Motion carried unanimously.

Revenue Fund- Sewer $45,371.77

A motion was made by and seconded by to approve the sewer bills. Motion carried.

COA $144.00

A motion was made by and seconded by to approve the COA bills. Motion carried unanimously.

Project Engineer $27,143.00

A motion was made by and seconded by to approve the Project Engineer bill. Motion carried unanimously.

Contact No. 1 Pay Application $216,785.25

A motion was made by and seconded by to approve the Contract No. 1 Pay Application bills. Motion carried unanimously.

Contract No. 2 Pay Application $20,813.52

A motion was made by and seconded by to approve the Contract No. 2 Pay Application bills. Motion carried unanimously.

Contract No. 3 Pay Application $38,869.25

A motion was made by and seconded by to approve the Contract No. 3 Pay Application bills. Motion carried unanimously.

Contract No. 4 Pay Application $150,713.42

A motion was made by and seconded by to approve the Contract No. 3 Pay Application bills. Motion carried unanimously.

**BUSINESS AFFAIRS** –

**BOARD DISCUSSION-** None

**COMMENTS FROM VISITORS**- None

**EXECUTIVE SESSION**- Motion made by and seconded by to enter executive session at PM.; motion carried unanimously. Motion made by and seconded by to exit executive session at PM.; motion carried unanimously. Discussed personnel and litigation with no decisions made. Motion made by and seconded by to enter regular session at PM.; motion carried unanimously.

**ADJOURMENT OF MEETING**- Motion made by and seconded by to adjourn the meeting at

PM. Motion carried unanimously.

Kenneth Polaski,

Secretary

KLS