## S&D (hidden)
S&D HSSE PLANS Year __________
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | FM comments | HSSE Comments
Process Safety Improvement
HSSE for Front Line Leaders Training | [12 empty] | lets include PSSU, AI | done
Integrity Leadership Workshop
Weak Signals Session | bar: MAR
Process Safety Culture Survey
Process Safety Super User Network | [12 empty] | can we put under S&D as this led at HO | done | bar: FEB; MAY; AUG; NOV
Asset Integrity Review | [12 empty] | can we put under S&D | done | bar: MAR; JUN; SEP; DEC
HEMP Refresher (One-on-One session with HSSE/TM) | [12 empty] | ok | bar: FEB to JUN
Greenbanding | bar: JAN to MAR
Quarterly LoD1 Discussion w/ FM and CGM | bar: APR; JUL; OCT
PDSI AI-PSM Review
ACACIA AI-PSM Review
Follow up actions/recommendations from 2012 reviews (PDSI, FPIC and SHAPE)
Journey to Road Safety Excellence
RT Haulier Conference | bar: MAR
RT SO Convention | bar: MAR
Review of PARDS/STRIPES Mechanics - IVMS* | bar: JAN
Review Hauler Dashboard Mechanics - IVMS* | bar: JAN
Launch of Driver Behaviour Indicator Tool | bar: DEC
DDC refresher | bar: FEB
Review Driver training materials | bar: FEB; MAY; AUG; NOV
RTCA - Launch revised 4P/7P mechanics, train PH auditors | bar: APR to MAY
Arrive Alive Campaigns/TBTs - monthly
JMP Review | bar: OCT
Standards, Compliance and Assurance
Risk Matrix Review | bar: JAN; APR; JUL; OCT
HSSE & SP Control Framework Audit | bar: JUL
Incident Reviews | [12 empty] | can we put in S&D | done
ARROWS Audit | [12 empty] | can we put in S&D | done | bar: APR to DEC
Right HSSE People and Competences
GPTW & AGT Training
PTW Training - Haulers & Engineering Contractors
HAZOP Training
Fatigue Awareness Training
HSSE Competence Assurance for Front Line Staff
HSSE Competence discussion with Supply Staff
Annual Ship Owners' Meeting
Quarterly Ship Owners' Performance Review
Quarterly Surveyors' Meeting
Engineering SO Convention | bar: JAN
Quarterly Engineering Dashboard Review
Fire Fighting Training & Assessment | [12 empty] | can we put in S&D | done
BOSH Training* | [12 empty] | can we put in S&D | done
Safety Practitioner Accreditation | [12 empty] | can we put in S&D | done
Fatigue Awareness Training | [12 empty] | can we put in S&D | done
Safety Day 2013 (June 19) | bar: JUN
Note on A25: Lisa.M.Yap: Q1 – Managing Life on the Road incl. Driver Fatigue, H&M, Other Modules under MLR Q2 –Product Knowledge Q3 – Behavioral Based Safety Q4 – Emergency Response

## Per Terminal (hidden)
_____________ Terminal HSSE PLANS Year ________
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | FM Comments | HSSE Comments
Process Safety Improvement
Emergency Drills | [12 empty] | ok
Weak Signals Session | [12 empty] | pls clarify | TMs to cascade Weak Signals Session to staff after the session in the SD event | bar: MAR
TMC Meeting (including HEMP discussion) | [12 empty] | ok
HSSE Monthly Campaigns Discussion | [12 empty] | ok
Monthly Monitoring Well Testing (Visual) | [12 empty] | quarterly & monthly | Please confirm: Monthly - Visual?
Quarterly Effluent Testing | [13 empty] | added | bar: MAR; JUN; SEP
Journey to Road Safety Excellence
Road Safety Tool Box Talks TBT | [12 empty] | ok
7/4 Pillars Audit / RTCA | [12 empty] | ok
Monthly Hauler Dashboard Review | [12 empty] | ok
Quarterly Hauler Dashboard Review | [12 empty] | ok
JMP Review | [12 empty] | ok | bar: OCT
Standards, Compliance and Assurance
Monthly LoD1 Checks | [12 empty] | pls provide details | Done
Product Quality | bar: FEB; APR; JUN to DEC
AI-PSM/HEMP Management | bar: JUN
Statement of Fitness | bar: MAR; SEP
Inspection & Maintenance
Management of Change | bar: JAN; JUL
Permit to Work
Operational Controls
Road Safety
Contractor Safety | bar: JAN; MAR; MAY; JUL; SEP
Sharing of LFIs/Incidents to terminal staff | [12 empty] | ok
HEMP Review | [12 empty] | pls clarify | Review of the Terminal's HEMP to be included in their TMCs
HSSE Manuals Review | [12 empty] | ok | bar: JUN
HRA Review w/ Shell Health | [12 empty] | ok
SRA Review w/ Corporate Security | [12 empty] | pls clarify | Annual review of SRA which coincides with the annual review of the Security Plan | bar: AUG
FoW/JoWA | [12 empty] | ok
Risk Matrix Review | [12 empty] | ok | bar: FEB; JUL; OCT
Self Monitoring Report Submission (Quarterly) | [12 empty] | ok | bar: JAN; APR; JUL; OCT
Permit Renewal (refer to PAL tracker) | [12 empty] | pls provide details | bar: JAN
Right HSSE People and Competences
JCP review | [12 empty] | ok | bar: JAN; JUN
Safety Day 2013 (June 19) | [12 empty] | ok | bar: JUN

## Per Terminal 2021
ARCHIPELAGO INDUSTRIAL MANAGEMENT CORPORATION HSSE PLANS Year 2021
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
People
Gap Assessment | MAR: 2021-05-30
PPE Replacement | bar: SEP
Physical
Random Drug Test (no of staff per quarter)
NMIF (2 ~ 3) | MAR: 2021-03-27; JUN: 2021-06-12
CABADBARAN (1~2) | NOV: 2021-11-15
ILIGAN (1~2)
Sasa (1) | SEP: 2021-09-10
Zamboanga (1) | NOV: 2021-11-12
Villanueva (1) | JUL: 2021-07-14
Palawan
Tagbilaran
Cebu
Contractor Staff In-Haus Training
NMIF | Rigger Training (22-Jan) | 0 | LCM Training (Mar 20,21,27,28) 40 hrs; DOLE | CRANE SAFETY Apr 14 / SCAFFOLDING SAFETY (apr.23) | Pump Operation & Maintenance (May 10) | Rigger Hand Signal Review (June 19) | 0 | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3 | 0 | 0
CABADBARAN | 0 | 0 | LCM Training (Mar 20,21,27,28) 40 hrs; DOLE | 0 | Pump Operation & Maintenance (May 10) | 0 | 0 | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3 |  | 0
ILIGAN | 0 | 0 | LCM Training (Mar 20,21,27,28) 40 hrs; DOLE | 0 | Pump Operation & Maintenance (May 10) | 0 | 0 | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3 |  | 0
Sasa | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Zamboanga | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Villanueva | Rigger Training (22-Jan) | 0 | LCM Training (Mar 20,21,27,28) 40 hrs; DOLE | CRANE SAFETY Apr 14 | 0 | 0 | 0 | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3 |  | 0
Palawan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3 | 0 | 0
Tagbilaran | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3 | 0 | 0
Cebu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LINYARD INSPECTION TRAINING 3M | 0 | Pump Vibration Monitor | 0
Contractor 1st Responder Drill Plan
NMIF | Fall from Gantry: TA fell from gantry while getting sample from top of lorry( Jan 16) | Failure on the stadis pail handle,damaged full down to tank ring, reason a minor oil spill while on the way dope stadis additive to tank 102 Main tank Farm. (Feb 20) | Pump house’s (Pump seal or motor fire): Fire broke out an one of the product pump of mogas at the Day Tank Farm Terminal used for gantry loading (Mar 27) | First aid Rescue from warehouse ,a warehouse man suddenly slipped while transfering slop drums to wood pallet (Apr 4) | Product PUMP on fire, while gantry loading the pump overheat resulting to fire, while ongoing Gantry operations MOGAS product (May 29) | Delivery of additive pack resulting to LOPC at near the warehouse (June 26) | First aid Rescue. A tankfarm attendant collapsed while getting sample from tank 2 Day tank farm.( Jul 7) | Gantry on fire: During gantry operation, the lorry was suddenly hit by another lorry during queing on the gantry operation resulting to fire on gantry. (21 Aug) | A major earthquake occurred in the city. After evacuation, it was observed that two staffs were missing. A search and rescue was initiated in the terminal to look for the said personnel (Sept 18) | while receiving ethanol product a tankfarm attendant notice the MLI leaking on the tank in service for recieving ethanol lorr (Oct 29) | Fire on the manifold of the island 3 during product receiving of ETHANOL from gantry leak cargo hose connection and lorry manifold resulting to fire | Small leaks from process equipment and piping, sampling systems, sight glasses, flange joints, etc.: During product receiving of E98, leak occurred at the cargoline flange connection resulting LOPC
CABADBARAN |  |  | LOPC-drill: During loading of MOGAS from the BFG observed passing of lorry discharge valve resulted of LOPC and that resulted also of fire (Mar 25) | 0 | Fall from gantry:while getting sample from lorry compartment for water extraction testing a TFA fall down to gantry. (May 17) | 0 | MERS Drill: During getting sample from the tank of product after tanker receiving, the sampler was collapse | 0 | A major earthquake occurred in the city. After evacuation, it was observed that one staff were missing. A search and rescue was initiated in the terminal to look for the said personnel (Sept 29) | 0 | During tanker receiving while getting the product line sample at the the sampling cock, the attendant has been splash with product at his eye | 0
ILIGAN | Product PUMP on fire, while gantry loading the pump overheat resulting to fire, while ongoing Gantry operations ADO product (Jan 19) | 0 | 0 | Delivery of additive pack resulting to LOPC at near the warehouse (apr 13) | 0 | 0 | While decanting of Nemo 6164 additive a tankfarm attendant notice the MLI leaking on the tank | 0 | 0 | First aid Rescue from warehouse ,a warehouse man suddenly slipped while transfering slop drums to wood pallet (Oct 6) | 0 | 0
Sasa
Zamboanga
Villanueva | 0 | 0 | First Aid Rescue Gantry operator got burn while taking bitumen sample. (Mar 26) | 0 | Marine Portable genset at port on fire due to overheat.(May 26) | Supervisor discovered small fire due to Electrical sparks at the MCC room. (June 18) | 0 | Maintenance personnel collapsed due to extreme heat. (17-Aug) | 0 | Overheat at the lorry resulted to fire while at gantry. (Oct 19) | 0 | 0
Palawan
Tagbilaran
Cebu
Leadership
Dashboard Meeting | [9 empty] | S | bar: 0; 0
Contractor HSE Meetings/ Terminal Visits
NMIF | 0 | 2021-02-26 | 0 | 0 | 2021-05-24 | 0 | 0 | 0 | 2021-09-02 | 0 | 0 | 2022-12-22
CABADBARAN | 0 | 0 | 2021-03-24 | 0 | 2021-05-28 | 0 | 0 | 2021-08-26 | 2021-09-02 | 0 | S | 0
ILIGAN | 0 | 0 | 2021-03-23 | 2021-04-16 | 2021-05-25 | 0 | 0 | 0 | 2021-09-02 | 0 | S | 0
Sasa | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Zamboanga | 0 | 0 | 0 | 2021-04-19 | 0 | 0 | 0 | 0 | 0 | S | 0 | 0
Villanueva | 2021-01-29 | 0 | 2021-03-05 | 0 | 0 | 0 | 0 | 2021-08-27 | 0 | 0 | 0 | 2022-12-19
Palawan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-09-16 | S | 0 | 0
Tagbilaran | 0 | 0 | 0 | 0 | 2021-05-05 | 0 | 0 | 0 | 2021-09-02 | S | 0 | 0
Cebu | 0 | 0 | 0 | 0 | 2021-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contractor HSSE Management
Annual Review of HSE-MS | 0: 2021-05-30
HSSE Manuals Review | 0: 2021-05-30
Risk Matrix Review | 0: 2021-05-30
Compliance
Asset Monitoring | 0: 2021-03-30
Business Permit | 0: 2021-02-28
DOLE OSH Monitor
Work Accident & Injury Report (WAIR) | 2021-01-30 | 2021-02-28 | 2021-03-30 | 2021-04-30 | 2021-05-30 | 2021-06-30 | 2021-07-30 | 2021-08-30 | 2022-09-30 | 2021-10-30 | 2022-11-30 | 2022-12-30
Annual Work Accident/Injury Exposure Data Report | 0: 2021-01-30
Annual Medical Report (AMR) | 0: 2021-01-30
OSH Committee Report | 0: 2021-03-30; 0: 2021-06-30 | 2022-09-30 |  |  | 2022-12-30
Monthly Process Checks
Management of Change | 0: 2021-02-28
Updating of Audit Tracking System/Action Tracker | 2021-01-30 | 2021-02-28 | 2021-01-30 | 2021-04-30 | 2021-05-30 | 2021-06-30 | 2021-07-30 | 2021-08-30 | 2022-09-30 | 2022-10-30 | 2022-11-30 | 2022-12-30
Land Logistics
Third Party Certification of Crane 16 ton | [8 empty] | 2022-09-10
Third Party Certification of Crane 25 tons | 0: 2021-03-02
Third Party Certification of boom truck -2 ton | [8 empty] | 2021-09-10
Third Party Certification of boom truck - 5 ton | [8 empty] | 2021-09-10
Man Cage | [8 empty] | 2021-09-10
Shell Equipment Inspection | 0: 2021-06-30 |  |  |  | 2022-12-30
AIMC Safe Program Review
Scheduled | 0: S; 0: APPROVED BY
Done | 0: xx-xx-xx
Note on D14: Re-scheduled by DENR (TBA)

## HSSE Campaigns (hidden)
January | February | March | April | May | June
Health, Security & Environment Manuals | Personal Safety | Process Safety | HSE MS Manual | Transport | Contractor HSSE, Projects, SP, Product Stewardship
Seatbelt | Working at Heights | Isolation | Permit to Work | JMP | Smoking
July | August | September | October | November | December
Tier 1/ Tier 2 PSE and PS Near Misses | Fitness to Work | HSSE Competences | Risk Matrix | Contractor Safety | Office Safety
Override | Gas Test | M Phone/ Speed | CSE | Suspended Load | Alcohol & Drugs

## NMIF (hidden)
ARCHIPELAGO INDUSTRIAL MANAGEMENT CORPORATION HSSE PLANS Year 2019
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
People
Gap Assessment | bar: MAR
PPE Replacement | bar: OCT
Physical & Medical Examination incl drug test | bar: OCT
Random Drug Test (no of staff per quarter)
NMIF (2 ~ 3) | JAN: 2018-01-02; SEP: 0; DEC: S
Contractor Staff In-Haus Training
NMIF | Rigger Training (22-Jan) | 0 | LCM Training (Mar 20,21,27,28) 40 hrs; DOLE | CRANE SAFETY Apr 14 / SCAFFOLDING SAFETY (apr.23) | Pump Operation & Maintenance (May 10) | Rigger Hand Signal Review (June 19) | 0 | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3 | 0 | 0
Contractor In-Haus Drill Plan
NMIF | Fall from Gantry: TA fell from gantry while getting sample from top of lorry( Jan 16) | Failure on the stadis pail handle,damaged full down to tank ring, reason a minor oil spill while on the way dope stadis additive to tank 102 Main tank Farm. (Feb 20) | Pump house’s (Pump seal or motor fire): Fire broke out an one of the product pump of mogas at the Day Tank Farm Terminal used for gantry loading (Mar 27) | First aid Rescue from warehouse ,a warehouse man suddenly slipped while transfering slop drums to wood pallet (Apr 4) | Product PUMP on fire, while gantry loading the pump overheat resulting to fire, while ongoing Gantry operations MOGAS product (May 29) | Delivery of additive pack resulting to LOPC at near the warehouse (June 26) | First aid Rescue. A tankfarm attendant collapsed while getting sample from tank 2 Day tank farm.( Jul 7) | Gantry on fire: During gantry operation, the lorry was suddenly hit by another lorry during queing on the gantry operation resulting to fire on gantry. (21 Aug) | A major earthquake occurred in the city. After evacuation, it was observed that two staffs were missing. A search and rescue was initiated in the terminal to look for the said personnel (Sept 18) | while receiving ethanol product a tankfarm attendant notice the MLI leaking on the tank in service for recieving ethanol lorr (Oct 29) | Fire on the manifold of the island 3 during product receiving of ETHANOL from gantry leak cargo hose connection and lorry manifold resulting to fire | Small leaks from process equipment and piping, sampling systems, sight glasses, flange joints, etc.: During product receiving of E98, leak occurred at the cargoline flange connection resulting LOPC
Leadership
Dashboard Meeting | 2019-01-24 | S | S | S | S | S | S | S | S | S | S | S
Contractor HSE Meetings/ Terminal Visits
NMIF | 0 | 2021-02-26 | 0 | 0 | 2021-05-24 | 0 | 0 | 0 | 2021-09-02 | 0 | 0 | 2022-12-22
Contractor HSSE Management
Annual Review of HSE-MS | MAR: 0
HSSE Manuals Review | MAR: 0; MAY: `
Risk Matrix Review | MAR: 0
Compliance
Asset Monitoring | MAR: 2021-03-30
Business Permit | FEB: 2021-02-28
Monthly Process Checks
Management of Change | FEB: 2021-02-28
Updating of Audit Tracking System/Action Tracker | 2021-01-30 | 2021-02-28 | 2021-01-30 | 2021-04-30 | 2021-05-30 | 2021-06-30 | 2021-07-30 | 2021-08-30 | 2022-09-30 | 2022-10-30 | 2022-11-30 | 2022-12-30
Land Logistics
Third Party Certification of Crane 16 ton | SEP: 2022-09-10
Third Party Certification of boom truck | SEP: 2021-09-10
Shell Equipment Inspection crane 16 ton | bar: JUN
AIMC Safe Program Review |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduled |  |  |  | 0: APPROVED BY
Done | xx-xx-xx
March 13, 2019

## Training Plan
ARCHIPELAGO INDUSTRIAL MANAGEMENT CORPORATION TRAINING PLAN Year 2020
SITE | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
NMIF | Rigger Training (22-Jan) |  | LCM Training (Mar 20,21,27,28) 40 hrs; DOLE | CRANE SAFETY Apr 14 / SCAFFOLDING SAFETY (apr.23) | Pump Operation & Maintenance (May 10) | Rigger Hand Signal Review (June 19) |  | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3
CABADBARAN |  |  | LCM Training (Mar 20,21,27,28) 40 hrs; DOLE |  | Pump Operation & Maintenance (May 10) |  |  | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3
ILIGAN |  |  | LCM Training (Mar 20,21,27,28) 40 hrs; DOLE |  | Pump Operation & Maintenance (May 10) |  |  | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3
SASA
ZAMBOANGA
VILLANUEVA | Rigger Training (22-Jan) |  | LCM Training (Mar 20,21,27,28) 40 hrs; DOLE | CRANE SAFETY Apr 14 |  |  |  | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3
PALAWAN | [7 empty] | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3
TAGBILARAN | [7 empty] | Maintenance Checklist Training MOD 1 (Aug 16) | Maintenance Checklist Training MOD 2 | Maintenance Checklist Training MOD 3
CEBU
MAINTENANCE | [8 empty] | LINYARD INSPECTION TRAINING 3M |  | Pump Vibration Monitor
Scheduled
Done

## Plant Visit
ARCHIPELAGO INDUSTRIAL MANAGEMENT CORP
2020 PLANT VISIT SCHEDULES & STAFF ENGAGEMENTS | [12 empty] | schedule - | S
[13 empty] | done - | XX-XX
Particular | TGT per annum | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN | JUL | AUG |  | SEP |  | OCT | NOV | DEC |  | TGT per annum | ACTUAL visits
1) NMIF | 1 |  |  | 2021-02-26 | 1 |  |  |  |  | 2021-05-24 | 1 |  |  |  |  | 2021-09-02 | 1 |  |  | 2022-12-22 | 1 | 1 | 4
2) CABADBARAN | 1 |  |  |  |  | 2021-03-24 | 1 |  |  | 2021-05-28 | 1 |  |  | 2021-08-26 | 1 | 2021-09-02 | 1 |  | S |  |  | 1 | 4
3) ILIGAN | 1 |  |  |  |  | 2021-03-23 | 1 | 2021-04-16 | 1 | 2021-05-25 | 1 |  |  |  |  | 2021-09-02 | 1 |  | S |  |  | 1 | 4
4) SASA | 1 | [20 empty] | 1 | 0
5) ZAMBOANGA | 1 | [6 empty] | 2021-04-19 | 1 | [8 empty] | S |  |  |  | 1 | 1
6) Villanueva | 4 | 2021-01-29 | 1899-12-31 |  |  | 2021-03-05 | 1 | [6 empty] | 2021-08-27 | 1899-12-31 |  |  |  |  | 2022-12-19 | 1 | 4 | 4
7) Palawan | 1 | [14 empty] | 2021-09-16 | 1 | S |  |  |  | 1 | 1
8) Tagbilaran | 1 | [8 empty] | 2021-05-05 | 1 |  |  |  |  | 2021-09-02 | 1 | S |  |  |  | 1 | 2
9) Cebu | 1 | [5 empty] | 0 |  |  | 2021-05-07 | 1 | [10 empty] | 1 | 1
[22 empty] | 12 | 21

## NMIF Drll Plan
ARCHIPELAGO INDUSTRIAL MANAGEMENT CORPORATION NMIF HSSE PLANS Year 2019
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
People
contructor assessement / FLBM | JAN: new TFA
Gap Assessment | bar: MAR
PPE Replacement | JAN: 2019-01-24
Physical & Medical Examination incl drug test | JAN: 2019-01-10
Random Drug Test (no of staff per quarter)
NMIF (2 ~ 3) | JAN: 2019-01-25
Contractor Staff In-Haus Training | FEB: BOSH jayn; MAR: BOSH Arvin; MAY: Electrical Technicians Training/PTW; AUG: Defensive Driving
Leadership
Dashboard Meeting | JAN: 2019-01-24
Contractor HSSE Management
DRILLS | bar: JAN to JUN; AUG to NOV
| Fall from Gantry: TA fell from gantry while getting sample from top of lorry( Jan 16) | Failure on the stadis pail handle,damaged full down to tank ring, reason a minor oil spill while on the way dope stadis additive to tank 102 Main tank Farm. (Feb 20) | Pump house’s (Pump seal or motor fire): Fire broke out an one of the product pump of mogas at the Day Tank Farm Terminal used for gantry loading (Mar 27) | First aid Rescue from warehouse ,a warehouse man suddenly slipped while transfering slop drums to wood pallet (Apr 4) | Product PUMP on fire, while gantry loading the pump overheat resulting to fire, while ongoing Gantry operations MOGAS product (May 29) | Delivery of additive pack resulting to LOPC at near the warehouse (June 26) | First aid Rescue. A tankfarm attendant collapsed while getting sample from tank 2 Day tank farm.( Jul 7) | Gantry on fire: During gantry operation, the lorry was suddenly hit by another lorry during queing on the gantry operation resulting to fire on gantry. (21 Aug) | A major earthquake occurred in the city. After evacuation, it was observed that two staffs were missing. A search and rescue was initiated in the terminal to look for the said personnel (Sept 18) | while receiving ethanol product a tankfarm attendant notice the MLI leaking on the tank in service for recieving ethanol lorr (Oct 29) | Fire on the manifold of the island 3 during product receiving of ETHANOL from gantry leak cargo hose connection and lorry manifold resulting to fire | Small leaks from process equipment and piping, sampling systems, sight glasses, flange joints, etc.: During product receiving of E98, leak occurred at the cargoline flange connection resulting LOPC
Compliance
Asset Monitoring | bar: MAR
Business Permit | bar: FEB
MAINTENANCE Monthly Process Checks | bar: JAN
Management of Change | bar: FEB; APR to DEC
Updating of Audit Tracking System/Action Tracker
AIMC Safe Program Review
Scheduled | bar: JAN
Done | JAN: xx-xx-xx

## CBDB Drill Plan
ARCHIPELAGO INDUSTRIAL MANAGEMENT CORPORATION CABADBARAN HSSE PLANS Year 2019
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
People
contructor assessement / FLBM | bar: JAN to FEB
Gap Assessment | bar: MAR
PPE Replacement | JAN: 2019-01-30
Physical & Medical Examination incl drug test | MAY: Rechell Cagula 05 May 2019; JUL: Julius Loque 04 July 2019; AUG: Zarah Peñaflorida 1 Aug 2019 Alljhon Salumanda 06 Aug 2019 Felipe Eway 08 Aug 2019; OCT: Dennis c. Salvador 23 Oct 2019 Lemuel Simin 23 Oct 2019; NOV: Richie Rin 06 Nov 2019
Random Drug Test (no of staff per quarter)
Contractor Staff In-Haus Training | FEB: Gantry operator Training Richie Rin; MAR: Gantry Operator Training Lemuel Simin; AUG: Maintenance Checklist Training
Leadership
Dashboard Meeting | bar: JAN; MAY to JUN; SEP; NOV to DEC
Contractor HSSE Management
DRILLS
Shell Drills | bar: JAN
AIMC In Haus Drill | MAR: LOPC-drill: During loading of MOGAS from the BFG observed passing of lorry discharge valve resulted of LOPC and that resulted also of fire (Mar 25); MAY: Fall from gantry:while getting sample from lorry compartment for water extraction testing a TFA fall down to gantry. (May 17); JUL: MERS Drill: During getting sample from the tank of product after tanker receiving, the sampler was collapse; SEP: A major earthquake occurred in the city. After evacuation, it was observed that one staff were missing. A search and rescue was initiated in the terminal to look for the said personnel (Sept 29); NOV: During tanker receiving while getting the product line sample at the the sampling cock, the attendant has been splash with product at his eye
Compliance
Asset Monitoring | bar: MAR
Business Permit | bar: FEB
MAINTENANCE Monthly Process Checks | bar: JAN
Management of Change | bar: FEB; APR to DEC
Updating of Audit Tracking System/Action Tracker
AIMC Safe Program Review
Scheduled | bar: JAN
Done | bar: JAN

## ILIG Drill Plan
ARCHIPELAGO INDUSTRIAL MANAGEMENT CORPORATION ILIGAN HSSE PLANS Year 2019
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
People
contructor assessement / FLBM | bar: JAN to FEB
Gap Assessment | bar: MAR
PPE Replacement | JAN: 2019-01-30
Physical & Medical Examination incl drug test | FEB: 3-6 Feb-19, Malongayon and Cabarce
Random Drug Test (no of staff per quarter)
Contractor Staff In-Haus Training | AUG: Maintenance Checklist Training
Leadership
Dashboard Meeting
Contractor HSSE Management
Shell Drills
AIMC In House Drill Plan | JAN: Product PUMP on fire, while gantry loading the pump overheat resulting to fire, while ongoing Gantry operations ADO product (Jan 19); APR: Delivery of additive pack resulting to LOPC at near the warehouse (apr 13); JUL: While decanting of Nemo 6164 additive a tankfarm attendant notice the MLI leaking on the tank; OCT: First aid Rescue from warehouse ,a warehouse man suddenly slipped while transfering slop drums to wood pallet (Oct 6)
Compliance
Asset Monitoring | bar: MAR
Business Permit | bar: FEB
MAINTENANCE Monthly Process Checks | bar: JAN
Management of Change | bar: FEB; APR to DEC
Updating of Audit Tracking System/Action Tracker
AIMC Safe Program Review
Scheduled | bar: JAN
Done | JAN: xx-xx-xx

## Villa Drill Plan
ARCHIPELAGO INDUSTRIAL MANAGEMENT CORPORATION Villanueva HSSE PLANS Year 2019
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
People
contructor assessement / FLBM | bar: JAN to FEB
Gap Assessment | bar: MAR
PPE Replacement | JAN: 2019-01-30
Physical & Medical Examination incl drug test | FEB: 3-6 Feb-19, Malongayon and Cabarce
Random Drug Test (no of staff per quarter)
Contractor Staff In-Haus Training
Leadership
Dashboard Meeting
Contractor HSSE Management
Shell Drills
AIMC In House Drill Plan | MAR: First Aid Rescue Gantry operator got burn while taking bitumen sample. (Mar 26); MAY: Marine Portable genset at port on fire due to overheat.(May 26); JUN: Supervisor discovered small fire due to Electrical sparks at the MCC room. (June 18); AUG: Maintenance personnel collapsed due to extreme heat. (17-Aug); OCT: Overheat at the lorry resulted to fire while at gantry. (Oct 19)
Compliance
Asset Monitoring | bar: MAR
Business Permit | bar: FEB
MAINTENANCE Monthly Process Checks | bar: JAN
Management of Change | bar: FEB; APR to DEC
Updating of Audit Tracking System/Action Tracker
AIMC Safe Program Review
Scheduled | bar: JAN
Done | JAN: xx-xx-xx

## Palawan
ARCHIPELAGO INDUSTRIAL MANAGEMENT CORPORATION ILIGAN HSSE PLANS Year 2019
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
People
contructor assessement / FLBM | bar: JAN to FEB
Gap Assessment | bar: MAR
PPE Replacement | JAN: 2019-01-30
Physical & Medical Examination incl drug test | FEB: 3-6 Feb-19, Malongayon and Cabarce
Random Drug Test (no of staff per quarter)
Contractor Staff In-Haus Training | AUG: Maintenance Checklist Training
Leadership
Dashboard Meeting
Contractor HSSE Management
Shell Drills
AIMC In House Drill Plan | bar: JAN; APR; JUL; OCT
Compliance
Asset Monitoring | bar: MAR
Business Permit | bar: FEB
MAINTENANCE Monthly Process Checks | bar: JAN
Management of Change | bar: FEB; APR to DEC
Updating of Audit Tracking System/Action Tracker
AIMC Safe Program Review
Scheduled | bar: JAN
Done | JAN: xx-xx-xx

## Tagbilaran
ARCHIPELAGO INDUSTRIAL MANAGEMENT CORPORATION ILIGAN HSSE PLANS Year 2019
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
People
contructor assessement / FLBM | bar: JAN to FEB
Gap Assessment | bar: MAR
PPE Replacement | JAN: 2019-01-30
Physical & Medical Examination incl drug test | FEB: 3-6 Feb-19, Malongayon and Cabarce
Random Drug Test (no of staff per quarter)
Contractor Staff In-Haus Training | AUG: Maintenance Checklist Training
Leadership
Dashboard Meeting
Contractor HSSE Management
Shell Drills
AIMC In House Drill Plan | bar: JAN; APR; JUL; OCT
Compliance
Asset Monitoring | bar: MAR
Business Permit | bar: FEB
MAINTENANCE Monthly Process Checks | bar: JAN
Management of Change | bar: FEB; APR to DEC
Updating of Audit Tracking System/Action Tracker
AIMC Safe Program Review
Scheduled | bar: JAN
Done | JAN: xx-xx-xx

## Cebu
ARCHIPELAGO INDUSTRIAL MANAGEMENT CORPORATION ILIGAN HSSE PLANS Year 2019
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
People
contructor assessement / FLBM | bar: JAN to FEB
Gap Assessment | bar: MAR
PPE Replacement | JAN: 2019-01-30
Physical & Medical Examination incl drug test | FEB: 3-6 Feb-19, Malongayon and Cabarce
Random Drug Test (no of staff per quarter)
Contractor Staff In-Haus Training
Leadership
Dashboard Meeting
Contractor HSSE Management
Shell Drills
AIMC In House Drill Plan | bar: JAN; APR; JUL; OCT
Compliance
Asset Monitoring | bar: MAR
Business Permit | bar: FEB
MAINTENANCE Monthly Process Checks | bar: JAN
Management of Change | bar: FEB; APR to DEC
Updating of Audit Tracking System/Action Tracker
AIMC Safe Program Review
Scheduled | bar: JAN
Done | JAN: xx-xx-xx