## Sheet1
BUILDING COMMITTEE MEETING NOTES
MEETING AGENDA - August 27, 2024
Item Number | Origin Date | Item Description | Ball In Court
1.1 | 2024-04-25 | Bldg. 3 - Unit 209 Roof | J Callanan
| Discussion on 4/25: | Committee discussed the status on Bldg. 3 leaking roof. Solicited (3) quotes; compared cost and quality of work with a 1/4" taper. Replacing the entire roof on Bldg. 3 will set the protocol for all 15 roofs uncover the problem points. Discussed issues with insurance lifespans on current roofs. Would make sense to issue a changer order to Campany instead of issuing a new contract and notify bonding company of addendum. All agreed as a committee to move forward & present budget number for the upcoming BOD meeting once we receive revised final quote from Campany.
| Discussion on 5/15: | BOD Approved Campany quote. Change Order signed to existing Lakeside Roof Contract. Campany has submitted permits. Awaiting permit approval and schedule from Campany. Expected to be sometime in June. Will give residents plenty of notice as to the commencement and sequence of events. A tab for building 3 has been added to spreadsheet for lakeside roof.
| Discussion on 6/18 | Still held up on permits with Campany, no ETA, its in queue. Once approved schedule will be sent out to residents of Bldg. 3 om timeframe. Material is on site ready waiting to go.
| Discussion on 7/16 | Closeout Meeting Scheduled with Campany today @ 2pm
| Discussion on 8/27 | Goes along with item 1.2,Campany is complete and we are still waiting for O&M Manual. We are holding roughly 40k until received. Ed will follow through with Campany by weeks end.
1.2 | 2024-04-25 | Close Out on Lakeside Roofs | E Nappa
| Discussion on 4/25: | Have Campany bill 100%, hold the 10% retainage until we get the warranty and executed partial lien waiver up to the 90%. We will then create a final lien waiver for the final payment. The lien waiver that Ed initiated that both Joe, Sean agreed on the language floating around. Joe will send to Sean if he cannot find.
| Discussion on 5/15: | City of Fort Lauderdale has signed off. Punch List completed. Campany in the process of submitting O&M Manuals and closeout docs to JBA for approval and sign off. Once we receive this, Campany will then sent us an AIA rep to close out phase 1 and retainage except for $500. This balance will keep contract open for Building #3 change order. Campany is aware that we will not release retainage until we have an approved O&M. Also waiting on (2) paperwork documents required Ed & Sean need to submit to insurance for rebate on Building for 17 and 18. Received building 16. Expected within a week to get this closed out.
| Discussion on 6/18 | Waiting on paperwork from Peter Catallo for the credit and O&M manuels to close this out. Paid everything except for retainage of $500.
1.3 | 2024-04-25 | Various Gutter Repairs | J Callanan
| Discussion on 4/25: | Joe sent the committee quote from Royal Pro, the same contractor from Lakeside roof project. (3) different quotes. Would like to proceed to get them done around the property. The $5,494 includes all of the gutters, dented and clubhouse with 6inch gutters. Recommendation to create a rule to have a standoff for anyone going onto the roof to protect the gutter. To help identify & keep track of damaged gutters going forwards.
| Discussion on 5/15: | Work Completed
| Discussion on 7/16 | Issue with Insurance Company as to whether we are entilited to credit. Ed Nappa following up. Still waiting on closeout documents from Campany
| Discussion on 8/27 | See above 1.1
1.4 | 2024-04-25 | Pitch Pocket Repairs | S Arena
| Discussion on 4/25: | Quote from Bange for approximately $24K to repair selective pitch pockets on Bldgs. 1 - 15. Decided to forego repairs due to overall roof replacement within 2 years in these buildings. Recommended to have Sam update the list to prioritize which are worse and to complete those first and just fill any pockets with additional asphalt material
| Discussion on 5/15: | Going to take a look at a survey to temporarily repair with maintenance crew, due to fact that these roofs will be replaced in the coming years.
| Discussion on 6/18 | Sam did survey with Alex, Sean will be sending list to Joe.
| Discussion on 7/16 | Sean to send out list of pitch pocket repair locations
| Discussion on 8/27 | All pitch pockets and small electrical conduits that are rotted have been filled/sealed with silicone caulking to try to eleviate leaks happening in those general areas. Once the roofs are done over that will solve this problem entireley. Pictures of prior/roofs will be attached to write up.
1.5 | 2024-04-25 | Guard Shack Electrical | Ed Nappa
| Discussion on 4/25: | Fiesher Electric was out there last week and mounted junction boxes on the back of the guard shack. They were given approval to go underground from the guard shack to the back side of the waterfall to enable to guards to read license plates on longer trucks. Hoping that by the end of May that will all be taken care of and closed out. All of the rotting conduits and boxes on the column adjacent to the guard shack will all disappear; leaving 1 new box located at ground level from point to point.
| Discussion on 5/15: | Goes along with 50 year inspection, rotted metering on the column on the right as you enter. Fiesher Electric is about 75% complete. What is delaying them is awaiting response from FPL on new electrical service which has been difficult. As soon as this comes in Sean and Ed will have to coordinate with guard shack. They anticipate to be without power for 1 day, will be brining a generator for backup. Would like to bring Sam with Sean and Ed to look at Fisher drawing, remove junction box and install hand hole to remove everything off column and be able to utilize moving forward. The metering was apart of the 50 year inspection. Expected this to be done in the next 2-3 weeks.
| Discussion on 6/18 | Started concrete patching, going to clean up the column. $2,800 for adding (2) coduits from guard shack to fountain (1) for camera to see larger truck license plates and (1) for future use/cleanup current electrical. Sam will also be painting lights and columns along with other misc touch ups including new shrubs. Asked security committee to add a camera for this location to their camera package going out to bid. Ed will schedule conduit installation.
| Discussion on 7/16 | Concrete down at base of column where electrical was moved to the Guardhouse is being sanded and then painted, all four columns have been painted three of the bases and new shrubs and flowers added. OCB approved $2,800.00 quote to run (2) Conduits undergroundfrom guard shack to fountain.
| Discussion on 8/27 | (2) additional conduits were installed last week by Fisher Electric. (1) for electrical future use and (1) future additional card reader/camera. Sean/Sam can now be proceed to cleaned up landscaping around guard shack for upcoming season. | Painting Complete on Guard Shack. Bahama Shutters to complete this week
1.6 | 2024-04-25 | Bluestream | R Cotter/S Arena
| Discussion on 4/25: | The Bluestream engineer is coming out this coming Wednesday @ 2 o'clock with the building committee to meet at the site to determine if they can install antenna mount in the vicinity of the bike shed to be able to mount the dish. This discussion will give a better understanding of what needs to happen to complete this.
| Discussion on 5/15: | Meet with contractor for Bluestream Contractor a week ago. Confirmed best location is where it currently is. Will be able to install a 20 foot pole and paint pole/antenna a light green shad to blend in with foliage. Contractor is currently making the proposal for Bluestream to approve and then get back to Sean. The contractor will be the one to perform any maintenance and on antenna/microwave and inspecting quarterly. Sean will check with Shannon to confirm that he the dedicated contact for emergencies.
| Discussion on 6/18 | Sean sent out notes, waiting for an additional design with additonal bracket has not heard back yet from Shannon.
| Discussion on 7/16 | Scheduled for week of July 24-26 PE Foundation Design Received
| Discussion on 8/27 | Completed. Still waiting to get confirmation from Blue Stream on company that will be completing preventative maintance. | Sean advises that we will have plan this week
1.7 | 2024-04-25 | Status of 50 yr. Certification | S Arena
| Discussion on 4/25: | The paperwork is in the process of being brought into the city for the structural and electrical ACG. Monday or Tuesday will be in city hall Fort Lauderdale and will be calling Sean once it is accepted to let him know. Dennis Bonner was there signing off on the (3) lakeside roofs and to go to the next step to put them in his reports. Anything that has happened is not part of the 50 year as discussed. Would be a great news piece for membership.
| Discussion on 5/15: | All documentation submitted to City of Fort Lauderdale. Sean & Andres have meeting on May 23, 2024 before Magistrate to finalize approval and signoff. Dennis Bonner has done all of the signoff, just waiting for the other permits for the Lake Side. At that point all will be complete on this matter.
| Discussion on 6/18 | Accepted. 6-8 weeks turnaround for city to sign and return.
| Discussion on 7/16 | Waiting on city document this takes 6-8 weeks.
| Discussion on 8/27 | Completed. Certificate has been received
1.8 | 2024-04-25 | Beach Issues | R Doherty/Sean Arena
| Discussion on 4/25: | The only concern right now is the tractor that we have, it does not do the job and is in fact dangerous. The current machine is leased and would like to see if we could turn it in for a Kubota unit. Sean has already reach out to Casey Gifford about the RTV that we are referring to. Look at United Rental agreement/form to look at liability of signer as it makes economical sense to rent. Sean does not believe we will get nearly what was paid as a resale value.
| Discussion on 5/15: | Talked to Casey Gifford to see if we can turnover to lease the RTV. Sean will follow up to see where they are at. Still awaiting information back on this.
| Discussion on 6/18 | Will not take current tarctor lease back, unless the lease is paid off. $400-500 extra a month for another lease on an RTV. After Hurricane/Turtle season is over e have to push sand to high water mark this year.
| Discussion on 7/16 | Rakiing sand on beach next week between seawall and palm trees
| Discussion on 8/27 | Sean has scheduled beach raking of sand for the week of December 2nd through 6th.
1.9 | 2024-04-25 | Dock Issues | C Hopgood
| Discussion on 4/25: | Several people have inquired about floating docks again. The current permit is for the floating dock for three kayaks. To get an additional one would require additional permitting and fees which Chris has the process. The issue with additional docks is that it is common element not limited common element. It is a material alteration, the docks are "rented" to put your boat in on an annual basis the association owns it.
| Discussion on 5/15: | Met with Ron and walked the docks and identified several open issues. Cleaning outer piers of barnacles, this is routine maintenance, there a couple ponfrons that will need to be pulled out. (2) non working lights have been identified and need to be replaced. Slip(3) there's a piece facia board that need to be tacked back in, added to maintenance. teams list. Several rusted caps on pilings that could catch arms, these will be replaced. Wood has been purchased for boards that need to be fixed. Shrubbery in the last slip has been cut back by maintenance staff. Leftover hoses/lines that will be tossed and an email will be sent out to the association that any leftover items will be thrown out. We should get ride of (1) of the (2) floats used for maintenance, we do not need (2). The poles that hold the float area came up about 4-5 inches and need to be put back in place, added to maintenance. list. Slip 16 is now rentable. Going to talk to some folks about moving some boats around to give some of the bigger boats wider slips.
| Discussion on 6/18 | No Additional Issues. Completed
| Discussion on 7/16 | The metal caps are copper, and somewhat tarnished. We will polish them and repair where needed and then recoat with a clear coat poly. Float is being removed.
| Discussion on 8/27 | Wood has been replaced. Float has been removed. Rick is going to pressur wash and Sam can stain/seal. Metal caps have not been completed yet.
1.1 | 2024-04-25 | Up Date on Ongoing Projects | S Arena
| Discussion on 4/25: | Work going on at the front entrance for beautification. Next weekend tree company will be trimming off coconuts on all the trees throughout the property. Mid to late June we will be doing all trees, hardwoods, palms to prepare for hurricane season. The contract for Beach & Patio has been put together for storage and delivery. It will be discussed on Wednesday, May 1st to the board. There has been back and forth with Beach and Patio but once finished everyone will have all access to it. It takes all of the checks away from Oceanage and onto Beach and Patio.
| Discussion on 5/15: | Coconuts have all been done. Company that did the coconuts will be giving us a quote to trim hard woods, expected to be around mid to late June. Walkthrough tomorrow morning (May 16th) to go through broken pieces as the numbering did not line up.
| Discussion on 6/18 | Getting quotes from Company that has done trees for the enitre property for the past 3/4 years also getting a quote from the company that did cocunuts. Before we can except either one. Previous company - Quality trees has given us a quote for a max of $2,500 a day for hurricane clean up ($25,000 max cleanup). Asked the company that did the cocunuts to give us a quote for the same. Hardwoods and trees against the building will be done Mid July before Hurricane season. Summer list is being put together, starting with the larger items. Summer list needs to be sent to Donna in the next week/half. Will send to make sure all yearly items are on it. Tree planted behind Jodis house. Sam will also be tightening the pavers and planted trees down bottom for fill in. Irrigation was also installed.
| Discussion on 7/16 | Columns and light fixtures have been painted the brown area will be ainted in late September, tree trimming will begin July 15,2024
| Discussion on 8/27 | Reference ongoing projects document. | See Updated List from Sean
1.11 | 2024-04-25 | Building & Grounds Punchlist | S Arena
| Discussion on 4/25: | Just over 50% of it has been accomplished. Sean will send out to see where that is.
| Discussion on 5/15: | About 90 % complete.
| Discussion on 6/18 | 2-3 items left to be completed.
| Discussion on 7/16 | 90% accomplished.
| Discussion on 8/27 | Metal overhangs still outstanding. Randy will send copies of the different punch lists. Sam will go back through the multiple punch lists and cross reference
1.12 | 2024-04-25 | SOP - Windows & Doors | J Callanan & E Nappa
| Discussion on 4/25: | Priority right now is enhancing SOP for windows and doors. Including enhanced SOP, specific material literature, unit opening inspections prior to windows and doors installed. We need to look at creating a list of recommended contractors. Any contractors can fill out a form to be added, the committee can check references and get all documents required. Only when all references and documents are received would they be added to the "recommended" list. This list can be created and distributed. The bigger issue is that we have all openings inspected for any concrete deterioration before the unit is installed. The number of visits from Andre would vary based on unit. Need to decide how Andres cost for inspection is handled. Unit owner, Association or cost split.
| Discussion on 5/15: | Joe and Ed are going through current procedures for residents, most specifications will not change. The main thing that is changing is putting together a list of recommended contractors that are regularly on property and have not had any issues. We are also trying to have these companies provide a standardized pricing for different unit types. The issues that came up from Unit 263 due to improper installation procedures by the contractor has determined that Andrea needs to be onsite anytime windows/doors are being replaced. All openings will be required to be inspect by Andrea for deterioration of rebar, concrete or sill work prior to contractor installing new windows/doors. Status of 263, is complete. Andrea has recommended 2-3 weeks cure time before water test. 163 will be repaired after the water test.
| Discussion on 6/18 | In progress, passing back and forth changes between Ed & Joe. By the end of next week should be completed, then will share. We will then set up a meeting with the building committee for input.
| Discussion on 7/16 | Final draft should be completed and ready for OCB review by next meeting
| Discussion on 8/27 | Draft has been completed and forwarded to building committee members for review and comments before final fraft is completed. Added specified products by Andres, our record engineer, all caulking and sealants. Also that Andres inspects each windows & doors when exisiting units are taken out toinspect for deterioration behidn the wall/sills and building envelope. Also discussing a recommended groupof window contractors. All will be disucssed in September. Once majoirty of association members are on site there will be a in person workshop on these two topics. | In review with Randell Roberfs office. Epect to be finalized for BOD review next week
1.13 | 2024-04-25 | SOP - Unit Owner Construction | J Callanan & E Nappa
| Discussion on 7/16 | Final draft should be completed and ready for OCB review by next meeting
| Discussion on 8/27 | Completed. Waiting for Item 1.12 to be finalized before this is sent out to residents. | Expect to forawrd to Randall Robert's office once Door & Window SOP complete
1.14 | 2024-04-25 | Power Washing/Painting Buildings | S Arena
| Discussion on 4/25: | Couple years ago they had a company come in to wash the buildings and did a very good job. The team can wash them down but it’s a different level of washing and do not have the time to do it in house. Because of the salt from the Ocean, the soft wash needs to be done once or twice on an annual basis. This needs to be a line item for budgeting. Sean will get approximate cost to complete all buildings on an annual basis. Winston has been doing front and back entrance halls interiors. Discussed buying the right low pressure unit to be able to do this in house. Will continue to discuss to see which direction we want to go in.
| Discussion on 5/15: | Sean has called two companies to come out and give quotes on this. It would be possible for our maintenance team to compete 1-2 a month. Sean will be getting a quote for a low pressure power washed to compare.
| Discussion on 6/18 | Quote for power washing was $14k. Will do this in house and has been started. Due to rain this was pushed back but will start back up in a couple weeks. Between now and end of summer we expect all 18 buildings including the clubhouse to be washed down. Going along the base of the building, sealant is being redone/cleaned up. All agree to keep this inhouse.
| Discussion on 7/16 | Windsor has finished 4 buildings is getting to one a week. Winsor has cleaned and paint touch up on four building s to date will be continuing during the summer
| Discussion on 8/27 | Completed through Building 6. Currently working on Building 7.
1.15 | 2024-04-25 | Joint Finance Meeting | J Callanan/Ed Nappa
| Discussion on 4/25: | The two chairs of the committees to see when it is appropriate to have a joint meeting. Joe will reach out to Ed next week.
| Discussion on 5/15: | Building committee is looking to have a joint meeting with the finance committee to bring up budget items for repairs coming up in the next 6 months to 3 years. We will discuss how we will spread them out and how we will pay for them. We will try to accomplish this sometime in June.
| Discussion on 6/18 | Spoke to Ed Pinape, will start 1st finance meeting Monday 6/24. Will be sitting down with them to review McBride invoices. Once we get through the first one we will set something up with the Building Committee to let them know where we stand with the budget.
1.16 | 2024-04-25 | Next Meeting | Open Discussion
| Discussion on 4/25: | 2-3 weeks from now, unless there is something pressing that comes up that cannot be handled via e-mail
Discussion on 5/15:
| Discussion on 7/16 | Ed Nappa trying to set up meeting in August
| Discussion on 8/27 | Ed finalizing write ups on upcoming projects/what needs to be discussed with both committees. Ed Nappa will send to Ed P and they will discuss on 9/4. Anticipate joint meeting to discuss the following week. | Tenatively scheduled for 1st week of November
1.17 | 2024-04-25 | Exterior Lighting | Mike Pucc
| Discussion on 4/25: | Will discuss at the next meeting.
| Discussion on 5/15: | Need to develop Master Plan for exterior lighting and receptacles. Start by doing a survey of property and preparing plan of existing light types and receptacles. Need to look at an overall plan down the line for lighting including turtle lighting. There are no more state grants for turtle lighting, looking to see if the City has any grants available. Looking for volunteers to help on this, as it will take more than one person. Randy has a master plan for lighting, which should include all exterior receptacles. Randy will dig this out. Electrical charging stations for cars has been voted down; too many items on the list right now.
| Discussion on 6/18 | Quiet a bit of work was already completed on this years ago. Grant feel through. Layouts/plans are all done. We can start removing fixtures from trees no longer needed. Will continue to research any grants avaiable. As far as the big picture, we have all documents, plans, layouts we can do things such as removing fixtures and wiring on trees no longer connected. Also can complete some of the ground lighting that complies with the turtle lighting could be done low cost.
| Discussion on 7/16 | Sean Submitted the light plan attachment to Mike Pucciarelli.
| Discussion on 8/27 | Inadequate lighting behind Building 14, installed (6) turtle compliant lights. Susan does not recommend installing these throughout the grounds. We have recently been cited because light has been left on in the clubhouse, signs are now up to turn off when leaving. City sends drones over properties as well to check compliance. Moving forward, Ed will be reaching out to (2)consulants to get foot lighting analysis to then dictate which fixtures can be used. Joe and Ed will hold interviews on consultants. Will refer to previous documents for qty ect. but the suggested fixtures from 5 years ago are obsolete.
2.1 | 2024-05-15 | Bldgs. 16, 17, 18 Interior Ceiling Damage | Sean Area
| Discussion on 5/15 | Need to get (3) Painting quotes to repair/paint water damaged ceilings. Approx. 18 units that have some repair, Sean has the list. Sean & Sam will need to go through to confirm the list. They will take pictures, note which rooms repair is required and separate based on repair needed (Stain that can be sprayed with Tile-X, paint with Kills and paint whole ceiling, any that might need plaster repairs particularly with popcorn ceiling. Oceanage has someone that has done work on the property(Monica Mallon), there is an agreement that was done through our lawyers years ago which allowed people that worked here to work on property. This helps keep costs down, Sean will forward agreement.
| Discussion on 6/18 | 5 Units that have damage. Looking at this in house for the minor ones, for the larger repairs (3 units) we are getting a quote to see what he can do and the cost. Some residents submitted invoices for repair costs, these have not been paid. We are waiting to get all ceilings corrects and pay accordingly.
| Discussion on 7/16 | Windsor will be painting the three with the least water marks 280,286,287 on rainy days. Charlie Silverio will begin in the next two weeks the reamining 5 units
| Discussion on 8/27 | Completed.
2.2 | 2024-05-15 | Contractor T&M Slips | Open Discussion
| Discussion on 5/15 | Going forward Daily T&M Slips are needed from all contractors performing T&M Work on the property. The T&M sheets will give us description of work, where the work was done, materials and labor/equipment needed for work being completed. These will be signed by Sean daily and used as backup for Invoices submitted. No invoice will be paid without Sean signing daily slips. Sean to confirm and issue to Building Committee all Contractor Hourly Rates.
| Discussion on 6/18 | Ed meeting with Sean to review SOP for T&M Work
| Discussion on 7/16 | SOP in place for dealing with T&M Contractors
| Discussion on 8/27 | Completed. Protocol is completed. Job number system has been set up that coincides to a spreadsheet that finance has as well as OBC.
2.3 | 2024-05-15 | Building 14 Electrical Issue | Joe Callanan/Ed Nappa
| Discussion on 5/15 | At the end of April unit owner at Building 14 made us aware they were having an electrical issue. There is a damaged feeder leg which feeds Building 14 and needs to be replaced. It runs from the pad mount to main breaker of Building 14. FPL disconnected faulty conductor and ran a temp feed to get Building 14 up and running. Confirmed that Oceanage owns the cable, getting prices from MJK and Fisher to go underground.
| Discussion on 6/18 | Ed trying to get FPL to put the temp. feeder underground in the existing single conduit until they can have a permanent fix. Fisher is checking on this as well, quoted 30k. Plan moving forward is still in the works.
| Discussion on 7/16 | Joe is reaching out to his contacts at FPL
| Discussion on 8/27 | Joe and Ed reached out to FPL turns out FPL owns current cable from pad to Building 14, but Oceanage owns any repairs/upgrades/reinstallation. Ed has donated the time of his engineering dept and we have established that a 600 amp is needed. Ed is getting (2) quotes, cost is between 20-30k for this building alone. In motion, estimated completion repair timeline is 4-5 weeks. | We have contracted the work out to MJK Electrical. They are finalizing permits and schedule with FPL. Process has been delayed by FPL due to Hurricane Milton
2.4 | 2024-05-15 | Electrical Metering - All buildings | Joe Callanan/Ed Nappa
| Discussion on 5/15 | Building Committee needs to look at replacing metering equipment in all buildings as the current set up is beyond its intended lifespan. Need to develop overall budget & timeline. Price from Fiesher for Building 14 is $25,000 alone. It has been recommended to hire an electrician that can handle the job size. Looking at a $600k total job, need to look at how we are going to phase this out. Lead time for equipment is 6-8 months for equipment. The project is more than just replacing the temp feed underneath. Ed Nappa is going to look at various plan options including a list of prioritized buildings. This will take approximately 3 weeks to put together with pricing. This is a line item in the reserve, and will be discussed with finance after cost and direction of project is established.
| Discussion on 6/18 | We need about 22-24 quads done, looking at approx $25k per quad. All are outdated. Material alone is $10,000 per building. Ed still looking at options on how to save. Material is a 6 month lead time, Ed is still working on a plan to move forward and options to save money. Nobody wants an assessment but this may need to happen for some of these larger items that are not going away. Breaking up the buildings in stages where we can absob itall at once . Oceanfront, lakefront and move to the middle.
| Discussion on 7/16 | Looking at various options for equipment. Ed is working with suppliers for design, cost and leadtimes on equipment. Looking at possibly buying equipment for all buildings at once and financing cost with commerical lenders
| Discussion on 8/27 | Once we get Building 14 behind us, this will be further discussed.
2.5 | 2024-05-15 | Back stairways - Metal Roof Overhangs | Sean Arena
| Discussion on 5/15 | Metal roof overhand are starting to show age, mostly rusting. Need to survey all buildings and develop list of back stairway overhangs that need caulking, sanded, primed & painting with a good metal rust resistant top coat. 28 of them need to be sanded and painted asap. The one 107 and 134 it is recommended to replace, Randy is going to look to see if these cant just be repaired. Two of the doors on the electrical 102 and 106 there are rust bottoms. A few doors that needs to be replaced, Sean is going to get a quote on replacing them with fiberglass doors. This should be an ongoing preventative maintenance item. Winston can get started on fixing overhang. (8) Closets have been replaced. We have a vendor to get a quote for a det of doors to program into budget for the next few years to get the rest replaced.
| Discussion on 6/18 | This will start after the 4th of July. Will start with the worst building 2 unit 107/108 and work our way across.
| Discussion on 7/16 | 4 metal roof overhangs completed as of July 3, 1 metal roof overhang is being completed weekly during the summer schedule.
| Discussion on 8/27 | Out of 45 - 13 have been replaced. 25 are showing rust/deterioation, 5 of those are worse than others, 3 are fine. All will eventually have to be replaced. The ones replaced 5 years ago still look ok. 4 done, about 12 more primed with rust stop primer but not completed. Sean will also transfer report to spreadsheet by building to change the status as we go. Sean going to research alternative fiberglass/composite options that are similar appearance to the metal. Will compare to repairing, and priming/painting the entire metal with a quality paint.
2.6 | 2024-05-15 | Status of renovations at 165 | Open Discussion
| Discussion on 5/15 | Ongoing, demo consisted of tile flooring and kitchen cabinets. Demo is complete, there were some electrical issues that arose once everything was open include splices just buried without a junction box. Right now in a holding pattern waiting to get his kitchen design.
| Discussion on 6/18 | Originally told floor and baseboard were the only things being renovated. Found out that they renovating the kitchen and informed them of the proper paperwork that is required. Sean told they were applied for by Sweeney (contractor) and later found out they were not applied for. Issued a stop work on the unit. Sheet rock, electrical and plumbing was all exposed. Owner has submitted some but not all required documents and work went on to later find out they installed new sheet rock without proper inspections. Before they can continue we will require the proper permit applications and will be present at time of inspection. Major concern is on plumbing stack that was moved. We will require them to obtain rough sign offs from the city. Once these are recvieved, they can continue with work. Sean will be drafting out comments from building committee, will follow email protocol.
| Discussion on 7/16 | Still awaiting permits and inspections by City of Fort Lauderdale
| Discussion on 8/27 | Permits have been received and inspected. Cabinets have been installed.
| Discussion on 10/14 | Work has been complete and signed off by City
2.7 | 2024-05-15 | Painting of railings on property | Sean Areana
| Discussion on 5/15 | All need to be done. A survey has been done on 16, 17, 18.
| Discussion on 6/18 | Paint ordered from JB Paint. Job has been given to Seahorse as discussed. Starting to get in process. Charlie Selverio who is quoting ceilings on lakefront, their company also does exterior painting. Will be picking a stairrail to show us their level of work at their cost. They will be wuoting out the rest of the buildings for us.
| Discussion on 7/16 | Paint delivered, Captain Ronnie has started the hand Rails as of July 11,2024
| Discussion on 8/27 | Buildings on lakeside are completed. Sean will get an update from Ronnie. Sean will update Joe where he is at later today.
2.8 | 2024-05-15 | Carpets on landings. | Sean Areana
| Discussion on 5/15 | Carpets on landings have to be removed. Not in compliance.
| Discussion on 6/18 | Believe its between 16, 17 and 18. Sean will reach out to Randy. Randy had sent an email.
| Discussion on 7/16 | Carpet at back entrance 272/273 removed , carpet at back entrance 286/287 will be done when Sam returns from vacation, the rails in this back stairway were being painted so Sam could not remove the carpet. He will then be painting with a non slip paint.
| Discussion on 8/27 | Carpets have been removed, decks have been repainted. Completed.
2.9 | 2024-05-15 | Columns | Open Discussion
| Discussion on 5/15 | Will add to list for next meeting to spend some time on this. 104, 204, 212, 150, 250. Need to contact Dominic, let him know what is happening. If it is a column, Randy's recommendation is to cut viewing port on second floor to see if there's column damage early on. Then we know which side of the fence the bill is going. Need to sit down with McBride to go over agreement that Sean signed vs. rates agreed upon. Being charged Mobilization multiple times. Paying anywhere from 17k to 30k when it’s a column repair. If he is involved in removing sliders its another 7 to 8k. Sean, Joe and Randy to get together to go through rates/invoices. They will then set up a meeting with the owner of McBride to make sure everyone's on the same page.
| Discussion on 6/18 | Sean/Ed meeting ACG/McBride. A procedure was drafted for Sean/McBride moving forward; sit down with A on clear direction of what we want an how we will proceed with the next few projects. Will walk down the next few projects 150 & 250, 112 & 212, 104 & 204. Will sit down to go over how Sean will set up job number and tracking. Will ask for a budget number from McBride on what he sees visually. Then can discuss the best path forward. Once approved will send out a schedule.
| Discussion on 7/16 | Waiting on Andres reports. He is on vacation.
| Discussion on 8/27 | Sean has reached out to McBride multiple times on pricing, still have not heard back. Sean will reach out to a previous company used and look for an additional company to make this comepetive and backups. Andrea has inspected units and made recommendations but no sheetrock has not been cut out to inspect. Sean will forward Andreas report to the Building committee & Sam. The reports may give the explaination of why the sheet rock did not need to be cut. | Last week we opened up sheetrock in unit to view columns We will have report from Andres this week. Units 104/204, 112/214, 150/250
2.1 | 2024-05-15 | Survey Bluestream vs Comcast | Sean Areana
| Discussion on 5/15 | Sean is going to email to residents that we are looking to do a survey to remove any unnecessary old wiring around the building. In order to do this we will need them to respond who is still running Comcast for tv/internet vs Bluestream. Most of Bluestream is in compliance, attached correctly and run correctly with caps going into building. Most cables not in compliance are Comcast.
| Discussion on 6/18 | Sean will be sending out a survey to residents.
| Discussion on 7/16 | Email sent out Email sent out 7/2/24. So far 5 Comcast residents on property.
| Discussion on 8/27 | Updated to 6 residents that have comcast. Will go survey of proprty to figure out where others that can be taken out and remove them.
2.11 | 2024-05-15 | Visitor Pass | Sean Areana
| Discussion on 5/15 | Sean going to check in to see if they can add it on to pass that they cannot backup. In addition to the street address it should have unit number of authorizing person on pass, it just shows the street address. Turn down anyone that does not have the proper insurance requirements on file will be turned away.
Discussion on 6/18
| Discussion on 7/16 | Waiting for response from TEKWAVE through Roydel, will receive by Monday 7-15-24
| Discussion on 8/27 | Acount manager has not called back. Security Committee could be going a different direction in the future.
2.12 | 2024-05-15 | Kitchen Vent | Open Discussion
| Discussion on 6/18 | Ed talked to attorneys, believe its an agenda item on the board tomorrow.
| Discussion on 7/16 | Issue still with the BOD. New Vent Issue: Complaints from Unit 159 on cooking smells from Unit 259
| Discussion on 8/27 | Microwave does not hook up to vent. The vent can be sealed in the cabinet above the microwave by homeowner. Sean is going to talk with home owner. This is a common problem, when we do roofs in the future we can separate vents.
4.1 | 2024-07-16 | Electrical Room Doors | Sean Areana
| Discussion on 5/15 | Meeting notes will be distributed. If anyone on the call that is not apart of the building committee can email Sean any questions they may have. Next meeting will be scheduled for Mid June.
| Discussion on 6/18 | Meeting notes will be sent out. Next meeting in August.
| Discussion on 7/16 | Sean to order (5) ELECTRICAL ROOM DOORS WITH KEY CODE LOCKS.
| Discussion on 8/27 | Sean has been getting prices from door companies, coming out to give prices. Held up buying locks to see if combines door/lock price is cheaper. | Ordered 8/29/24 - 12 to 14 week lead time
4.2 | 2024-07-16 | Next Meeting | Open Discussion
| Discussion on 5/15 | Meeting notes will be distributed. If anyone on the call that is not apart of the building committee can email Sean any questions they may have. Next meeting will be scheduled for Mid June.
| Discussion on 6/18 | Meeting notes will be sent out. Next meeting in August.
| Discussion on 7/16 | Meeting notes will be sent out. Next meeting in August 27, 2024
| Discussion on 8/27 | No date has been established for next meeting
5.1 | 2024-08-27 | Beach Seawall Repairs | Open Discussion
| Discussion on 8/27 | Seawall has spalling concrete and areas of exposed rebar. Awaiting Andreas detailed report. Hope to have this by weeks end. | Still waiting on Andrea's Report
5.2 | 2024-08-27 | Emergency Repair Report/Line Items | Open Discussion
| Discussion on 8/27 | Recieved emergency repair report from ACG as part of 50 year certification. Can use this report to tie it all together and remove this line item. 48k from McBridge 18k emergency repair work was strictly on stair treds. All invoices have been paid, accounting that needs to be corrected. Working with finance commitee to project funds. Transitions between committee members should hold multiple transition meetings.
5.2 | 2024-08-27 | Engineering Line Item | Open Discussion
| Discussion on 8/27 | We can start July 1st, and as well as add it as a separate line item for next year.
5.3 | 2024-08-27 | Dumpster Gates | Sean Areana
| Discussion on 8/27 | (2) quotes received, 7k difference between the two quotes. Spoken with Largo Mar will split cost 50%. Sean will send the quotes to the building committee to make a recommendation. Includes gates and piece of fence that goes over the wall. Exisiting framing system is okay and can be utilized. | Installation was scheduled for 10/18/24. Cancelled due to high winds. Hope to have installed this week.
6.1 | 2024-10-14 | Unit Mechanical Maintenece Items | Open Discussion
| Discussion on 10/14 | Proposed Service Requirements 1) Dryer Vents - annual 2) AC Condensate Line - semi-annual 3) SS Braided Hoses for Plumbing Shut Offs & Washers 4) Water Heater Inspections by Licensed Plumbers annually for all WH over 5 yrs old and mandatory replacement after 10 yrs old Discussion: 1) How do we implement this? 2) Prepare SOP for this work 3) Resident or Association Responsibility ? 4) Creat Budget if by Association 5) Other Considerations | The committee discussed all items agreeed to continue discussions at future meetings.
7.1 | 2025-02-18 | Annual Cleaning of Dryer Vents | Open Discussion
|  | Sean solcited (3) quote for Dryer Vent Cleaning. The low bid to clean all 180 units was $22,500 from Mold Remediton Pros. Ed Nappa contacted Assocation Counsel for his opinion on the Oceanage taking on the responsibility of the dryer vent cleaning. Counsel responded via letter Februay 06, 2025. This letter has been previously forwarded to committee members. Discuss whether or not this committee agrees the association should move forward with cleaning of vents and propose same to the Board of Directors. | The Oceanage Building Committee (OBC) voted to recommend to the Board of Directors (BOD) hiring Mold Remediation Pros to clean the the dryer vents in all units. Dryer vent cleaningshould continue on a annual basis.
7.2 | 2025-02-18 | Require all unit to install Stainless Steel (SS) Braided Hoses & permantly secure drain hoses to drain | Open Discussion
|  | At the same time we perform the dryer vent cleaning, hoses can be replaced with SS and drainlines be permantly secured. This would be a one time fix for unit owners and paid for by the unit owners. Estimate cost: Less than $100/unit. This was also addressed in counsel's letter for February 6th. Counsel suggested that an ammendment to the Declarations would be necessary. Discuss whether or not the committee should recommend to the Board of Directors that an ammendment to the Declarations be proposed to Assocation Members to make SS hoses and secured drains mandatory for all units | The OBC voted to recommend to the BOD all washing machine hoses be changed to SS hoses in all unit and all drain hoses be permantly affixed with a mechanical fastener. This would be a one time requirment and would be completed at the same time the dryer vents are cleaned
7.3 | 2025-02-18 | Require Annual Inspections of all Water Heaters (WH) over 5 years old. Replace all WH at 10 years | Open Discussion
|  | Require WH inspections by a Licenced Plumber annnualy for all WH over 5 yrs old. Unit owner to submit inpsection letter to Managers Office. All WH's at 10 years require mandatory replacement. This was also addressed in counsel's letter for February 6th. Counsel suggested that an ammendment to the Declarations would be necessary. Discuss whether or not the committee should recommend to the Board of Directors that an ammendment to the Declarations be proposed to Assocation Members for mandatory inspections and replacement of WH as outlined above. | The OBC voted to recommend to the BOD that the mainatenance staff complete a survery of all water heaters (WH) on the propoerty and provide the age on each unit WH
7.4 | 2025-02-18 | Require Engineer oversight of Windows, Sliders & Door Replactment. Inspection of Openings | Open Discussion
|  | Require the Association's Building Envolope Engineer to inspect all openings for rebar or concrete deterioration prior to new windows being installed. Also engineer to inspect the contractor waterproofing and caulking installations upon completion. This was also addressed in counsel's letter for February 6th. Counsel suggested that an ammendment to the Declarations would be necessary. Discuss whether or not the committee should recommend to the Board of Directors that an ammendment to the Declarations be proposed to Assocation Members for 50/50 between the association and unit owners for the cost on the engineer inspections. Cost will vary on the number of window/door units being replaced and number of visits by the engineer. | The OBC voted to recommend to the BOD enginnering inspections by the Assocation of all new window and door installation. Assocation Enginer to inspect each opening prior to the new window/door being installed, along with a final inspection including water tests of all openings. Cost for enginnerign inspections to br split 50/50 between unit onwer and assocation.
7.5 | 2025-02-18 | Review of Association requirements for Dumpster and/or Storage Units on property | Randy Cotter
|  | Please refer to Randy's emails of 2/12 and 2/16 on dumpster regulations on propery | Dumpster regulations to be clarifed and recommended to the Rules Committee
7.6 | 2025-02-18 | Review of Association requirements for Unit Owner's renovation work and document approval | Randy Cotter
|  | Please refer to Randy's emails of 2/12 and 2/16 regulations on propery | Joe Callanan & Ed Nappa to distribute the new SOP on renovation work to committee member for fina l review prior to senfing to BOD for approval.
7.7 | 2025-02-18 | Update on the list of current units with water infiltration issues and contractor walk throughs | Frank Shannon
|  | Frank Shannon has walked the property with 3 contractors to solicite quotes for concrete and waterproofing repairs | OBC voted to recommend to the BOB to have Krips proceed on a time and material basis on Units 134/234 and 160/260