## Template
Time in ET | Conference Schedule | Location | Executive Director | Conference Director | Communications Director | Staff 1 | Staff 2 | Staff 3 | Staff 4 | Staff 5
7am
7:15am
7:30am
7:45am
8am
8:15am
8:30am
8:45am
9am
9:15am
9:30am
9:45am
10am
10:15am
10:30am
10:45am
11am
11:15am
11:30am
11:45am
12pm
12:15pm
12:30pm
12:45pm
1pm
1:15pm
1:30pm
1:45pm
2pm
2:15pm
2:30pm
2:45pm
3pm
3:15pm
3:30pm
3:45pm
4pm
4:15pm
4:30pm
4:45pm
5pm
5:15pm
5:30pm
5:45pm
6pm
6:15pm
6:30pm
6:45pm

## Example
Time in ET | Conference Schedule | Location | Executive Director | Conference Director | Communications Director | Staff 1 | Staff 2 | Staff 3 | Staff 4 | Staff 5
6am |  |  |  | Final Walkthrough & AV Check |  |  | Final AV walkthrough of all rooms |  | Ensure all breakout rooms are set as planned
6:15am
6:30am |  |  |  | Staff & Volunteer Briefing + Supply Check | Final Messaging Review & Press Check-In | Oversee registration desk & volunteer check-in |  | Greet keynote and VIP speakers in Green Room
6:45am | [9 empty] | Staff mobile app help desk at registration
7am |  |  | Private Breakfast & Daily Briefing
7:15am |  |  |  | Oversee Registration & Breakfast Setup | Monitor Registration & Capture Early Buzz
7:30am | Registration & Breakfast | Summit Lobby & Trailhead Café | Meet with Registration Staff |  |  |  | Manage live stream, slides, and audio cues
7:45am
8am | [7 empty] | Cue ED and keynote speaker | Respond to session room issues: chairs, tables, A/C
8:15am |  |  | Deliver welcome remarks
8:30am | Opening Remarks & Keynote Session | Grand Horizon Ballroom |  | Backstage for Keynote Support | Support Keynote Session – Live Coverage | Track no-shows and help late check-ins
8:45am | [9 empty] | Assist attendees with session schedule and room finder
9am
9:15am |  |  |  | Monitor Breakout Session Launch | Press Coordination + Breakout Session Drop-ins
9:30am | Breakout Session Block 1 | See Schedule | Press & Media Briefing |  |  |  | Support virtual tech for hybrid session | Check-in with breakout speakers
9:45am
10am |  |  | Coffee with Sponsors |  |  | Manage lost-and-found and accessibility requests |  |  | Float between rooms to replenish pens/paper, confirm session counts
10:15am
10:30am | Morning Break | The Junction Lounge |  | Touch Base with Catering, Expo & Security & Session Monitoring | Exhibitor Check-In |  |  |  |  | Monitor app analytics and push poll notifications
10:45am |  |  | Drop-in: Org Strategy Breakout
11am | Breakout Session Block 2 | See Schedule |  |  | Capture Breakout Highlights | Oversee lunch ticket scanning and VIP table assignments
11:15am
11:30am |  |  | Meet with Board Chair
11:45am
12pm | Lunch & Networking | Skyline Terrace & Garden Ballroom | Lunch & Sponsor Recognition Remarks | Lunch Oversight & Midday Team Check-In | Lunch: Sponsor Recognition Coverage | Lunch/Break | Lunch/Break | Eat at reserved VIP lunch table | Eat lunch in shifts with volunteers | Grab lunch and post mid-day engagement challenge in the app
12:15pm
12:30pm
12:45pm
1pm
1:15pm | [6 empty] | Set up AV for closing session |  | Prepare Grand Horizon Ballroom for closing session
1:30pm | Breakout Session Block 3 | See Schedule | One-on-One Meetings | Breakout Sessions + Social Media Coordination | Media Interviews + Attendee Testimonials | Session Support |  | Prep closing panelists and brief them backstage |  | Manage live Q&A and polling for North Summit Room session
1:45pm
2pm
2:15pm |  |  | Break / Review Closing Notes
2:30pm | Afternoon Break | Recharge Bar & Expo Commons |  | Staff Break Rotation | Email Draft
2:45pm
3pm | Featured Speaker | Grand Horizon Ballroom | General Session & Closing Remarks | General Session & Conference Close | General Session Coverage + Closing Highlights | Staff late registration kiosk | Run AV booth | Monitor backstage during general session | Monitor room temperature, lighting, and traffic flow | Upload photo gallery to app
3:15pm
3:30pm
3:45pm
4pm | Wrap-up Panel | Grand Horizon Ballroom
4:15pm
4:30pm | Networking Reception | Riverlight Rooftop | Evening Reception – Host & Circulate | Reception Support + Strike Prep | Evening Reception – Social & Press Wrap-Up | Reception Support | Test reception playlist, mic, and uplighting | Accompany keynote to reception for photos and press | Begin strike of signage and room resets for next day | Staff app booth at reception for survey completion prize
4:45pm
5pm
5:15pm
5:30pm
5:45pm
6pm
6:15pm |  | The Collider Room | Post-Reception Debrief with Events Team | Post-Reception Debrief with Events Team | Debrief & Next-Day Prep | Debrief & Next-Day Prep | Debrief & Next-Day Prep | Debrief & Next-Day Prep | Debrief & Next-Day Prep | Debrief & Next-Day Prep
6:30pm
6:45pm