Workplan Template

Local Implementation Onboarding

Implementation Site / Circuit / County: __________________________

School System(s): _______________________________________________

Lead Agency: ____________________________________________________

Primary HFI Contact: ____________________________________________

Date Prepared: __________________________________________________

Version: _________________________________________________________

Prepared By: _____________________________________________________

Reviewed / Approved By: __________________________________________

# TABLE OF CONTENTS

i

TABLE OF CONTENTS	ii

1. Purpose of This Workplan	1

2. Local Program Overview	2

2.1 Program Statement	2

2.2 Local Goals	2

2.3 Population Served	2

3. Program Governance and Leadership	4

3.1 Lead Agency and Decision-Making Structure	4

3.2 Local Steering Team	4

3.3 Governance Questions	5

4. HFI Process Flow	6

4.1 HFI Process Map	6

5. Triggering Events and Referral Criteria	9

5.1 Triggering Events	9

5.2 Referral Source	9

5.3 Referral Intake Checklist	10

6. Parent / Guardian Communication	11

6.1 Initial Communication	11

6.2 Parent Communication Script / Letter Elements	11

6.3 Contact Attempts	12

6.4 Non-Response Protocol	12

7. Family Engagement and Consent	14

7.1 Engagement Approach	14

7.2 Consent and Information Sharing	14

8. Family Assessment Process	16

8.1 Assessment Tool	16

8.2 Assessment Workflow	16

8.3 Assessment Summary	17

8.4 Determination After Assessment	18

9. Individualized Intervention Plan (IIP)	19

9.1 IIP Development	19

9.2 Service Plan Template	19

10. Interagency Team (IAT) Meeting Process	21

10.1 Criteria for IAT Meeting	21

10.2 IAT Participants	21

10.3 IAT Meeting Preparation	22

10.4 IAT Meeting Agenda	23

10.5 IAT Meeting Notes	23

11. Community Service Provider Coordination	24

11.1 Provider Network	24

11.2 Referral Follow-Up	25

12. Monitoring and Follow-Up	26

12.1 Monitoring Period	26

12.2 Monitoring Activities	26

12.3 Monitoring Log	26

13. Re-evaluation, Closure, and Re-Entry	27

13.1 Re-evaluation Criteria	27

13.2 Closure Criteria	27

13.3 Closure Summary – Refer to Case Management System for Closure Assessment	28

13.4 Re-Entry	28

14. Staffing Plan	29

14.1 Staffing Model	29

14.2 Caseload Expectations	29

15. Training Plan	30

15.1 Required Training	30

HFI program overview	30

[All Personnel]	30

[Insert]	30

[Insert]	30

[Insert]	30

15.2 Training Completion Log	31

16. Data Protocols and Documentation	32

16.1 HFI Case Management System	32

16.2 Required Data Elements for HFI Case Management System	33

16.3 Data Quality Controls	33

17. Program Metrics and Reporting	35

17.1 Output Measures	35

17.2 Outcome Measures	35

17.3 Reporting Schedule	36

18. Community Engagement Strategy	37

18.1 Partner Identification	37

18.2 Community Partner Engagement Plan	37

18.3 Communication with Community Partners	38

19. Implementation Timeline	39

19.1 Planning and Launch Timeline	39

20. Risk Areas and Mitigation Plan	42

21. Quality Assurance and Fidelity Review	43

21.1 Fidelity Expectations	43

21.2 Case Review Process	43

22. Required Attachments and Local Templates	45

23. Final Local Approval	46

24. Revision History	47

## 1. Purpose of This Workplan

This workplan is intended to help the local Helping Families Initiative Team define, document, and organize the workflow for implementing HFI in a consistent and understandable manner.

The workplan should describe how the local HFI Team will identify students and families, communicate with parents or guardians, conduct family assessments as needed, coordinate Interagency Team Meetings when appropriate, connect families with needed services, monitor progress, document outcomes, and maintain accountability for each step of the process.

This document should be completed by the local District Attorney and HFI Team Leader in coordination with school system representatives, community service partners, and the HFI State Support Team.

## 2. Local Program Overview

### 2.1 Program Statement

Complete the following statement:

The Helping Families Initiative in [circuit/county/school system] is designed to support students and families by addressing the root causes of:

- Excessive unexcused absences;

- Serious or repeated school behavior violations of the codes of student conduct;

- Chronic absenteeism (excused and unexcused absences);

- Family and/or neighborhood issues affecting school attendance or behavior;

- Unmet family and/or needs that may be addressed through coordinated community services.

The local HFI program will operate as an early-intervention and family-support process intended to connect families with appropriate resources before issues escalate further.

### 2.2 Local Goals

Identify the primary goals of the local HFI implementation.

| Goal | Description | How Success Will Be Measured |
| --- | --- | --- |
| Reduce excessive unexcused absences | [Compare annual data] | [Most recent data show improvement] |
| Improve student behavior | [Compare annual data] | [Most recent data show improvement] |
| Connect families with services | [Compare annual data] | [Most recent data show improvement] |
| Reduce escalation to early warning truancy programs | [Compare annual data] | [Most recent data show improvement] |
| Reduce escalation to court intervention | [Compare annual data] | [Most recent data show improvement] |
| Other local goal | [Compare annual data] | [Most recent data show improvement] |

### 2.3 Population Served

Define the population HFI will serve locally.

- Which school systems, schools, or grade levels are included in this implementation?

- Response:
All school systems or schools in a judicial circuit may participate.

- Are there any schools, grades, programs, or populations excluded from the initial implementation?

- Response:
No one is excluded. However, HFI data begins with kindergarten.

- Will HFI serve families only after a school referral, or may families also self-refer or be referred by community partners?

- Response:
Yes. Families may self-refer. Community Partners may refer.

- Are court-involved students and/or families eligible, or is HFI limited to prevention and early intervention?

- Response:
Students/families involved in the criminal justice system are ineligible.

## 3. Program Governance and Leadership

### 3.1 Lead Agency and Decision-Making Structure

Identify the lead agency and leadership structure for the local HFI program.

- District Attorney: Provides executive oversight of the local HFI site, ensures alignment with legal and attendance-enforcement responsibilities, and serves as the reporting authority for HFI personnel within the judicial circuit.

- Team Leader: Coordinates local HFI operations, supervises HFI case officers, maintains liaison with schools and community agencies, leads Interagency Team Meetings, and manages initial communication from the District Attorney to families.

- Case Officer: Delivers direct outreach and family services, completes needs assessments as needed, tracks progress, and supports day-to-day case logistics for the HFI Team.

- State Support Team: Provides statewide training, technical, analytical, and operational support to local HFI sites, including support for assessment tools and computer systems.

| Role | Name / Position | Organization | Responsibilities |
| --- | --- | --- | --- |
| Program Sponsor | District Attorney | [Insert] | [Insert] |
| HFI Program / Team Leader | [Team Leader] | [Insert] | [Insert] |
| School System Lead | [Supt] | [Insert] | [Insert] |
| Data / Reporting Lead | [ALSDE] | ALSDE | [Insert] |
| Community Partner Coordinator | [Team Leader] | [Insert] | [Insert] |
| Training Coordinator | [State Support Team and Team Leader] | [Insert] | [Insert] |
| Quality Control / Fidelity Lead | [Team Leader and State Support Team] | [Insert] | [Insert] |

### 3.2 Local Steering Team

List the members of the local HFI steering or leadership team.

| Name | Organization | Role in HFI | Meeting Frequency |
| --- | --- | --- | --- |
| [District Attorney] | Office of the District Attorney | Local Leadership | [Insert] |
| [Team Leader] | Office of the District Attorney | Daily Operations | [Insert] |
| [State Support Team] | Helping Families Initiative, Inc. | Statewide Support | [Insert] |

### 3.3 Governance Questions

- Who has authority to approve local HFI procedures?

- Response:
District Attorney with advice from the State Support Team

- Who may change referral criteria or timelines?

- Response:
District Attorney in consultation with school system superintendent and State Support Team

- How often will leadership review program performance and implementation fidelity?

- Response:
Daily monitoring, Monthly monitoring reports, quarterly reports, and as needed

- How will unresolved operational issues be escalated?

- Response:
Team meetings, DA, referral to state support team

## 4. HFI Process Flow

The local HFI workflow will generally follow this sequence: [insert process flow diagram]

- Triggering event occurs. {unexcused absences, serious bad behaviors, referrals]

- School or authorized party refers the student/family to HFI.

- HFI sends a letter or other communication to the parent or guardian.

- HFI attempts family contact and engagement.

- HFI conducts a family assessment using the North Carolina Family Assessment tool, if necessary.

- HFI identifies family strengths, needs, barriers, and service priorities.

- HFI schedules and conducts an Interagency Team Meeting (IAT), if needed.

- HFI and the family contact or coordinate with service agencies.

- HFI monitors the family’s progress and student outcomes.

- HFI determines whether continued monitoring, additional services, escalation, or closure is appropriate.

### 4.1 HFI Process Map

The HFI process begins when a student is referred to the HFI/DA Office either through the case management system or by direct referral. HFI determines eligibility of the student/family for inclusion in the Helping Families Initiative. In the case management system, this is coded as “new offense”.

If the “new offense” involves unexcused absences, a warning letter, email, and/or text message is sent to the parent/guardian. While each circuit sets its own threshold for unexcused absences that trigger a new offense based on unexcused absences, early intervention remains the most effective approach. After the warning is sent, the case status is then updated from “new offense” to “closed.” In some cases, if an immediate need is identified, the case may be moved to the assessment / “in progress” stage rather than being closed.

If the “new offense” involves discipline violations, a warning letter, email, and/or text message is sent to the parent/guardian. The case status is then updated from “new offense” to “closed.” In some cases, if an immediate need is identified, the case may be moved to the assessment / “in progress” stage rather than being closed.

If unexcused absences and/or discipline violations continue after the warning, an “assessment letter” is sent inviting the parent/guardian and student to meet. At this point, the case status is changed from “closed” or “new offense” to “in progress.”

If the parent/guardian declines the assessment meeting, the case status is updated from “in progress” to “closed.” If the parent/guardian agrees to meet, the case status is changed from “in progress” to “active/open.”

Once the case is “active/open”, referrals for immediate needs may begin. The case officer should conduct interviews and/or home visits with the family, and the initial North Carolina Family Assessment (NCFAS) is completed. Three priority areas for intervention are identified.

An Individual Intervention Plan (IIP) is then developed for the student and family, with referrals coordinated through the Interagency Team (IAT). The case officer provides the family with the IIP and all relevant referral information. The family then signs and agrees with the IIP. HFI then continues to monitor progress through “follow-up” communication to ensure services are being utilized.

If the student and/or family demonstrate sufficient improvement, the case officer completes a “closure” NCFAS, and the case status is updated from “active/open” to “closed.”

If insufficient progress is made, the case officer completes a “reassessment” NCFAS. The case is then returned to the IAT to revise the IIP and referral plan, and monitoring by the case officer continues.

Describe the local workflow from referral through closure.

| Step | Local Activity | Responsible Party | Target Timeline | Required Documentation |
| --- | --- | --- | --- | --- |
| Triggering event | [Insert] | [Insert] | [Insert] | [Insert] |
| Referral to HFI | [Insert] | [Insert] | [Insert] | [Insert] |
| Parent / guardian communication | [Insert] | [Insert] | [Insert] | [Insert] |
| Family assessment | [Insert] | [Insert] | [Insert] | [Insert] |
| Service planning | [Insert] | [Insert] | [Insert] | [Insert] |
| IAT meeting | [Insert] | [Insert] | [Insert] | [Insert] |
| Family signs IIP | [Insert] | [Insert] | [Insert] | [Insert] |
| Agency referrals | [Insert] | [Insert] | [Insert] | [Insert] |
| Monitoring | [Insert] | [Insert] | [Insert] | [Insert] |
| Closure or recycle the process | [Insert] | [Insert] | [Insert] | [Insert] |

## 5. Triggering Events and Referral Criteria

### 5.1 Triggering Events

Define the events that will trigger HFI involvement.

| Trigger Category | Local Definition | Referral Threshold | Source of Information |
| --- | --- | --- | --- |
| Excessive unexcused absences | [Insert] | [Insert] | [Insert] |
| Serious behavior incident | [Insert] | [Insert] | [Insert] |
| School administrator concern | [Insert] | [Insert] | [Insert] |
| Parent Referrals | [Insert] | [Insert] | [Insert] |
| Community Alerts | [Insert] | [Insert] | [Insert] |

### 5.2 Referral Source

- Who may refer a student or family to HFI?

- Response:
School, community partner

- What information must be included in a referral?

- Response:
Student name, school, parent/guardian, concern, context

- How will referrals be submitted?

- Response:
Data download from school system, referrals from community alerts

- Who reviews referrals for completeness and eligibility?

- Response:
Team Leader; Case Officer

- What is the target timeframe for reviewing a referral after receipt?

- Response:
24-72 hours

### 5.3 Referral Intake Checklist

| Required Intake Item | Required? | Responsible Party | Notes |
| --- | --- | --- | --- |
| Student name | Yes / No | [Insert] | [Insert] |
| Student ID | Yes / No | [Insert] | [Insert] |
| School | Yes / No | [Insert] | [Insert] |
| Grade | Yes / No | [Insert] | [Insert] |
| Date of Birth | Yes / No | [Insert] | [Insert] |
| Soc Sec Number | Yes / No | [Insert] | [Insert] |
| Parent / guardian name | Yes / No | [Insert] | [Insert] |
| Parent / guardian contact information | Yes / No | [Insert] | [Insert] |
| Attendance record | Yes / No | [Insert] | [Insert] |
| Behavior record | Yes / No | [Insert] | [Insert] |
| Prior school interventions | Yes / No | [Insert] | [Insert] |
| Known safety concerns | Yes / No | [Insert] | [Insert] |
| Language / translation needs | Yes / No | [Insert] | [Insert] |
| Existing service involvement | Yes / No | [Insert] | [Insert] |
| Other | Yes / No | [Insert] | [Insert] |

## 6. Parent / Guardian Communication

### 6.1 Initial Communication

Describe the first communication to the parent or guardian.

- What form of communication will be used?

  - Letter;

  - Phone call;

  - Email;

  - Text message;

  - School meeting;

  - Home visit;

  - Other: [Insert].

- Who sends the initial communication?

- Response:
DA authorizes, HFI Team sends

- When is the communication sent after the triggering event or referral?

- Response:
24-72 hours

- What tone and message should the communication convey?

- Response:
Professional, polite, empathetic, factual

- What information must be included in the communication?

- Response:
Specific dates, facts, understanding of explanations

### 6.2 Parent Communication Script / Letter Elements

The initial communication should generally include the following elements. Local teams should customize as appropriate.

| Element – Suggested Information to be included | Local Wording / Notes |
| --- | --- |
| Identification of student and school concern | [Insert] |
| Explanation of HFI purpose | [Insert] |
| Statement that HFI is intended to help the family | [Insert] |
| Request for parent / guardian contact | [Insert] |
| Description of next steps | [Insert] |
| Contact information for HFI personnel | [Insert] |
| Language access / accommodation information | [Insert] |
| Confidentiality statement (subsequent letter) | [Insert] |
| Deadline or requested response date (subsequent letter) | [Insert] |

### 6.3 Contact Attempts

Define how HFI will document attempts to reach the family.

| Contact Attempt | Method | Responsible Party | Timeline | Documentation Required |
| --- | --- | --- | --- | --- |
| Attempt 1 or | [Letter] | [Insert] | [Insert] | [Insert] |
| Attempt 2 or | [Text] | [Insert] | [Insert] | [Insert] |
| Attempt 3 or | [Phone Call] | [Insert] | [Insert] | [Insert] |
| Additional attempts | [Meeting] | [Insert] | [Insert] | [Insert] |

### 6.4 Non-Response Protocol

- What happens if the parent or guardian does not respond?

- Response:
Letter – no response required; Subsequent Letters: Follow up phone call; or, other follow up procedure; attempt to locate

- When should the school be notified of non-response?

- Response:
Initial Letter – no response required; Subsequent Letters; depends on nature of referral

- Are home visits permitted or required?

- Response:
Depends on nature of referral; where in the HFI process the case is; circumstances of the family situation

- When should the case be re-evaluated for additional review?

- Response:
Depends on nature of referral; where in the HFI process the case is; circumstances of the family situation

## 7. Family Engagement and Consent

### 7.1 Engagement Approach

Describe the local approach to engaging families.

- How will staff explain HFI to the family?

- Response:
Direct conversation, Program literature, web site,

- How will staff emphasize that HFI is intended to identify needs and connect the family to services?

- Response:
Conducted during initial program explanation to family.

- How will staff identify immediate concerns, barriers, or urgent needs?

- Response:
North Carolina Family Assessment. Barriers or urgent needs may be initiated by Case Officers or Team Leaders.

- How will staff address distrust, fear, or reluctance to participate?

- Response:
HFI personnel reconfirm on a case by case basis the fundamental purpose and processed of the Heling Families Initiative.

### 7.2 Consent and Information Sharing

- What consent forms are required before information is shared with service providers?

- Response:
Confidentiality forms

- Who obtains consent?

- Response:
Local HFI personnel (Case Officers and Team Leaders

- Where are consent forms stored?

- Response:
Release and Confidentiality Form are stored in the Case Management System

- How often must consent be updated?

- Response:
Consent forms are updated for service agencies as additional needs are identified.

- What information may be shared with schools, agencies, or community partners?

- Response:
Information pertinent to the IAT plan/meeting

- What information may not be shared without additional authorization?

- Response:
Information that is not pertinent to the IAT plan/meeting

## 8. Family Assessment Process

### 8.1 Assessment Tool

The local HFI Team will use the North Carolina Family Assessment tool to identify family strengths, needs, barriers, and service priorities.

Complete the following:

| Items | Local Response |
| --- | --- |
| Exact assessment tool/version used | [NCFAS] |
| License or authorization confirmed? | License authorization is the responsibility of the State Support Team. |
| Staff authorized to administer assessment | [Team Leader, Case Officer] |
| Required training completed? | Team Leader, Case Officer |
| Where assessment records are stored | Case Management System |
| Who may access assessment results | [Case Officers, Team Leaders, State Support Team] |
| When assessment must be completed | [Local Team Decision] |
| Whether reassessment is required | [Local Team Decision] |

### 8.2 Assessment Workflow

- When does the initial assessment process begin?

- Response:
24-72 hours

- Where may the assessment occur?

  - School

  - HFI office

  - Family home

  - Community location

  - Virtual meeting

  - Phone

  - Other: _________________________________

- Who participates in the assessment?

- Response:
Parents, guardians, school personnel, student

- What collateral information may be reviewed before completing the assessment?

- Response:
Context of family situation, not directly from the family, other sources of Information, School sourced information, Criminal History

- How are urgent safety, health, housing, food, or crisis needs identified during the assessment?

- Response:
Refer to NCFAS instrument

- How are family strengths documented?

- Response:
Refer to NCFAS instrument

- How are family needs prioritized?

- Response:
Judgement of the case officer and top three most pressing goals

### 8.3 Assessment Summary

After completing the assessment, staff should prepare a summary of the family’s strengths, needs, and recommended next steps.

Refer to the NCFAS instrument, domain scores,  review NCFAS and align domains. Generally, only three (3) needs are addressed at the first assessment.

| Domain Name | Description / Details |
| --- | --- |
| 1. Environment | Evaluates physical living conditions, including housing quality, safety, and access to basic community resources like utilities and transportation . |
| 2. Parental Capabilities | Assesses caregiver knowledge, mental health, substance use, and ability to protect and nurture children. |
| 3. Family Interactions | Analyzes relational dynamics, such as communication patterns, conflict resolution, and the emotional bond between caregivers and children. |
| 4. Family Safety | Gauges the level of safety within the home, specifically monitoring the presence or risk of abuse and neglect. |
| 5. Child Well-Being | Measures indicators of children's emotional, behavioral, and physical health, including developmental progress . |
| 6. Social/Community Life | Examines the quality of external networks, social support, extended family, and community ties . |
| 7. Self-Sufficiency | Evaluates the family's ability to manage finances, employment, and basic needs. |
| 8. Family Health | Measures the overall health status and access to medical/dental care for all family members . |
| 9. Caregiver/Child Ambivalence | Assesses the emotional barriers, attachment issues, or ambivalence between a caregiver and the child. |
| 10. Readiness for Reunification | Used strictly in reunification cases to measure the family's preparedness to safely bring the child back home. |
| 11. Trauma / Well-Being | An optional package measuring the recovery of children and caregivers following traumatic events. |

### 8.4 Determination After Assessment

Based on the assessment, identify the next step.

| Possible Next Step | Criteria | Responsible Party | Documentation |
| --- | --- | --- | --- |
| No further action / close | [Insert] | [Insert] | [Insert] |
| Monitor only | [Insert] | [Insert] | [Insert] |
| Schedule IAT meeting | [Insert] | [Insert] | [Insert] |
| Family sign IIP Agreement | [Insert] | [Insert] | [Insert] |
| IIP is implemented | [Insert] | [Insert] | [Insert] |
| Monitor IIP progress | [Insert] | [Insert] | [Insert] |
| Re-evaluation for urgent review | [Insert] | [Insert] | [Insert] |
| Other | [Insert] | [Insert] | [Insert] |

## 9. Individualized Intervention Plan (IIP)

### 9.1 IIP Development

Describe how the HFI Team will develop an individualized plan for the family.

- Who is responsible for preparing the service plan?

- Response:
Case Officers, Team Leader

- How will the family participate in creating the plan?

- Response:
Follow up interview with case officer, elicit buy in. Include parents/guardian, students

- How will the plan connect identified needs to specific services or actions?

- Response:
Plan is based on top three priorities identified by NCFAS. Set goals, identify helping agencies

- How will the plan identify what the family agrees to do?

- Response:
Family signs and agrees to follow the plan.

- How will the plan identify what HFI, the school, and partner agencies agree to do?

- Response:
Based on identified needs, partner agency capacity, specific goals, guide the family to self-help contact with agencies.

### 9.2 Service Plan Template

Based on existing IIP section of Case Management Database System

| Identified Need | Family Goal | Responsible Party | Target Date | Follow-Up Method | Status |
| --- | --- | --- | --- | --- | --- |
| [Top Need #1] | [Depends on Need] | [IAT and Agency] | [Insert] | [Check with family; check with agency] | Not Started / In Progress / Complete |
| [Top Need #2] | [Depends on Need] | [IAT and Agency] | [Insert] | [Insert] | Not Started / In Progress / Complete |
| [Top Need #3] | [Depends on Need] | [IAT and Agency] | [Insert] | [Insert] | Not Started / In Progress / Complete |

## 10. Interagency Team (IAT) Meeting Process

### 10.1 Criteria for IAT Meeting

Define when an Interagency Team Meeting should be scheduled.

An IAT meeting should be considered when:

- IAT meetings should take place after the Individualized Intervention Plan has been created.

In addition, IAT meetings may take place when:

- The assessment identifies multiple family needs requiring coordinated services;

- The family has needs that cannot be addressed by a single agency or single solution;

- Prior referrals have not resolved the underlying issues;

- Attendance or behavior issues continue after initial HFI contact;

- The family would benefit from direct coordination among school, social service, and community providers;

- Immediate or complex barriers require a coordinated response.

### 10.2 IAT Participants

Identify the agencies and individuals that may participate in IAT meetings.

| Participant / Agency | Contact Person | Contact Information | Participation Method |
| --- | --- | --- | --- |
| District Attorney or designee | [Insert] | [Insert] | In person / Virtual / Phone |
| Team Leader | [Insert] | [Insert] | In person / Virtual / Phone |
| Case Officer | [Insert] | [Insert] | In person / Virtual / Phone |
| School Representative | [Insert] | [Insert] | In person / Virtual / Phone |
| Department of Human Resources | [Insert] | [Insert] | In person / Virtual / Phone |
| Mental Health provider | [Insert] | [Insert] | In person / Virtual / Phone |
| Department of Health | [Insert] | [Insert] | In person / Virtual / Phone |
| Housing provider | [Insert] | [Insert] | In person / Virtual / Phone |
| Food / clothing provider | [Insert] | [Insert] | In person / Virtual / Phone |
| Law Enforcement | [Insert] | [Insert] | In person / Virtual / Phone |
| Mentoring provider | [Insert] | [Insert] | In person / Virtual / Phone |
| Legal aid provider | [Insert] | [Insert] | In person / Virtual / Phone |
| Employment / workforce provider | [Insert] | [Insert] | In person / Virtual / Phone |
| Other | [Insert] | [Insert] | In person / Virtual / Phone |

### 10.3 IAT Meeting Preparation

| Preparation Task | Responsible Party | Timeline | Completed? | Notes |
| --- | --- | --- | --- | --- |
| Confirm family consent | Case Officer or Team Leader | [Insert] | Yes / No | [Insert] |
| Review assessment summary | Case Officer or Team Leader | [Insert] | Yes / No | [Insert] |
| Identify priority needs and goals | Case Officer or Team Leader | [Insert] | Yes / No | [Insert] |
| Identify required agencies | Case Officer or Team Leader | [Insert] | Yes / No | [Insert] |
| Schedule meeting | Case Officer or Team Leader | [Insert] | Yes / No | [Insert] |
| Send meeting notice | Case Officer or Team Leader | [Insert] | Yes / No | [Insert] |
| Prepare agenda | Case Officer or Team Leader | [Insert] | Yes / No | [Insert] |
| Confirm interpreter or accommodation needs | Case Officer or Team Leader | [Insert] | Yes / No | [Insert] |
| Prepare family-friendly explanation of meeting purpose | Case Officer or Team Leader] | [Insert] | Yes / No | [Insert] |

### 10.4 IAT Meeting Agenda

Suggested agenda (for New Cases and Review of Active Cases):

- Welcome and introductions.

- Explanation of HFI and purpose of IAT meeting.

- Confirmation of consent and confidentiality expectations.

- Family perspective: strengths, concerns, and goals.

- School perspective: attendance, behavior, academic concerns, and prior interventions.

- Summary of assessment findings.

- Identification of priority needs.

- Discussion of available services and supports.

- Agreement on action steps, responsible parties, and deadlines.

- Follow-up schedule.

- Closing summary and next steps.

### 10.5 IAT Meeting Notes

| Item | Notes (Documented in Case Management System) |
| --- | --- |
| Date of meeting | [Insert] |
| Agencies present | [Insert] |
| Primary issues discussed | [Insert] |
| Family strengths identified | [Insert] |
| Priority needs identified | [Insert] |
| Services offered | [Insert] |
| Referrals made | [Insert] |
| Family commitments | [Insert] |
| Agency commitments | [Insert] |
| School commitments | [Insert] |
| HFI commitments | [Insert] |
| Follow-up date | [Insert] |

## 11. Community Service Provider Coordination

### 11.1 Provider Network

Identify the local service providers that may support HFI families.

| Service Category | Provider / Agency | Contact | Eligibility Requirements | Referral Process | Expected Response Time |
| --- | --- | --- | --- | --- | --- |
| Addiction Treatment | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Adult Mental Health Services | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Basic Needs/ Emergency Services | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Child Care | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Children Services | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Children’s Mental Health Services | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Drug / Alcohol Education | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Drug / Alcohol Treatment | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Education Support | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Faith Community Outreach | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Financial | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Health Services | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Housing | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Job Training / Support | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Law Enforcement | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Legal Services | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Mentoring | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Parent Education / Support | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Recovery / Support Groups | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| School System Services | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Transportation | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Other | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |

### 11.2 Referral Follow-Up

- Who confirms that the referral was sent?

- Response:
Case Officer

- Who confirms that the family connected with the service provider?

- Response:
Case Officer

- How soon after referral should HFI follow up with the family?

- Response:
Variable depending on referral

- How soon after referral should HFI follow up with the provider?

- Response:
Variable depending on referral

- How will unsuccessful referrals be handled?

- Response:
Documented in Case Management System; Utilized Yes / No; if no, what was the issue?

## 12. Monitoring and Follow-Up

### 12.1 Monitoring Period

Define how long HFI will monitor the family after assessment, referral, or IAT meeting.

| Case Type | Minimum Monitoring Period | Follow-Up Frequency | Responsible Party |
| --- | --- | --- | --- |
| Assessment only | [Variable] | [Variable] | [Variable] |
| Service referral | [Variable] | [Variable] | [Variable] |
| IAT meeting completed | [Variable] | [Variable] | [Variable] |
| High-priority family needs | [Variable] | [Variable] | [Variable] |
| Continued attendance / behavior issues | [Variable] | [Variable] | [Variable] |

### 12.2 Monitoring Activities

Suggested monitoring, HFI staff should review and document:

- Current attendance status

- New absences or tardies

- New behavior incidents or suspensions

- Parent / guardian engagement

- Student progress (attendance, behavior, grades)

- Service referrals made

- Services received

- Barriers preventing service connection

- New or emerging family needs

- Whether additional IAT coordination is needed

- Whether the case should remain open, be re-evaluated, or closed.

### 12.3 Monitoring Log

| Date | Contact / Review Type | Attendance Update | Behavior Update |  | Service Update | Family Update | Next Step | Staff Initials |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |  | [Insert] | [Insert] | [Insert] |

## 13. Re-evaluation, Closure, and Re-Entry

### 13.1 Re-evaluation Criteria

Define when a case should be re-evaluated.

Re-evaluation may be appropriate when:

- The family cannot be reached after required contact attempts; CLOSE CASE

- The family declines participation and attendance or behavior issues continue; CLOSE CASE

- The family participates but identified barriers remain unresolved; REASSESS

- The student’s attendance or behavior worsens; REASSESS

- Urgent safety concerns arise; REFERRAL

- Service agencies are unable to meet the family’s needs; REASSESS

- The case requires review by the District Attorney’s Office, school leadership, or another authorized party. REFERRAL

### 13.2 Closure Criteria

Define when a case may be closed.

A case may be considered for closure when:

- Attendance has improved and remained stable for the defined monitoring period;

- Behavior concerns have improved and remained stable for the defined monitoring period;

- The family has been connected to appropriate services;

- The family declines further participation and required follow-up steps have been completed;

- The student is no longer enrolled in a participating school;

- The case has been transferred to another agency or process;

- Other local closure criteria are met.

### 13.3 Closure Summary – Refer to Case Management System for Closure Assessment

| Item | Response |
| --- | --- |
| Date case opened | [Insert] |
| Date case closed | [Insert] |
| Reason for referral | [Insert] |
| Assessment completed? | Yes / No |
| IAT meeting completed? | Yes / No |
| Services referred | [Insert] |
| Services received | [Insert] |
| Attendance outcome | [Insert] |
| Behavior outcome | [Insert] |
| Family engagement outcome | [Insert] |
| Reason for closure | [Insert] |
| Re-entry criteria explained? | Yes / No |
| Staff completing closure | [Insert] |

### 13.4 Re-Entry

- May a closed case be re-referred to HFI?

- Response:
Yes

- What events trigger re-entry?

- Response:
New Triggering Event or Referral

- Is a new assessment required upon re-entry?

- Response:
Yes

- How will prior HFI history be reviewed?

- Response:
Case Officer use of HFI Case Management System

## 14. Staffing Plan

### 14.1 Staffing Model

Identify the staff needed to operate HFI locally.

| Position / Role | Number of Staff | Full-Time / Part-Time | Primary Duties | Backup Coverage |
| --- | --- | --- | --- | --- |
| Team Leader | [Insert] | [Insert] | [Insert] | [Insert] |
| Case Officer / | Variable | [Insert] | [Insert] | [Insert] |
| School Liaisons [Adjunct School Personnel] | [Insert] | [Insert] | [Insert] | [Insert] |
| Adjunct Data / Administrative Support | [Insert] | [Insert] | [Insert] | [Insert] |
| Adjunct Community Partner Coordinator [Team Leader] | [Insert] | [Insert] | [Insert] | [Insert] |
| Other | [Insert] | [Insert] | [Insert] | [Insert] |

### 14.2 Caseload Expectations

- What is the expected caseload per case officer?

- Response:
Variable

- How will caseloads be assigned?

- Response:
Geographic Assignment; school assignment, or other considerations

- What factors will be considered in caseload balancing?

- Response:
Full-time personnel; part-time personnel; cross-training

- How will staff vacancies or absences be covered?

- Response:
Cross Training of Personnel

## 15. Training Plan

### 15.1 Required Training

Identify required training for all HFI personnel.

| Training Topic | Required For | Training Provider | Completion Date | Refresher Frequency |
| --- | --- | --- | --- | --- |
| ### HFI program overview | ### [All Personnel] | ### [Insert] | ### [Insert] | ### [Insert] |
| Referral and intake process | [All Personnel] | [Insert] | [Insert] | [Insert] |
| Parent engagement | [All Personnel] | [Insert] | [Insert] | [Insert] |
| North Carolina Family Assessment tool | [All Personnel] | [Insert] | [Insert] | [Insert] |
| IAT meeting facilitation | [All Personnel] | [Insert] | [Insert] | [Insert] |
| Service planning | [All Personnel] | [Insert] | [Insert] | [Insert] |
| HFI Case Management System | [All Personnel] | [Insert] | [Insert] | [Insert] |
| Confidentiality and information sharing | [All Personnel] | [Insert] | [Insert] | [Insert] |
| Mandatory reporting / safety protocols | [All Personnel] | [Insert] | [Insert] | [Insert] |
| Cultural competency / family-centered practice | [All Personnel] | [Insert] | [Insert] | [Insert] |
| Community resource navigation | [All Personnel] | [Insert] | [Insert] | [Insert] |

### 15.2 Training Completion Log

| Staff Member | Role | Required Training Completed? | Date Completed | Documentation Location |
| --- | --- | --- | --- | --- |
| Team Leader | [Insert] | Yes / No | [Insert] | [Insert] |
| Case Officer | [Insert] | Yes / No | [Insert] | [Insert] |
| Other Personnel | [Insert] | Yes / No | [Insert] |  |

## 16. Data Protocols and Documentation

### 16.1 HFI Case Management System

Identify how the Case Management System is used to document HFI activity.

| Data / Record Type | System or Location | Responsible Party | Access Limited To |
| --- | --- | --- | --- |
| ALSDE Data Download | ALSDE to HFI Case Management System | State Support Team | HFI Personnel; State Support Team |
| Other Referral records | Case Management System | [Case Officer; Team Leader] | HFI Personnel |
| Parent Communication (letters, phone calls, email, text, in person meeting) | Case Management System | [Case Officer; Team Leader] | HFI Personnel; State Support Team |
| Contact attempts | Case Management System | [Case Officer; Team Leader] | HFI Personnel; State Support Team |
| NCFAS Assessment records completed | Case Management System | [Case Officer; Team Leader] | HFI Personnel; State Support Team |
| NCFAS Assessment records attempted | Case Management System | [Case Officer; Team Leader] | HFI Personnel; State Support Team |
| IIP plans created | Case Management System | [Case Officer; Team Leader] | HFI Personnel; State Support Team |
| IIP Plan presented | Case Management System | [Case Officer; Team Leader] | HFI Personnel; State Support Team |
| IAT Minutes of the IAT Meeting | Case Management System | [Case Officer; Team Leader] | HFI Personnel; State Support Team |
| IIP plans signed by family | Case Management System | [Case Officer; Team Leader] | HFI Personnel; State Support Team |
| Provider referrals | Case Management System | Case Officer; Team Leader] | HFI Personnel; State Support Team |
| Monitoring notes | Case Management System | [Case Officer; Team Leaderette] | HFI Personnel; State Support Team |
| Closure assessment | Case Management System | [Case Officer; Team Leader] | HFI Personnel; State Support Team |
| Reports / dashboards | Case Management System | [Team Leaders; State Support Team] | HFI Personnel; State Support Team |

### 16.2 Required Data Elements for HFI Case Management System

Define the data elements that must be captured for each HFI case.

| Data Element | Required? | Source | Entered By | Quality Check |
| --- | --- | --- | --- | --- |
| Student identifiers | Yes / No | [Insert] | [Insert] | [Insert] |
| School System | Yes / No | [Insert] | [Insert] | [Insert] |
| School |  |  |  |  |
| Grade | Yes / No | [Insert] | [Insert] | [Insert] |
| Referral date | Yes / No | [Insert] | [Insert] | [Insert] |
| Referral reason | Yes / No | [Insert] | [Insert] | [Insert] |
| Attendance count (unexcused absences; chronic absences) at referral | Yes / No | [Insert] | [Insert] | [Insert] |
| Behavior incidents at referral | Yes / No | [Insert] | [Insert] | [Insert] |
| Parent contact (letter, phone, text, etc.) date | Yes / No | [Insert] | [Insert] | [Insert] |
| Assessment date | Yes / No | [Insert] | [Insert] | [Insert] |
| NCFAS Assessment result summary | Yes / No | [Insert] | [Insert] | [Insert] |
| IAT date, if applicable | Yes / No | [Insert] | [Insert] | [Insert] |
| Provider Services referred | Yes / No | [Insert] | [Insert] | [Insert] |
| Provider Services utilized | Yes / No | [Insert] | [Insert] | [Insert] |
| Monitoring updates | Yes / No | [Insert] | [Insert] | [Insert] |
| Closure date | Yes / No | [Insert] | [Insert] | [Insert] |
| Closure reason | Yes / No | [Insert] | [Insert] | [Insert] |

### 16.3 Data Quality Controls

- Who reviews case records for completeness?

- Response:
Case Officer and Team Leader

- How often are case records reviewed?

- Response:
Ongoing

- What errors or missing items require correction?

- Response:
All data and process elements must be completed.

- How are corrections documented?

- Response:
Documented in HFI Case Management System

- Who prepares program reports?

- Response:
Team Leader; State Support Team

- Who reviews program reports before distribution?

- Response:
Team Leader; State Support Team

## 17. Program Metrics and Reporting

### 17.1 Output Measures

Identify what activity measures will be reported.

| Measure | Reporting Frequency | Responsible Party |
| --- | --- | --- |
| Number of referrals received | Ongoing | Team Leader; State Support Team |
| Number of families contacted | Ongoing | Team Leader; State Support Team |
| Number of assessments attempted | Ongoing | Team Leader; State Support Team |
| Number of assessments completed | Ongoing | Team Leader; State Support Team |
| Number of IIPs created | Ongoing; Quarterly | Team Leader; State Support Team |
| Number of IAT meetings held | Ongoing; Quarterly | Team Leader |
| Number of service referrals made | Ongoing | Team Leader |
| Number of families connected to services | Ongoing | Team Leader |
| Number of open cases monitored | Ongoing | Team Leader |
| Number of cases closed | Ongoing; Quarterly | Team Leader |

### 17.2 Outcome Measures

Identify what outcome measures will be tracked.

| Measure | Baseline | Follow-Up Point | Responsible Party |
| --- | --- | --- | --- |
| Attendance improvement | Comparison of annual data | [Insert] | HFI Personnel |
| Reduction in unexcused absences | Comparison of annual data | [Insert] | HFI Personnel |
| Reduction in behavior incidents | Comparison of annual data | [Insert] | HFI Personnel |
| Reduction in suspensions | Comparison of annual data | [Insert] | HFI Personnel |
| Number of Family engagements | Comparison of annual data | [Insert] | HFI Personnel |
| Number of Service connections | Comparison of annual data | [Insert] | HFI Personnel |
| Assessment improvement, if reassessed | Comparison of annual data | [Insert] | HFI Personnel |
| Assessment improvement, at closure | Comparison of annual data | Insert] | HFI Personnel |

### 17.3 Reporting Schedule

| Report | Audience | Frequency | Prepared By | Due Date |
| --- | --- | --- | --- | --- |
| Internal case activity report | [Insert] | Ongoing and quarterly | [Insert] | As needed |
| School system report | [Insert] | Ongoing and quarterly | [Insert] | As needed |
| Community partner report | [Insert] | Ongoing and quarterly | [Insert] | As needed |
| Grant / legislative / funding report | [Insert] | As needed/ required | [Insert] | As needed |
| Annual program summary | Legislature; school system; school; partners; public | As needed/ required | Team Leader; State Support Team | As needed/ required |

## 18. Community Engagement Strategy

### 18.1 Partner Identification

Describe how HFI will identify and maintain relationships with community partners.

- Who is responsible for building the local provider network?

- Response:
Team leader; Case Officer; District Attorney; School Personnel

- How will HFI identify service gaps?

- Response:
Team leader; Case Officer; District Attorney; School Personnel

- How will HFI onboard new community partners?

- Response:
State Support Team; Team Leader; District Attorney; School Personnel

- How will HFI maintain current contact information for providers?

- Response:
Team Leader; Case Officer; Maintained in HFI Case Management System

### 18.2 Community Partner Engagement Plan

| Partner Group | Engagement Method | Frequency | Responsible Party | Notes |
| --- | --- | --- | --- | --- |
| Schools | [Insert] | Ongoing | Team Leader | [Insert] |
| Social service agencies | [Insert] | Ongoing | Team Leader | [Insert] |
| Mental health providers | [Insert] | Ongoing | Team Leader | [Insert] |
| Faith-based organizations | [Insert] | Ongoing | Team Leader | [Insert] |
| Nonprofit organizations | [Insert] | Ongoing | Team Leader | [Insert] |
| Law enforcement / juvenile justice partners | [Insert] | Ongoing | Team Leader | [Insert] |
| Local government | [Insert] | Ongoing | Team Leader | [Insert] |
| Community foundations / funders | [Insert] | Ongoing | Team Leader | [Insert] |

### 18.3 Communication with Community Partners

- What information will HFI share with partners about the purpose and process of the program?

- Response:
Program Overview; Program Literature; Presentations customized to target audience (e.g., school personnel, healthcare, social services, etc.

- How will partners know how to accept referrals from HFI?

- Response:
Program Overview, Program Rollout, customized for referral partners

- How will HFI communicate expectations regarding confidentiality and consent?

- Response:
Program Overview, Program Rollout, customized for referral partners

- How will HFI receive feedback from partners about referral quality, capacity, and service gaps?

- Response:
Formal and informal feedback loops; meetings, calls, customized to agency protocols

## 19. Implementation Timeline

### 19.1 Planning and Launch Timeline

| Phase | Activity | Responsible Party | Start Date | Target Completion Date | Status |
| --- | --- | --- | --- | --- | --- |
| Planning | Confirm leadership structure | District Attorney; School System | [Insert] | [Insert] | [Insert] |
| Planning | Confirm participating schools | School System Personnel | [Insert] | [Insert] | [Insert] |
| Planning | Finalize referral criteria | Contingent on local school system policy | [Insert] | [Insert] | [Insert] |
| Planning | Finalize parent communication templates | District Attorney; School System | [Insert] | [Insert] | [Insert] |
| Planning | Confirm assessment tool and training | State Support Team | [Insert] | [Insert] | [Insert] |
| Planning | Build community provider list | HFI and all participating local personnel (DA; school personnel; agencies, etc. | [Insert] | [Insert] | [Insert] |
| Planning | Define data protocols | Alabama State Department of Education | [Insert] | [Insert] | [Insert] |
| Training | Train HFI staff | State Support Team; Team Leader | [Insert] | [Insert] | [Insert] |
| Training | Train school referral personnel | Team Leader; State Support Team] | [Insert] | [Insert] | [Insert] |
| Introduction to the Helping Families Initiative | Introduce HFI to participating school personnel, community service agencies, and families, social media, new outlets | District Attorney, Superintendent, Team Leader, Case Officers | Beginning of each school year | No more than 20 days into the new school year | Annual |
| Launch | Begin accepting referrals | HFI Personnel] | [Insert] | [Insert] | [Insert] |
| Launch | Conduct first family assessments | HFI Personnel | [Insert] | [Insert] | [Insert] |
| Launch | Conduct first IAT meetings | HFI Personnel | [Insert] | [Insert] | [Insert] |
| Monitoring | Review first 30 days of implementation | HFI Personnel; State Support Team | [Insert] | [Insert] | [Insert] |
| Monitoring | Review first 90 days of implementation | HFI Personnel; State Support Team | [Insert] | [Insert] | [Insert] |
| Ongoing | Quarterly program review | Personnel; State Support Team | [Insert] | [Insert] | [Insert] |

## 20. Risk Areas and Mitigation Plan

Identify operational risks that may affect local implementation.

| Risk Area | Mitigation Strategy | Responsible Party |
| --- | --- | --- |
| Inconsistent referrals | [Problem Identification; Training] | Team Leader |
| Delayed parent contact | [Problem Identification; Training] | Team Leader |
| Low family engagement | [Problem Identification; Training] | Team Leader |
| Incomplete assessments | [Problem Identification; Training] | Team Leader; State Support Team |
| Lack of provider capacity | [Problem Identification; Training] | HFI Personnel; State S/support Team |
| Incomplete data entry | [Training] | Team Leader; State Support Team |
| Confidentiality concerns | [Training] | Team Leader; State Support Team |
| Staff turnover | [Problem Identification; Training] | Team Leader; State Support Team |
| Insufficient training | [Problem Identification; Training] | Team Leader; State Support Team |
| Weak follow-up after referrals | [Problem Identification; Training] | Team Leader; State Support Team |

## 21. Quality Assurance and Fidelity Review

### 21.1 Fidelity Expectations

Define the required elements of the HFI process that must occur for each eligible case unless an exception is documented.

| Required Element | Required? | Exception Allowed? | Documentation Required |
| --- | --- | --- | --- |
| Referral reviewed | Yes | No | [Yes] |
| Parent communication sent | Yes | / No | [Yes] |
| Contact attempts documented | Yes / | / No | [Yes] |
| Family assessment completed | As Needed | Yes / | [Yes] |
| Needs prioritized | As Needed | Yes / | [Yes] |
| IIP created | As Needed | Yes / | [Yes] |
| IAT held when criteria met | As Needed | Yes / | [Yes] |
| Family signature and agreement | As Needed | Yes / | [Yes] |
| Provider Service referrals tracked | As Needed | Yes / | [Yes] |
| Monitoring completed | As Needed | Yes / | [Yes] |
| Closure reason documented | Yes | / No | [Yes] |

### 21.2 Case Review Process

- How many cases will be reviewed for quality assurance?

- Response:
As Needed; Random

- How often will reviews occur?

- Response:
As Needed and quarterly

- Who conducts the review?

- Response:
Team Leader; State Support Team; Case Officer

- How are findings documented?

- Response:
Case Management System

- How are corrective actions assigned and tracked?

- Response:
Team Leader; State Support Team

## 22. Required Attachments and Local Templates

The following documents should be attached to or maintained with this workplan.

| Attachment | Completed? | Location |
| --- | --- | --- |
| Local HFI process map | Yes / No | On file in the office of the Team Leader |
| Referral form | Yes / No | On file in the office of the Team Leader |
| Parent letter template | Yes / No | On file in the office of the Team Leader |
| Parent call script | Yes / No | On file in the office of the Team Leader |
| Consent / release of information form | Yes / No | On file in the office of the Team Leader |
| Family assessment procedure | Yes / No | On file in the office of the Team Leader |
| IAT meeting agenda | Yes / No | On file in the office of the Team Leader |
| IAT meeting notes template | Yes / No | On file in the office of the Team Leader |
| Service Provider plan template | Yes / No | On file in the office of the Team Leader |
| Service Provider referral form | Yes / No | On file in the office of the Team Leader |
| Monitoring log | Yes / No | Case Management System |
| Closure summary form | Yes / No | On file in the office of the Team Leader |
| Data elements | Yes / No | Case Management System |
| Reporting template | Yes / No | Case Management System |
| Staff training materials | Yes / No | [Case Management System User Guide, HFI Workplan] |
| Community provider directory | Yes / No | Case Management System |

## 23. Final Local Approval

By approving this workplan, the local District Attorney confirms that the local implementation process has been reviewed and that the HFI Team understands the required workflow, staffing responsibilities, training expectations, data protocols, and community engagement strategy.

| Approver | Title / Organization | Signature | Date |
| --- | --- | --- | --- |
| [District Attorney] | [DA] | [Insert] | [Insert] |
| [State Support Team] | [HFI] | [Insert] | [Insert] |
| [Team Leader] | [HFI Team Leader] | [Insert] | [Insert] |

## 24. Revision History

| Version | Date | Revised By | Summary of Changes |
| --- | --- | --- | --- |
| 1.0 | [June 2026 | State Support Team | Initial Version |
| [Insert] | [Insert] | [Insert] | [Insert] |

Triggering events include meeting the threshold for unexcused absences, serious violations of the school system’s code of student conduct, or referral from an appropriate source.

Contact attempts are not listed in chronological order. For example, the first attempt may be a phone call or a letter. In most cases, however, a letter from the District Attorney is preferred. Generally phone calls and text messages are follow up attempts.

Monitoring of a case is entered into the Case Journal notes.