## 90-Day Plan
90-Day Security Operations Performance Improvement Plan — Completed Example
Illustrative example only. Baseline means the measured starting condition before corrective actions begin.
Plan Information
Organization / Account | Metro Office Portfolio — Example
Plan Owner | Director of Operations
Start Date | 2026-07-23 | 2026-07-23
90-Day End Date | 2026-10-21 | 2026-10-21
Primary Objective | Stabilize staffing, strengthen frontline supervision, and improve service-quality execution.
Three Priority Outcomes
Priority | Problem / Opportunity |  | Baseline |  | 90-Day Target |  | Success Measure
1 | Staffing is reactive, with recurring open posts, uncovered hours, and overtime. |  | 8 open positions; 96.8% fill rate; 42 dark hours per week; overtime at 4.6%; about 18 last-minute schedule changes per week. |  | Reduce open positions to 2 or fewer; reach at least 99.5% fill rate; reduce dark hours below 5 per week; reduce overtime to 2.0% or less. |  | Targets sustained for 4 consecutive weeks and reviewed in the weekly scorecard.
2 | Employees report inconsistent communication, follow-through, recognition, and fairness from frontline supervisors. |  | Supervisor/service-climate score 2.7/5; only 48% agree concerns are addressed; monthly turnover 7.5%; supervisor huddles are inconsistent. |  | Raise survey score to at least 3.6/5; 75% agree concerns are addressed; monthly turnover below 4%; weekly huddles completed at all sites. |  | Repeat survey, turnover report, huddle logs, and corrective-action follow-up show sustained improvement.
3 | Tour completion and report quality are below expectations, creating client complaints and rework. |  | 82% tour completion; 76% reports submitted on time; 14 report corrections per week; 5 client complaints in the prior 60 days. |  | Tour completion at least 98%; on-time reporting at least 95%; no more than 3 corrections per week; no repeat complaint for 30 days. |  | System reports and client-review records verify the targets for 4 consecutive weeks.
Action Plan | [9 empty] | Observed Result / Outcome | Why It Changed / Evidence
Priority | Corrective Action | Owner | Start Date | Due Date | 30-Day Milestone | 60-Day Milestone | 90-Day Outcome | Status | Evidence / Notes
1 | Launch a weekly staffing review covering open posts, call-offs, dark hours, overtime causes, and assigned corrective actions. | Operations Manager | 2026-07-23 | 2026-07-30 | Weekly review launched; owners assigned to each exception. | Recurring vacancy and call-off patterns identified; relief roster active. | Weekly review is standard practice; exceptions are addressed before client impact. | Completed | 12 weekly reviews completed; action log retained. | Coverage exceptions fell steadily; open positions dropped from 8 to 2 and dark hours averaged 3 per week by day 90. | Weekly exception review exposed recurring vacancy and call-off causes early enough to assign owners and intervene before shifts went uncovered.
1 | Create a qualified relief roster and cross-train officers for the five highest-risk posts. | Recruiting Manager | 2026-07-23 | 2026-08-31 | 20 candidates screened; 8 relief officers hired or reassigned. | All five high-risk posts have at least two qualified relief options. | Open positions reduced from 8 to 2; dark hours average 3 per week. | Completed | Final fill rate 99.6%; overtime 1.9%. | Relief capacity increased and last-minute coverage became more reliable, reducing dependence on emergency overtime. | The staffing pool was broadened around specific high-risk posts rather than adding ad hoc part-time coverage across the portfolio.
1 | Require 14-day schedules and written escalation for any unfilled shift inside 72 hours. | Scheduling Manager | 2026-07-27 | 2026-08-14 | Scheduling standard issued and compliance tracking started. | Last-minute schedule changes reduced by at least 40%. | Last-minute schedule changes reduced from 18 to 6 per week. | Completed | Four-week average: 6 changes per week. | Schedule volatility declined and employees received more predictable work assignments. | A stable baseline schedule and earlier escalation made known gaps visible sooner instead of rebuilding schedules reactively each week.
2 | Conduct supervisor reset meetings covering expectations for communication, fairness, follow-through, recognition, and respectful feedback. | Director of Operations | 2026-07-27 | 2026-08-07 | All supervisors attend reset meeting and receive expectations guide. | Coaching observations completed for each supervisor. | Supervisor practices are reviewed monthly and included in performance discussions. | Completed | Attendance and coaching notes on file. | Supervisor communication became more consistent, although two supervisors still required additional coaching. | Clear expectations, observation, and follow-up created a common management standard instead of relying on individual supervisory style.
2 | Implement weekly five-minute shift huddles and a concern log with owner and due date. | Site Supervisors | 2026-08-01 | 2026-08-15 | Huddles operating at 80% of sites; concern log introduced. | Huddles operating at all sites; 85% of concerns closed by due date. | All sites use huddles; 91% of concerns closed by due date. | Completed | Huddle logs and concern tracker reviewed weekly. | Employees received more consistent communication and management follow-through became visible. | The concern log converted informal complaints into assigned actions with owners and due dates, making follow-up measurable.
2 | Repeat the employee pulse survey at day 75 and create individual coaching plans for supervisors below 3.5. | HR Business Partner | 2026-09-15 | 2026-10-15 | Survey date and communication plan established. | Survey launched; minimum anonymity threshold confirmed. | Survey score improved from 2.7 to 3.4; two supervisors placed on continued coaching plans. | Completed | Target of 3.6 was not fully achieved; improvement continues. | Employee experience improved, but the full target was not reached and two supervisors remain below the desired level. | Survey results identified that portfolio-wide practices improved faster than individual supervisor behavior, supporting targeted coaching rather than another broad intervention.
3 | Audit tour schedules and device configuration; correct missed checkpoints and unclear tour instructions. | Quality Manager | 2026-07-23 | 2026-08-10 | All tour templates audited; configuration errors corrected. | Tour completion reaches at least 95%. | Tour completion reaches 98.5% for four consecutive weeks. | Completed | System export retained. | Tour completion improved from 82% to 98.5% and remained above target for four consecutive weeks. | The audit separated officer-performance issues from configuration and instruction problems; correcting the system removed avoidable missed-tour exceptions.
3 | Introduce report-writing refresher training and supervisor review of exceptions within 24 hours. | Training Manager | 2026-07-30 | 2026-08-21 | Training completed for all officers with recent report errors. | On-time reporting reaches 90%; corrections reduced below 7 per week. | On-time reporting reaches 96%; corrections average 2 per week. | Completed | Quality audit shows no recurring error pattern. | On-time reporting and report quality improved while rework fell from 14 corrections per week to an average of 2. | Targeted retraining plus rapid supervisor review corrected recurring errors before they became normalized or reached the client.
3 | Add tours, report quality, complaints, and open actions to the monthly client review. | Client Service Manager | 2026-08-01 | 2026-08-31 | New review format approved by client. | Two structured reviews completed with documented actions. | No repeat complaint for 45 days; client confirms improvement. | Completed | Client email and meeting minutes retained. | Client reviews shifted from anecdotal updates to data-supported discussions; no repeat complaint occurred for 45 days. | Making service-quality trends and open actions visible created shared accountability and allowed the client to see what management changed and what happened next.
Plan Progress
Total Actions | 9 |  | What changed, why did it change, and what evidence links the action to the result? |  |  | Staffing became proactive, supervisors used a regular operating cadence, and service-quality exceptions were reviewed before becoming client complaints.
Completed | 9 |  | What changed because of the actions taken? |  |  | Supervisor consistency improved, but two supervisors remain below the desired employee-experience score and require continued coaching.
In Progress | 0 |  | Which root cause remains unresolved? |  |  | Compensation compression on two hard-to-fill overnight posts requires a contract and pricing discussion with the client.
Overdue Open Actions | 0 |  | What must be escalated beyond the current owner? |  |  | Four-week KPI trends, completed action logs, repeat survey results, client meeting records, and assigned recurring owners.
Completion Rate | 100% |  | What evidence shows the improvement is sustainable?

## Review Log
30-, 60-, and 90-Day Review Log
Record progress at each checkpoint. Focus on evidence, barriers, decisions, and the next action.
[8 empty] | Intervention / Change Made | Observed Outcome | Evidence / Confidence
Review Point | Review Date | Priority | Result to Date | Evidence / KPI | Barrier or Root Cause | Decision / Next Action | Owner
30-Day Review | 2026-08-22 | 1 | Weekly staffing review launched; relief recruitment underway. | Open positions 6; fill rate 98.1%; dark hours 21/week; OT 3.7%. | Overnight posts remain difficult to recruit because of wage compression. | Continue relief hiring; prepare pricing analysis for two overnight posts. | Operations Manager | Weekly exception review plus relief recruiting and cross-training. | Coverage improved but overnight vacancies continued to generate avoidable OT. | KPI trend and staffing roster show improvement; wage issue remains a documented constraint.
30-Day Review | 2026-08-22 | 2 | Supervisor reset completed and huddles operating at most locations. | 82% huddle compliance; 73% of logged concerns closed by due date. | Two supervisors are not consistently documenting follow-up. | Begin observation and coaching schedule; require weekly concern-log review. | Director of Operations | Supervisor reset, weekly huddles, and concern log introduced. | Communication cadence improved, but follow-through remained inconsistent for two supervisors. | Huddle logs and concern-closure data provide moderate evidence; individual behavior still varies.
30-Day Review | 2026-08-22 | 3 | Tour templates corrected and report training launched. | Tours 93%; on-time reports 87%; 8 corrections/week. | Several officers missed training because of leave and schedule conflicts. | Provide make-up sessions and supervisor review of exceptions. | Quality Manager | Tour-template audit, device corrections, report refresher training. | Tours and reporting improved, but missed training kept quality below target. | System exports and report audits show measurable improvement with a clear remaining gap.
60-Day Review | 2026-09-21 | 1 | Coverage has stabilized and overtime continues to decline. | Open positions 3; fill rate 99.2%; dark hours 7/week; OT 2.4%. | One overnight vacancy remains persistently open. | Use temporary pay differential pending client pricing decision. | Operations Manager | Relief roster active; 14-day schedule and escalation standard in place. | Coverage is substantially more stable and overtime is approaching target. | Eight-week staffing trend supports improvement; remaining overnight vacancy is isolated and documented.
60-Day Review | 2026-09-21 | 2 | Huddles are standard practice; concern follow-through has improved. | 100% huddle participation; 86% of concerns closed on time; monthly turnover 5.1%. | Relationship quality varies by supervisor; recognition remains inconsistent. | Use survey results for individual coaching and recognition expectations. | HR Business Partner | Portfolio huddle cadence maintained; supervisors receive observation and coaching. | Concern closure improved, but employee experience remains uneven by supervisor. | Huddle compliance and concern logs are strong evidence; pulse survey will test employee perception.
60-Day Review | 2026-09-21 | 3 | Quality metrics are near target and client complaints have stopped. | Tours 97.3%; reports 94%; 4 corrections/week; no repeat complaint for 25 days. | One device has intermittent connectivity. | Replace device and continue weekly quality audit. | Quality Manager | Quality audit cadence, report review, and device correction. | Service execution is near target and complaints have stopped recurring. | System data and client complaint record provide strong evidence; one technology issue remains.
90-Day Review | 2026-10-21 | 1 | Staffing and labor-control targets achieved. | Open positions 2; fill rate 99.6%; dark hours 3/week; OT 1.9%. | Overnight wage issue is contained but not structurally resolved. | Make weekly staffing review permanent; complete client pricing discussion. | Director of Operations | Weekly staffing review, relief roster, stable scheduling standard, and escalation process. | Staffing/labor targets were achieved and sustained for four weeks. | Four-week scorecard trend confirms performance; unresolved wage compression is explicitly separated from operational execution.
90-Day Review | 2026-10-21 | 2 | Employee experience improved, but the full survey target was not reached. | Survey 3.4/5; 72% agree concerns are addressed; turnover 4.5%. | Two supervisors remain below 3.5 and require continued development. | Carry supervisor coaching into the next 90-day cycle. | HR Business Partner | Supervisor reset, huddles, concern tracking, observation, and targeted coaching. | Portfolio employee experience improved, but two supervisors remain below target. | Repeat survey plus turnover and concern-closure data provide moderate-to-strong evidence; improvement is incomplete.
90-Day Review | 2026-10-21 | 3 | Service-quality targets achieved and sustained. | Tours 98.5%; reports 96%; 2 corrections/week; no repeat complaint for 45 days. | No material barrier remains. | Standardize monthly client-quality review and quarterly refresher training. | Client Service Manager | Tour corrections, report coaching, weekly audits, and data-supported client reviews. | Service-quality targets were achieved and sustained, with no repeat complaint for 45 days. | System exports, report audits, and client meeting records provide strong converging evidence.
Final 90-Day Review
Which targets were achieved? |  |  | Priority 1 staffing/labor targets and Priority 3 service-quality targets were achieved.
Which actions did not produce the intended result? |  |  | Supervisor coaching improved results, but the survey target of 3.6/5 and turnover target below 4% were not fully achieved.
Which improvements should become standard operating practice? |  |  | Weekly staffing review, stable baseline scheduling, site huddles, concern tracking, weekly quality audits, and data-supported client reviews.
Which issue should become the next 90-day priority? |  |  | Developing the two lowest-rated supervisors and resolving compensation compression on hard-to-fill overnight posts.