## Dashboard
DASHBOARD
Metric | Value
Total Cost | 261365.744
Contingency | 34091.184
Project Status | ⚠ High Cost | Avg Budget for Major Renovation or Addition =$200k
Subtotal | 227274.56 | Excludes permit expediting -Vary according to project and number of agencies routed

## Budget
EXAMPLE COST FOR MAJOR HOME RENOVATION OR ADDITION
Category | Item | Unit Cost (Hrs or /SF) | Qty | Subtotal
Design | Architect/Eng Design / hr | 250 | 40 | 10000 | Prevailing rate per hour ($250 -$350/hr) by independent local architects/eng. Permits Hawaii rates are generally much lower
Permits | Honolulu C&C Permit Fees | 0.020733 | x Cost of Constr | 4395.4667 | C&C Fee Calculator | https://www.honolulu.gov/dpp/permitting/building-permits-home/bp-fee-calc/
Permits | Honolulu C&C Plan Review Fee | 0.0041467 | x Cost of Constr | 879.0933
Permits | Permit Expeditor (Flat Fee) |  | Contingent on agencies |  | Call for Quote. Contingent on complexity of project, number of agencies routed to and If drafting/ stamped drawings are included
Structural | Struct Construction ($600/sqft) | 600 | 30 | 18000 | Omit if none apply; Added ceiling structural roof/ceiling beams, headers, columns, (concrete) reinforced window or door openings;Estimtated specialty sf area;
Building | General Construction ($400/sf) | 400 | 200 | 80000 | Average/Medium-end building materials/contractor fees (Note: Costs can range from $400-800 per/sf depending on medium to high-end building materials or specialties
Plumbing Sub | Major Relocation | 12000 | 1 | 12000 | Reduce to 2/3 of this cost ($8,000) if only replacing fixtures or minor relocation of plumbing
Electrical Sub | Major Upgrade | 11000 | 1 | 11000 | Major rewiring (example -1970's home wiring fully upgraded to current elec code); add another $4k if upgrading panels and meter/exterior excavation
Cabinets | Mid-range | 18000 | 1 | 18000 | Avg kitchen size is 225 sf; See these guides for reference |  | https://bit.ly/4tHere1 | https://bit.ly/3QJUg0q
Countertops | Quartz/sf (high end;mater & labor | 90 | 100 | 9000 | Quartz Counteropts roughly $300 sf
Roofing | Add'l Roof For Room Additions | 8 | 1000 | 8000 | Apprx $8/ sf for shingle roof; apprx $20/sf for metal roof- materials only cost
Appliances | Mid Range Full set (Kitchen) | 12000 | 1 | 12000
Flooring Sub | Materials & Install (approx 300 sf) | 30 | 300 | 9000
GC Labor & OH | General Contractor | 35000 | 1 | 35000 | Based on 15% to 25% (of construction) for overhead/insurance & profit |  | We recommend only using licensed contractors |  | Hawaii Dept of Commerce - Hire a Licensed Contractor Website
https://cca.hawaii.gov/pvl/hire-a-licensed-contractor/
|  |  | Construction Cost Only (for C&C Permit Fee Calculation) | 212000 | Excludes permit expediting fee
|  |  | Subtotal | 227274.56
|  |  | Contingency % | 15% | for emergency unforeseen conditions and change orders; held on reserve
|  |  | Contingency | 34091.184 | for emergency unforeseen conditions and change orders; held on reserve
|  |  | TOTAL | 261365.744

## Timeline
Task | Start Date | Duration (days) | End Date
Planning/Design | 2026-05-01 | 30 | 2026-05-31 | Approx Durations SHOWN HERE AS AN EXAMPLE
Permitting |  | 60 | 60
Construction |  | 120 | 120
Finishes |  | 45 | 45
Final Inspection |  | 10 | 10
Formulas:
End Date = [Start Date]+[Duration (days)]

## Permits
PERMIT TRACKER
Permit | Required | Status
Building | Yes -Exterior Ground Work | Not Started
Electrical | Yes | Not Started
Plumbing | Yes | Not Started
Zoning | Yes | In Progress
Stormwater | Yes -Exterior Ground Work | In Progress
BWS | Yes | Not Started
Wastewater | Yes | Not Started
Stuctural | Yes | Not Started

## Contractors
CONTRACTOR BID TABULATION & QUALIFICATION CALCULATOR
(EXAMPLE)
Criteria | Weight | Contractor A | Contractor B | Contractor C | HOW TO SCORE
License | 20% | 20% | 20% | 0% | yes = 20% / no = 0
Experience | 20% | 20% | 15% | 10% | 5 yrs or more = 20%; 4 or more = 10%; less than 4yrs - 5%
References | 15% | 15% | 10% | 5% | real customer referal = 15%; paid ads =10%; Craigslst = 0
Timeline | 15% | 15% | 15% | 5% | 6 months or less = 15%; 6 months or more = 10% (allow for project size)
Communication | 15% | 15% | 15% | 5% | yes = 15% (Bad communication is a RED FLAG)
Inured | 15% | 15% | 15% | 0% | yes = 15% (No insurance = 0% MAJOR RED FLAG
Total score: | 100% | 100% | 90% | 25% | Any Score Below 70 is HIGH RISK
Price |  | 20000 | 35000 | 18000
CONTRACTOR BID TABULATION & QUALIFICATION CALCULATOR
Hawaii Dept of Commerce - Hire a Licensed Contractor Website
Criteria | Weight | Contractor A | Contractor B | Contractor C | https://cca.hawaii.gov/pvl/hire-a-licensed-contractor/
License | 20%
Experience | 20%
References | 15%
Timeline | 15%
Communication | 15%
Inured | 15%
Total score: | 100% | 0% | 0% | 0%
Price