# Community Impact & Value Report: Summer 2025

## Greater Northeast Keizer Neighborhood Association (GNEKNA)

Contact: gnekna.com | 503-991-1671 | nekna2022@gmail.com

Leadership: Tammy Kunz, GNEKNA President

May 26,2026

## Executive Summary

Between May and August 2025, the Greater Northeast Keizer Neighborhood Association (GNEKNA) executed a high-impact literacy and community resource initiative across Keizer. Driven by a small, dedicated core team of volunteers, the project drastically outperformed its initial goal of reaching 550 families, ultimately impacting 2,695 families.

By blending interactive bilingual "Story Walks" with targeted resource distribution and the installation of Little Free Libraries, GNEKNA successfully fostered multi-generational connection, supported early childhood literacy, and bridged critical resource gaps for local families.

## High-Impact Metrics & Community ROI

GNEKNA turned a grassroots effort into a massive public service victory, demonstrating an extraordinary return on investment (ROI) for the City of Keizer and its residents.

| Metric | Project Achievement | Total Community Footprint |
| --- | --- | --- |
| Families Impacted | 2,695 families touched by literacy and resources | Far exceeded original project target of 550 families |
| Bilingual Story Walks | 19 interactive walks successfully hosted | Spread across local parks, church grounds, and school pathways |
| Resource Kits Distributed | 650 comprehensive bags + 1,500 standalone flyers | Delivered crucial safety, health, and crisis intervention resources |
| Infrastructure Added | 9 custom Little Free Libraries built and deployed | 8 placed in GNEKNA; 1 gifted to West Keizer NA |
| Leveraged Volunteer Capital | $21,318.75 in contributed labor value | Transformed minimal funding into extensive service hours |

## Volunteer Capital & Economic Leverage

The massive scale of this project was made possible through an incredible mobilization of local volunteer hours. By utilizing grassroots labor, GNEKNA provided a massive financial leverage to the city of Keizer, converting community dedication into formal economic value.

Financial Leverage Metric: According to Independent Sector data, the financial value of a volunteer hour in Oregon is calculated at $34.11.

- Executive Leadership Mobilization: President Tammy Kunz and Vice President Jacqueline Green spearheaded the operational push, personally donating approximately 25 hours per week over the 4-month summer initiative (May to August).

  - Total Contributed: ~400 hours

  - Estimated Economic Value: $13,644.00

- Hands-on Infrastructure Building: Core board members alongside local youth (including Gabe, age 7, and Lexiann, age 12) spent 5 hours’ hand-crafting each of the 9 new Little Free Libraries.

  - Total Contributed: 45+ hours of dedicated construction labor

  - Estimated Economic Value: $1,534.95 (plus raw materials saved through donation)

- Grassroots Event Support & Execution: The core team of 6 leaders was supported by an additional 6 community members who freely gave their time to assemble 650 resource kits, transport heavy mobile storyboards, manage paths, and guide families through events.

  - Total Contributed: Estimated ~180 combined event hours

  - Estimated Economic Value: $6,139.80

### Total Volunteer Value Contribution: $21,318.75

## Core Initiatives & Community Value

### 1. Bilingual Story Walks & Community Events

GNEKNA utilized mobile storyboards featuring engaging children's books (e.g., Everything Goes with Plátanos and 10 Ways to Hear Snow) to promote physical activity and family bonding.

- Inclusive Engagement: Staff provided bilingual readings (English/Spanish), ensuring equitable access for Spanish-speaking families and adult learners.

- Fun Friday (July 25, 2025): Hosted at St. Edward Church on River Road, drawing 650 participants, 150+ families, and 47 community partners.

- National Night Out (Aug 5, 2025): Partnered with the ELKS Lodge on Cherry, Southeast Keizer NA, and local schools to engage 557 families.

- School Readiness Pathways: Used a Story Walk along the MLK JR Parkway path to acclimate 35 incoming Kennedy Elementary families with their future walk-to-school route, building comfort and community safety.

- Keizer Community Library Host Partnership: Successfully partnered with the Keizer Community Library to host dedicated Story Walks, drawing 26 local families. At each library event, GNEKNA distributed comprehensive resource bags and gave away a backpack filled with school supplies to support academic readiness.

- Overcoming Language Barriers: To ensure equitable access, library and project staff provided fully bilingual readings (English/Spanish), helping Spanish-speaking families and adult learners navigate the text and comfortably connect with library resources.

### 2. Wrap-Around Resource Distribution

Rather than offering literacy alone, GNEKNA leveraged these events to distribute vital safety and health resources. Each resource bag included:

- Safety & Health: Distracted Driving information (Keizer Police Dept.), Safe Routes to School flyers, Center for Hope and Safety materials, and Liberty House flyers.

- Mental Health Support: Marion County 988 crisis line information and Early Learning Hub resources.

- Literacy & Development: Keizer Community Library and Dolly Parton Imagination Library bookmarks (for free monthly books), activity books, and school supplies.

- Youth Engagement: Custom GNEKNA slap bracelets, fidgets, pop-its, chalk, and stickers.

### 3. Sustainable Literacy Infrastructure

To ensure long-term value, volunteers dedicated 5 hours per unit to hand-build 9 Little Free Libraries. This sub-project fostered community fellowship, engaging local teens who gained hands-on building experience and a sense of civic pride.

## Feedback & Community Voices

Data collected from 67 formal participant surveys revealed overwhelmingly positive community sentiment and a clear demand for expansion:

- 100% of surveyed participants stated they would attend future Story Walks.

- 70% expressed a desire to see more walks, with 20 noting they would love to see additional languages integrated.

- Actionable Insights: Participants requested increased physical spacing between storyboards (12 responses) and the addition of matching crafts or activities tied to the book topics (22 responses).

Human Impact Highlights:

- One father of children with learning challenges used the initiative to take his kids on 19 different community walks, connecting deeply with library resources and winning a curated 7-book reading basket.

- A local mother who could not read was inspired by the interactive walks to enroll in a literacy program in Salem, fundamentally changing her family's trajectory.

## Future Outlook & Long-Term Leverage

GNEKNA is actively leveraging the momentum of this summer's success into long-term civic infrastructure:

- Parks Master Plan Integration: GNEKNA’s 2-year strategic goal is to formalize permanent, weather-resistant Story Walk platforms across Keizer's parks system (such as Claggett Creek Park and Keizer Rapids Park). GNEKNA will commit to refreshing these stories bi-monthly.

- School & Library Partnerships: Following outreach from 9 local educators, GNEKNA is looking to expand these walks into the academic school year and deepen ongoing event collaborations with the Keizer Community Library.

Special Thanks to Our Core Team & Partners:

Nancy Grace, James Jones, Lisa Little, Beverly Davis, Jacqueline Green, local youth builders (Lexiann & Gabe), the Keizer Community Library, Keizer Police Department, Early Learning Hub, Claggett Creek Watershed Council, Kennedy Neighborhood Family Council, Liberty House, Keizer Community Library, Cheeriots, Salem Leadership Foundation and the numerous community organizations that provided vital resources.

Submitted by the GNEKNA President Tammy Kunz and Board of Directors.