## MASTER_TRACKER
Task ID | Workstream | Phase | Task Name | Owner | Start | End | Duration | Dependency | Priority | Status | Progress | Baseline Start | Baseline End | Variance | Impact | Probability | Risk Score | Cost | Notes
T-001 | AI | Planning | System Architecture | PMO | 2026-05-01 | 2026-05-15 | 14 | - | High | In Progress | 20 | 2026-05-01 | 2026-05-15 | 0 | 5 | 4 | 20 | 50000 | Core design

## EXECUTIVE_DASHBOARD
KPI | Value
Total Tasks
Avg Progress
High Risk Tasks
Total Cost

## RISK_REGISTER
Task ID | Impact | Probability | Risk Score
T-001 | 5 | 4

## FINANCIAL_TRACKER
Task ID | Planned Cost | Actual Cost | Variance
T-001 | 50000 | 52000

## RESOURCE_PLANNER
Resource | Role | Capacity % | Assigned Tasks | Utilization
Engineer A | AI Engineer | 100 | 3

## GANTT_TIMELINE
Task | Start | End | Duration
System Architecture | 2026-05-01 | 2026-05-15 | 14