## Sheet1
No. 1 | No. 2 | No. 3
Morton Road | Buttermilk Hill Road | CHIPS Projects 2019
COMPLETED | DEFFERED | COMPLETED
Assess Flooding at Tube | Review E-mail from Scott Harris | Review CHIPS notes. CY 2019 = $104,424
1 DEC Permits-need to be obtained by property owner-H Ellis | Assess washout of road. Currently, stable | Mitchell called to Obtain Quotes from Vendors.
2 Remove Beavers | Jordon Clements - to assess for NRCS Project; may qualify | 1. Gorman Bros
3 Remove Beaver Dam | Grading: Done | 2. Suit Kote
Dam debris broke; water lower; no issue currently. |  | 3. Hansens 4. Cobleskill Stone Inc
Note: Town has Nuisance Permit |  | Set CHIPS Mtg when quotes are recv'd.
| Determine Plan of Action | CHIPS Projects 2019: Awarded to Cobleskill Stone
No. 4 | No. 5 | No. 6
CHIPS ---------Gage Road | Town Road (Kirshman, Thompson, LeFluer, Hoose-uper, Morton, Pirs Hill, Berry Lane | Hoose Road - Lower
IN PROGRESS | IN PROGRESS | COMPLETED
Ditching - done | Assess each road | Done: Assess ditches near Yearry Property
Brush Removal - done | Kirshman Hill - wsh out in center of road | Dig out ditches; divert runoff to creek
Weeping - done | Work: Honing | Issues: correct runoff to private property
Stone | Work: Pot Holes
Tubes: 12+ DONE | Work: Sweeping
CHIPS -2019: Aug 5 -9th | Do not wait for dry-out. Complete when little moist. Use item 4 and drag from shoulders. | No Cross Tube to be installed; per Hwy Supt. Spoke with resident.
DONE: Adair,Kirshman,Buttermilk Road(s)
Good Job Hwy DPW!!! | Some done: Thompson Hill Road
No. 7 | No. 8 | No. 9
Breen Driveway | Edwards Road | Salt Shed
IN PROGRESS | IN PROGRESS | IN PROGRESS
Assessed project | REMA Project: Tube Replament | Finalize Plans/Design: DG Completed
Taper/Tier side of driveway:done | Completion Date: Aug 30th!!! | Code Off to sign off on Plans: Cc to LS
| Set up date with S Gridley: Aug 5-9th | Prep Daily Work Logs-done
Landscaping: Patti & Charlie | Review SG Quote | Obtain quote: S Gridley for Excavation
| Purchase materials & Supplies | Obtain Quote: S Gridley for Concrete walls'
MV to call J Clement to request | Prep Daily Work Logs
Hydro Seeding. | PG to contact Tom Cowin re extension
Hydro Seeding Status: _______ | Will need 300 Ton Stackable Stone. Mitchell to obtain price. Will use stockpile dirt/stone from excavating salt shed area. | Date for Porject Work: August - September. Mitchell to call Steve G to lock down date and obtain adjusted quote for excavationn and concrete work for the 2 stall shed.
Engineer Prill to redesign salt shed - done
Supervisor to contact vendor for pricing on trees/shrubs. | Supervisor e-mailed T Cowin. FEMA is expected to approve before end of July 2019. | NYS DEC GRANT: Application prepped & to be submitted 7/26/19; completed
| Resident given notice 08/01: done | Thank you Board Members!!
No. 10 | No. 11 | No. 12
Front Building-Apron | Sand/Stone Quotes | Salt Quotes
DEFFERED | COMPLETED | COMPLETED
Obtain Quote for Apron Area | Obtain Quotes from Vendors: 500 yards | Obtain Quotes from Vendors: _________
1. S Gridley for Apron -front bldg | 1. Kiser- new vendor will give 2 loads free as sample. $7.50/yard; $60/$75/delivery | 1. Cargill --- NYS Contract
| 2. Cobleskill Stone: $8.75/ton $11/yd | 2. V Logan
Patti- find extra funds for Proj. | 3. Kuckenberger (aka M Stockings): $7.25/yd | 3. Appalachian
| 4. Seward Sand & Gravel: $8/yd | 4. Other
Mitchel Asked S Gridley for quote | 5. Onadaga County - NYS Contract | Mitchell submitted his request(due 5/3)
| 6. R Brimmer (County) uses variety of vendors | to NYS OGS for 550 tons w/ Cargill
Quote Rec'd = $11,000 for a | Have purchased 660 yds; need approx 750 yds more; this is within the budget amount | Rate:$_________
12' x 90'
No. 13 | No. 14 | No. 15
Sale of Excavator | Equipment (Dump Truck w/Plow) | Highway Budget for CY 2020
COMPLETED | IN PROGRESS | DEFFERED
Charlie: called Vendor (Roger from Kiser) who is interested in buying our excavator @ $30K | Mitchell: to continue to explore purchase of used dump truck w/plow | Prep Budget (salary, projects, etc)
Purchased: $28k | Truck #227 -MV put on Auction Intl
Repairs & Parts: $14K | Truck #229 -MV put on Auction Intl
Net: $42 - $30K = $12K loss | Done: Truck #65 -Scrapped; rec'd $1024.66
Sell Excavator, used proceeds for a used backhoe. | 10 Wheeler @ Aucttion Intl: Curtis/Dan reviewing options. No successful result
MV:Will check Aution Int'l for equp | Trailer - poor condition; Charlie to contact interested person. No one interested.
MV:Will check Aution Int'l for equp | Trailer - MV put on Auction Intl.
BID: Bid posted; rec'd 1; declined bid. Will keep excavator for Hwy use.
No. 16 | No. 17 | No. 18
Ditching & Brushing of Roads | Rake edge of fields of property owners | NYS & Couny Association Dues
In Progress | COMPLETED | COMPLETED
All Town Roads: | Rake edge of fields of property owners | NYS Dues = $200
Kirshman Hill: ditching done | Due to Snow Removal--large clumps in filed | County Dues = $200
Thompson Hill |  | Mitchell decided & to call to inform each
Upper Hoose | Joe Fedore--Hren Road | that the Town of Roseboom is opting out
Lower Hoose | Property --Town Line Road | of being a members.
Morton Road | Co Rte 39 - upper right side
Piers Hill |  | Savings: $400
Stannard Hill | Mitchell to discuss with Mr Fedore
Gage - School House | Cody to rake area. | Mitchel tocall Assoc on Monday to cancell
Gage road: in progress
LeFluer Road
work deferred due to the large
amount of work needed on Gage
Road.
No. 19 | No. 20 | No. 21
County Civil Service Forms | Electric Service Needs | Payroll Performance Bonus'
COMPLETED |  | COMPLETED
Patti: Cc to Mitchell his Civil | Electric Panel - for portable generator | Deputy Hwy Superintendent
Service form 426--reinstate as | GFI - Keep tripping;not breaker.
Hwy Supt. | Light/Fan - in Womens Bathroom | Payroll Performance Bonus': effective 6/1
Met with Hwy Dept emloyee 5/7/19
Mitchell contacted Crew Cap Electric.
| CCE will assess & give quote for repairs. | Mitchell: complete & submit Civil Service
| MV to called Crew again & R Brazie. | 426 forms with new payroll rates for
| Cap Crew did assessment & will present quote for needed electric work. | each employee, and Deputy Hwy Supt
Cap Crew appproved to complte needed
electric work at the Town Building.
No. 22 | No. 23 | No. 24
Daily Work Log Sheets | HMP-Hazard Mitigation Plan | AED Accessories
IN PROGRESS | IN PROGRESS | COMPLETED
Complete Daily Work Logs | Need to complete HMP; designate & prioritize tube/culvert replacements and associated costs. Complete HMP Forms. Submit & review with Steve Bornt, NYSDHSES. | Mitchel & Dan to coordinate and contact AED to order expired (10/2018) supplies (i.e. Adult & Spare Electrodes).
for any/all road work or projects. |  | 1-800-533-0523 Bound Tree Medical
Board insisted & reminded Hwy Supt to complete these Work Logs daily; for any and all work on @ road!! |  | Patti - set up acct and order supplies. Completed Credit Application & submitted on 6/11.
Adult Electrodes: 2742-60001 $51
Battery: 2750-40001 $395
No. 25 | No. 26
Mice/Rat Infestation | Road Committee Meetings
COMPLETED
Hwy Supt asked to purchase and | May 7th - 6:30 am
set poison at Town Building. | June 07th - 7:30 am
Update: Done | July 02, 2019 am
July 11, 2019 pm
| 2019-08-02 07:30 | Update: 08/01/19