## Sheet1
No. 1 | No. 2 | No. 3
Morton Road | Buttermilk Hill Road | CHIPS Projects 2019
Assess Flooding at Tube | Review E-mail from Scott Harris | Review CHIPS notes. CY 2019 = $104,424
1 DEC Permits-need to be obtained by property owner | Assess washout of road | Mitchell called to Obtain Quotes from Vendors.
2 Remove Beavers | Curtis to call Jordon Clements - to assess for NRCS Project | 1. Gorman Bros
3 Remove Beaver Dam | Determine Plan of Action | 2. Suit Kote
| MV to contact Mr Harris, may use "medium stone for backfill". | 3. Hansens
Set CHIPS Mtg when quotes are recv'd.
No. 4 | No. 5 | No. 6
Gage Road | Town Road (Kirshman, Thompson, LeFluer, Hoose-uper, Morton, Pirs Hill, Berry Lane | Hoose Road - Lower
Ditching, Brush Removal | Assess each road | Assess ditches near Yearry Property
Weeping | Kirshman Hill - wsh out in center of road | Dig out ditches; divert runoff to creek
Stone | Work: Honing | Issues: correct runoff to private property
Tubes: 12+ | Work: Pot Holes
CHIPS -2019: end of July | Work: Sweeping
MV-call to get quote on Paver/Shim from Vendors. | Do not wait for dry-out. Complete when little moist. Use item 4 and drag from shoulders. | Cross Tube: Purchase & Install Cross-Tube across from S Walls property to divert water runoff; from her property across the road and down to creek.
Award Quote & set Date
No. 7 | No. 8 | No. 9
Breen Driveway | Edwards Road | Salt Shed
Assessed project | REMA Project: Tube Replament | Finalize Plans/Design
Taper/Tier side of driveway | Completion Date: Aug 30th!!! | Code Off to sign off on Plans
Use of Blocks: 2 Tier Level | Set up schedule with S Gridley | Prep Daily Work Logs
Landscaping: Patti & Charlie | Review SG Quote | Obtain quote: S Gridley for Excavation
| Purchase materials & Supplies | Obtain Quote: S Gridley for Concrete walls'
Tonka Blocks: Purchase Blocks. | Prep Daily Work Logs
Stack Blocks &Backfill
| Will need 300 Ton Stackable Stone. Mitchell to obtain price. Will use stockpile dirt/stone from excavating salt shed area. | Date for Porject Work: August - September. Mitchell to call Steve G to lock down date and obtain adjusted quote for excavationn and concrete work for the 24x32 2-stall shed.
No. 10 | No. 11 | No. 12
Front Building-Apron | Sand/Stone Quotes | Salt Quotes
Obtain Quote for Apron Area | Obtain Quotes from Vendors: 500 yards | Obtain Quotes from Vendors: _________
1. S Gridley for Apron -front bldg | 1. Kiser- new vendor will give 2 loads free as sample. $7.50/yard; $60/$75/delivery | 1. Cargill
| 2. Cobleskill Stone | 2. V Logan
Patti- find extra funds for Proj. | 3. Kuckenberger (aka M Stockings) | 3. Appalachian
| 4. Seward Sand & Gravel | 4. Other
| 5. Onadaga County - NYS Contract | Mitchell submitted his request(due 5/3)
| 6. check w/ R Brimmer who County chose | to NYS OGS for 550 tons w/ Cargill
| Est need: 500 yards | Rate:$_________
No. 13 | No. 14 | No. 15
Sale of Excavator | Equipment (Dump Truck w/Plow) | Highway Budget for CY 2020
Charlie: Vendor (Roger from Kiser) is interested in buying our excavator @ $30K | Mitchell: to continue to explore purchase of used dump truck w/plow | Prep Budget (salary, projects, etc)
Purchased: $28k | Truck #227 - use for parts & scrap
Repairs & Parts: $14K
Net: $42 - $30K = $12K loss
Sell Excavator, used proceeds for a used mini-excavator or used backhoe.
Est Price: Backhoe $____
Est Price: Mini-Excavator $30K+
No. 16 | No. 17 | No. 18
Ditching & Brushing of Roads | Rake edge of fields of property owners | NYS & Couny Association Dues
All Town Roads: | Rake edge of fields of property owners | NYS Dues = $200
Kirshman Hill | Due to Snow Removal--large clumps in filed | County Dues = $200
Thompson Hill |  | Mitchell decided & to call to inform each
Upper Hoose | Joe Fedore--Hren Road | that the Town of Roseboom is opting out
Lower Hoose | Property --Town Line Road | of being a members.
Morton Road | Co Rte 39 - upper right side
Piers Hill |  | Savings: $400
Stannard Hill | Mitchell to meet with Mr Fedore to discuss.
Gage - School House | Mitchell to rake area.
Gage road
LeFluer Road
No. 19 | No. 20 | No. 21
County Civil Service Forms | Electric Service Needs | Payroll Performance Bonus'
Patti: Cc to Mitchell his Civil | Electric Panel - for portable generator | Deputy Hwy Superintendent
Service form 426--reinstate as | GFI - Keep tripping;not breaker.
Hwy Supt. | Light/Fan - in Womens Bathroom | Payroll Performance Bonus': effective 6/1
Met with Hwy Dept emloyee 5/7/19
Mitchell contacted Crew Cap Electric.
| CCE will assess & give quote for repairs. | Mitchell: complete & submit Civil Service
426 forms with new payroll rates for
each employee.
No. 22
Daily Work Log Sheets
Complete Daily Work Logs
for any/all road work or projects.
No. 22
Road Committee Meetings
May 7th - 6:30 am