## Sheet1
COMPLETED
| Mitchell & Charlie | Morton Road | Beaver Damage; Road Flooding | Dam Debris Broke; water level lower; no current issue | Completed
| Mitchell & Road Comm | CHIPS Projects | Obtain Quotes for 2019 CHIPS | Quotes rec'd; Approved Cob Stone Products | Completed
| Mitchell & Curtis | Hoose Road | Assess for Cross Tube and ditching | No Cross Tube installed; spoke with Resident | Completed
| Patti & Bldg Comm | Salt Shed | Assess Need | Finalize Assesment & Engineer Design Plan | Completed
| Patti |  | NYS DEC Grant | Resolution #2a - 50% match | Completed
| Mitchell & Road Comm |  | Excavation Quote | Excavation Quote - update Quote needed from Gridley | In Progress
| Allegra, Curtis, Patti |  | Grant Application: NYS DEC CSC | Submitted Grant Application COB: 7/26/19 | Completed
| Mitchell | Sand/Stone Quotes | Quotes for annual Sand/Stone | Rec'd Quotes. Ordered 660 yds from Kiser Sand & Gravel | Completed
Will need approx 750 yds additional; this is within the 2019 budget.
| Mitchell | Salt Quotes | Quotes for annual Salt | Rec'd verbal quotes. Submitted order (5/3) to NYS OGS for 55 tons w/ Cargill. | Completed
| Mitchell & Equipment Comm | Assess Equipment Needs | Purchased @28k; Repairs @ $14k | Posted, Rec'd, decline Bid. Will keep excator | Completed
| Mitchel & Patti | NYS & County Assoc.Dues | Hwy Supt decline to join | Hwy Supt notified NYS & County: decline membership | Completed
| Mitchel & Curtis & Patti | Rake Edge of Fileds | Rake/Repair edge of field of property owners due to snow removal | Field edges were assessed and repaired. | Completed
| Mitchel | Civil Service Forms | Submit updated Civil Service Forms | Hwy Employees raises (effective 6/1/19; (426 forms) | Completed
| Patti | Civil Service Forms | Submit updated Civil Service Forms | Hwy Supt raise and re-instated to Hwy Supt | Completed
| Mitchel & Patti | Order AED Supplies | AED Supplies & Set Up Account | Acct set up on-line, Supplies ordered & rec'd | Completed
In PROGRESS
| Mitchel | Work Logs | Complete Work Logs for all Hwy Work | Complete Work Sheets: Labor, Equipt, materials | In Progress
| Mitchel & Bldg Comm | Eectrical Needs @ Bldg | Obtained Quote for Electrical Repairs | Quote Rec'd & approved from Kap Krew; work date-COB 8/31 | In Progress
| Mitchel & Patti | Electrical Panel Box | Obtain Quote for Relocate Panel Box | Mitchel to call Kap Krew re Panel Box relocate from Bathroom | In Progress
| Mitchell & Curtis | Town Roads | Assess @ honing, pot holes, etc | Use item 4 & drag from shoulders,
|  |  | Roads Done: | Adair, Kirshman Hill, Buttermilk, Thompson Hill | Completed
|  |  | To Be Done: | Upper & Lower Hoose Rd, Morton, Piers, Stannard Hill, Gage-School House | In Progress
| Mitchel & Curtis & Patti | Hazard Mitigation Forms | Complete HMP Form for: Culverts | Intersection of Morton, Stannard Hill & Gage-School Hse | In Progress
|  | Contract Steve Bornt, DHSES | Complete HMP Form for: Culverts | Terpenings Road
|  |  | Complete HMP Form for: Culverts | Adair Road
|  |  | Complete HMP Form for: Culverts | Others
| Mitchell & Road Comm | Gage Road | CHIPS Project | Tubes & Prep Completed; CHIPS on August 28-29th | In Progress
| Mitchell & Road Comm | Town Roads | Ditching & Weeping & Brushing | Kirshman, Thompson, Hoose, Morton, Piers, Stannard, Gage-School Hs, Gage, LeFleuer | In Progress
|  | Note: Road Work deferred | Roads Done: | Kirshman Hill: Ditching | Completed
due to large amount of
work on Gage Road
| Mitchell & Equipment Comm | Assess Eqipment Needs | Truck #227 | Auction Intl: posted & A/R due $1850 | In Progress
|  |  | Truck #229 | Auction Intl: to be posted | In Progress
|  |  | 1 Ton Pick Up | Auction Intl: posted & A/R due $13,000 | In Progress
|  |  | Truck #65 | Scrapped & rec'd $1024.66 | Completed
|  |  | 10 Wheeler | Exploring purchase on web | In Progress
|  |  | Trailer - poor condition |  | In Progress
| Mitchell | Edwards Road | Tube Replacement & Enlargement | Work Date w/ Gridley: Aug 5-9th | Completed
| Mitchell |  | Note: FEMA expected to | Excavation for Tube & Tube installed | Completed
| Mitchell |  | extend completion date to | Excavation & Wall installed | Completed
| Mitchell |  | August 30, 2019! | Stone Align creek | Completed
| Mitchell |  |  | Road Elevation | Completed
| Mitchell |  | Work Force Reports | Labor, Fringe, Materials, Equipment Costs | in Progress
| Mitchel & Patti & Curtis | Note: Budgeted stone (300 tons) oversted. Only used approx 150 tons. Also, Work Hrs and Equipment rental costs understated. The extra stone will be used for Tube on Joslyn Road. Work Sheets will reflect some decreasse. Mitchel to review and finalize Work Force Reports. |  |  | In Progress
| Mitchell |  | Set Up Meeting W/Tom Cowin | T Cowin to inspect work completed | in Progress
| Mitchell & Road Comm | Breen Driveway | Taper/Tier side of Driveway |  | Completed
| Mitchell & Curtis |  | Hudro Seeding | Hwy Supt to set date with Otsego Co; J Clements | In Progress
| Charlie & Patti |  | Landscaping driveway & Sand pile | Supervisor & C Diamond to assess | In Progress
| Mitchell & Road Comm | Salt Shed | Excavation Quote | Excavation Quote - update Quote needed from Gridley | In Progress
DEFERRED
| Mitchel, Curtis, Patti | Buttermilk Hill Road | Assess Washout Area | Grading Done; J Clement to assess for NRCS Project | Deffered
| Mitchel, Curtis, Patti | Front Apron Excavation | New Quote for excavation work | Rec'd quote ($11,000) from S Gridley; need update quote | Deferred
| Mitchel, Curtis, Patti | Mitchel, Curtis, Patti | 2020 Budget - Prep Data for Hwy | Compile 2020 Budget data | Deferred