## Bid Schedule for Contractor Use
BID SCHEDULE
NAVAJO NATION DIVISION OF TRANSPORTATION
PROJECT: | N108(1-1)(3)1,2,4 | Date: June 11, 2026
LENGTH: | 0.249 km (0.155 miles)
ITEM | DESCRIPTION | Quantity | Units | Unit Bid Price | Total Price
10901-0000 | Extra & Miscellaneous Work - Authorized under Suppl. Spec. 109.02(s) of Exhibit F | All Required | Lump Sum | 200000 | 200000
15101-0000 | MOBILIZATION | LS | 1 | 0 | 0
15201-0000 | CONSTRUCTION SURVEY AND STAKING | LS | 1 | 0 | 0
15701-0000 | SOIL EROSION CONTROL, TEMPORARY | LS | 1 | 0 | 0
15703-1000 | SOIL EROSION CONTROL, TEMPORARY STRAW MULCH | HECTARE | 0.6 | 0 | 0
20102-0000 | CLEARING AND GRUBBING | LS | 1 | 0 | 0
20304-1000 | REMOVAL OF STRUCTURES AND OBSTRUCTIONS | LS | 1 | 0 | 0
20401-0000 | ROADWAY EXCAVATION | CU M | 920 | 0 | 0
20403-0000 | UNCLASSIFIED BORROW | CU M | 1390 | 0 | 0
20801-0000 | STRUCTURE EXCAVATION | CU M | 106 | 0 | 0
20803-0000 | STRUCTURE BACKFILL | CU M | 19 | 0 | 0
25112-1000 | WIRE ENCLOSED RIPRAP, CLASS 1 | CU M | 780 | 0 | 0
30101-0000 | AGGREGATE BASE COURSE, GRADING D | METRIC TON | 717 | 0 | 0
40301-0000 | ASPHALT CONCRETE PAVEMENT, TYPE 1 | METRIC TON | 379 | 0 | 0
41101-5000 | PRIME COAT, PENETRATING EMULSIFIED PRIME (PEP) | METRIC TON | 4.2 | 0 | 0
41201-1000 | TACK COAT, GRADE SS-1 | METRIC TON | 0.5 | 0 | 0
55102-1900 | HP 360 X 152 STEEL PILES, IN PLACE | METER | 105 | 0 | 0
55115-1000 | PREBORING | METER | 104 | 0 | 0
55120-0000 | TEST PILES | METER | 21 | 0 | 0
55201-0200 | STRUCTURAL CONCRETE, CLASS A (AE) | CU M | 241 | 0 | 0
55301-0500 | PRECAST, PRESTRESSED, CONCRETE STRUCTURAL MEMBERS, TYPE V - MODIFIED, (28.346 m) | EACH | 5 | 0 | 0
55401-1000 | REINFORCING STEEL | KILOGRAM | 5805 | 0 | 0
55401-2000 | REINFORCING STEEL, EPOXY COATED | KILOGRAM | 18950 | 0 | 0
55601-0900 | BRIDGE RAILING, STEEL | METER | 68 | 0 | 0
60405-0000 | MANHOLE ADJUSTMENT | EACH | 1 | 0 | 0
60812-0000 | PORTLAND CEMENT CONCRETE SPILLWAY, TYPE III AND TYPE IV | EACH | 4 | 0 | 0
60902-0400 | PORTLAND CEMENT CONCRETE CURB AND GUTTER, 152 mm DEPTH | METER | 460 | 0 | 0
60906-1000 | VALLEY GUTTER, CONCRETE, 152 mm DEPTH | SQ M | 40 | 0 | 0
61501-0100 | SIDEWALK, CONCRETE, 102 mm DEPTH | SQ M | 560 | 0 | 0
61701-5000 | GUARDRAIL SYSTEM SGR-20B TYPE PDE 02 w/ MSKT-TL3-8 END TERMINAL & THRIE BEAM TRANSITION | METER | 91 | 0 | 0
61901-1701 | FENCE, CHAIN LINK, 1372 mm HEIGHT | METER | 68 | 0 | 0
62101-0000 | RIGHT OF WAY MONUMENT | EACH | 16 | 0 | 0
62102-0000 | REFERENCE MARKER | EACH | 16 | 0 | 0
62510-1000 | SEEDING, DRY METHOD | HECTARE | 0.6 | 0 | 0
63302-0003 | SIGN INSTALLATION, 1 POST & HARDWARE: 4.10 kg/m | SQ M | 0.92 | 0 | 0
63302-0010 | SIGN INSTALLATION, 2 POSTS & HARDWARE: 2.98 kg/m | SQ M | 1.16 | 0 | 0
63308-3000 | OBJECT MARKERS, TYPE 3 WITH 1 POST AND HARDWARE: 2.98 kg/m | EACH | 4 | 0 | 0
63309-0020 | DELINEATORS, FLEXIBLE, TYPE 1b | EACH | 10 | 0 | 0
63401-1510 | PAVEMENT MARKINGS, TYPE H, SOLID YELLOW | METER | 490 | 0 | 0
63401-1520 | PAVEMENT MARKINGS, TYPE H, SOLID WHITE | METER | 470 | 0 | 0
63405-3260 | PAVEMENT MARKINGS, TYPE H, STOP BAR | EACH | 2 | 0 | 0
63501-0000 | TEMPORARY TRAFFIC CONTROL | LS | 1 | 0 | 0
|  |  | Subtotal: | 200000
|  |  | Navajo Nation Tax (6%): | 12000
| Contractor Name |  | Total Bid Price: | 212000
SCOPE-OF-WORK The proposed work consists of furnishing all labor, material, equipment and incidentals necessary for construction of 0.249 km (0.155 miles) of bridge reconstruction, earthwork, metal guardrail, drainage and roadway pavement, erosion control measures, traffic control, permanent signing and striping, and other miscellaneous construction in accordance with the specification and design drawings for this project. The quantities listed for each item is estimated and the unit price is applicable to each as given in the bid schedule above. The final pay quantity measurements shall be rounded to the significant figures given in this bid schedule for the final pay estimate. Payment for work performed on items furnished will be made in accordance with Sub-Section 109.05, Scope of Payment of FP-14. The Unit Bid Price must include all overhead, profit, and bonding.