| Recommendations | Action Steps | Owner | Due Date | Status | Progress Notes | Next Review Date | Metrics |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Clarify finance policy | Update draft; board approval; staff training | Jane Doe | 2025-10-15 | In Progress | Draft under board review | 2025-11-01 | Policy approved; 75% staff trained |
| Define pastoral roles | Create role descriptions; post openings | John Smith | 2025-09-30 | Not Started | Gathering input from elders | 2025-10-10 | Descriptions finalized; 2 roles filled |
| Launch member engagement survey | Design survey; distribute; analyze results | Mary Lee | 2025-11-05 | Completed | 120 responses; key themes identified | 2025-11-20 | 80% positive engagement feedback |
| Implement quarterly financial reviews | Schedule meetings; prepare reports | Finance Cmte | 2025-10-01 | In Progress | First meeting scheduled for next week | 2025-10-15 | 4 reviews completed by year-end |

# Consultant Recommendation Tracker

How to Use This Template

- Fill in each recommendation from your consultant’s report.

- Break down the recommendation into clear, actionable steps.

- Assign a single owner responsible for driving the action.

- Set realistic due dates and schedule the next review.

- Update Status and Progress Notes regularly.

- Track key Metrics to measure impact and celebrate wins.

Tips for Success

- Block time for your quarterly “report-review” meetings on your church calendar.

- Highlight completed items and wins in your congregational communications.

- In spreadsheets, apply conditional formatting to flag overdue or at-risk actions.

- Invite your consultant back for periodic check-ins aligned with your Next Review Date.

Feel free to adapt column names or add rows as needed. This tracker will keep your consulting recommendations active, visible, and moving forward.